## GanttChart
[BDS App] Project Schedule
Hello World Team
| Project Start Date | 2019-10-14 |  |  |  |  | Display Week | 5 | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12
| Project Lead | Đạt Huỳnh | [6 empty] | 2019-11-11 | [6 empty] | 2019-11-18 | [6 empty] | 2019-11-25 | [6 empty] | 2019-12-02 | [6 empty] | 2019-12-09 | [6 empty] | 2019-12-16 | [6 empty] | 2019-12-23 | [6 empty] | 2019-12-30
 | time axis 2019-11-11 to 2020-01-05
WBS | TASK | ASSIGN | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2019-11-11 to 2020-01-05
1 | Planing |  |  | 2019-10-14 | 2019-11-06 | 24
1.1 | Project Management Plan & Process |  |  | 2019-10-14 | 2019-10-30 | 17 | 97.5% | 15
1.1.1 | Create Communication Plan | Đạt Huỳnh |  | 2019-10-14 | 2019-10-15 | 2 | 100% | 2
1.1.2 | Create Configuration Plan | Đạt Huỳnh |  | 2019-10-15 | 2019-10-16 | 2 | 90% | 2
1.1.3 | Create Project Charter | Quốc Nhân |  | 2019-10-17 | 2019-10-19 | 3 | 100% | 3
1.1.4 | Create Project Plan | Quốc Nhân |  | 2019-10-21 | 2019-10-23 | 3 | 90% | 3
1.1.5 | Create Development Process | Đạt Huỳnh |  | 2019-10-21 | 2019-10-23 | 3 | 100% | 3
1.1.6 | Create Quality Management Plan | Quang Vương |  | 2019-10-24 | 2019-10-26 | 3 | 100% | 3
1.1.7 | Create Measurement Plan | Anh Minh |  | 2019-10-28 | 2019-10-30 | 3 | 100% | 3
1.1.8 | Create Risk Management Plan | Anh Minh |  | 2019-10-28 | 2019-10-30 | 3 | 100% | 3
1.2 | Requirement Plan and Process |  |  | 2019-10-24 | 2019-10-26 | 3 | 100% | 3
1.2.1 | Create Requirement Plan | Như Phương |  | 2019-10-24 | 2019-10-26 | 3 | 100% | 3
1.2.2 | Create Requirement Process | Như Phương |  | 2019-10-24 | 2019-10-26 | 3 | 100% | 3
1.3 | Architecture Plan and Process |  |  | 2019-10-28 | 2019-10-31 | 4 | 100% | 4
1.3.1 | Create Architecture Plan | Quang Vương |  | 2019-10-28 | 2019-10-31 | 4 | 100% | 4
1.3.2 | Create Architecture Process | Quang Vương |  | 2019-10-28 | 2019-10-31 | 4 | 100% | 4
1.4 | Details Design Plan and Process |  |  | 2019-10-31 | 2019-11-02 | 3 | 100% | 3
1.4.1 | Create Details Design Process | Quốc Nhân |  | 2019-10-31 | 2019-11-02 | 3 | 100% | 3
1.5 | Implementation Plan and Process |  |  | 2019-11-04 | 2019-11-06 | 3 | 100% | 3
1.5.1 | Create Implementation Plan | Quốc Nhân |  | 2019-11-04 | 2019-11-06 | 3 | 100% | 3
1.5.2 | Create Implementation Process | Quốc Nhân |  | 2019-11-04 | 2019-11-06 | 3 | 100% | 3
1.6 | Test Plan and Process |  |  | 2019-11-07 | 2019-11-09 | 3 | 100% | 3
1.6.1 | Create Test Plan | Như Phương |  | 2019-11-07 | 2019-11-09 | 3 | 100% | 3
1.6.2 | Create Test Process | Như Phương |  | 2019-11-07 | 2019-11-09 | 3 | 100% | 3
1.7 | Trainning Plan |  |  | 2019-11-07 | 2019-11-09 | 3 | 100% | 3
1.7.1 | Create Trainning Plan | Anh Minh |  | 2019-11-07 | 2019-11-09 | 3 | 100% | 3
2 | Analysing & Training |  |  | 2019-11-11 | 2019-12-16 | 36
2.1 | Requirement |  |  | 2019-11-11 | 2019-11-16 | 6 | 3.333% | 6
2.1.1 | Release S.R.S | All Menber Team |  | 2019-11-11 | 2019-11-16 | 6 | 10% | 6
2.1.2 | Release ConOp | All Menber Team |  | 2019-11-13 | 2019-11-16 | 4 |  | 4
2.1.3 | Release Tracebility Matrix | All Menber Team |  | 2019-11-14 | 2019-11-16 | 3 |  | 3
2.2 | Architecture and Design |  |  | 2019-11-18 | 2019-11-20 | 3 |  | 3
2.2.1 | Release Architecture Driver |  |  | 2019-11-18 | 2019-11-21 | 4 |  | 4
2.2.2 | Release Architecture Design |  |  | 2019-11-20 | 2019-11-22 | 3 |  | 3
2.2.3 | Release Details Design |  |  | 2019-11-21 | 2019-11-23 | 3 |  | 3
2.3 | Risk Management |  |  | 2019-11-18 | 2019-11-23 | 6 |  | 6
2.4 | Training |  |  | 2019-11-25 | 2019-12-21 | 27 |  | 24
3 | Implementation & Testing |  |  | 2019-12-23 | 2020-04-30 | 130 |  | 88
3.1 |  |  |  |  | - |  |  | 0
3.2 |  |  |  |  | - |  |  | 0
3.3 |  |  |  |  | - |  |  | 0
3.4 |  |  |  |  | - |  |  | 0
3.5 |  |  |  |  | - |  |  | 0
TEMPLATE ROWS
See the Help worksheet to learn how to use these template rows. You can hide these rows before printing.
1 | [ Level 1 Task, Category, or Phase ]
1.1 | . [ Level 2 Task ] |  |  |  | - |  | 0% | 0
1.1.1 | . . [ Level 3 Task ] |  |  |  | - |  | 0% | 0
1.1.1.1 | . . . [ Level 4 Task ] |  |  |  | - |  | 0% | 0
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.