## Slide 1
2019
2020
Today
Week 1
4
7
10
13
16
19
22
25
28
6 days
100%
Oct 14 - Oct 19
Kick-Off
18 days
70%
Oct 21 - Nov 9
Planning
36 days
38%
Nov 11 - Dec 21
Analysing
112 days
40%
Dec 23 - Apr 30
Implementation & Testing
24 days
Jan 13 - Feb 9
Tet Holiday
1 day
Apr 30
Close Project
24 days
Nov 25 - Dec 21
Training
End Phase Planning (Review Documments)
Nov 9
Release RE & AR & DD
Dec 7
Close Project
Apr 30
EOMP#1
Nov 16
Release Function 1
Dec 28
Release Function 2
Jan 4
Release Function 3
Jan 11
Release Function 4
Feb 15
Release Function 5
Feb 15
Release Function 6
Feb 15