## WBS Phase 1
Project Title
Project Manager | Đạt Huỳnh
Phase One | Planning
WBS Number | Task Title | Task Owner | Start Date | Due Date | Duration | % of Task Complete | Week 1 | [5 empty] | Week 2 | [5 empty] | Week 3 | [5 empty] | Week 4
[7 empty] | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa
1 | Project Management Plan & Process | [5 empty] | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18 | 2019-10-19 | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-26 | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31 | 2019-11-01 | 2019-11-02 | 2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09
1.1 | Create Communication Plan | Đạt Huỳnh | 2019-10-14 | 2019-10-15 | 2 | 100% | bar: 2019-10-14 to 2019-10-15
1.2 | Create Configuration Plan | Đạt Huỳnh | 2019-10-15 | 2019-10-16 | 2 | 90% | bar: 2019-10-15 to 2019-10-16
1.3 | Create Project Charter | Quốc Nhân | 2019-10-17 | 2019-10-19 | 3 | 100% | bar: 2019-10-17 to 2019-10-26
1.4 | Create Project Plan | Quốc Nhân | 2019-10-21 | 2019-10-23 | 3 | 90%
1.5 | Create Development Process | Đạt Huỳnh | 2019-10-21 | 2019-10-23 | 3 | 100%
1.6 | Create Quality Management Plan | Quang Vương | 2019-10-24 | 2019-10-26 | 3 | 100%
1.7 | Create Measurement Plan | Anh Minh | 2019-10-28 | 2019-10-30 | 3 | 100% | bar: 2019-10-21 to 2019-10-30
1.8 | Create Risk Management Plan | Anh Minh | 2019-10-28 | 2019-10-30 | 3 | 100% | bar: 2019-10-21 to 2019-10-30
2 | Requirement Plan and Process
2.1 | Create Requirement Plan | Như Phương | 2019-10-24 | 2019-10-26 | 3 | 100%
2.2 | Create Requirement Process | Như Phương | 2019-10-24 | 2019-10-26 | 3 | 100%
3 | Architecture Plan and Process
3.1 | Create Architecture Plan | Quang Vương | 2019-10-28 | 2019-10-31 | 4 | 100% | bar: 2019-10-21 to 2019-10-30
3.2 | Create Architecture Process | Quốc Nhân | 2019-10-28 | 2019-10-31 | 4 | 100% | bar: 2019-10-21 to 2019-10-30
4 | Details Design Plan and Process
4.1 | Create Details Design Process | Đạt Huỳnh | 2019-10-31 | 2019-11-02 | 3 | 100% | bar: 2019-10-31 to 2019-11-09
5 | Implementation Plan and Process
5.1 | Create Implementation Plan | Quốc Nhân | 2019-11-04 | 2019-11-06 | 3 | 100%
5.2 | Create Implementation Process | Quốc Nhân | 2019-11-04 | 2019-11-06 | 3 | 100%
6 | Test Plan and Process
6.1 | Create Test Plan | Như Phương | 2019-11-07 | 2019-11-09 | 3 | 100%
6.2 | Create Test Process | Như Phương | 2019-11-07 | 2019-11-09 | 3 | 100%
7 | Trainning Plan
7.1 | Create Trainning Plan | Quang Vương | 2019-11-07 | 2019-11-09 | 3 | 100%
Formulas:
Duration = DAYS([Due Date],[Start Date])+1

## WBS Phase 2
Project Title
Project Manager | Đạt Huỳnh
Phase Two | Analysing & Training
WBS Number | Task Title | Task Owner | Start Date | Due Date | Duration | % of Task Complete | Week 5 | [5 empty] | Week 6 | [5 empty] | Week 7 | [5 empty] | Week 8 | [5 empty] | Week 9 | [5 empty] | Week 10
[7 empty] | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa
| Requirement | [5 empty] | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14 | 2019-11-15 | 2019-11-16 | 2019-11-18 | 2019-11-19 | 2019-11-20 | 2019-11-21 | 2019-11-22 | 2019-11-23 | 2019-11-25 | 2019-11-26 | 2019-11-27 | 2019-11-28 | 2019-11-29 | 2019-11-30 | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-06 | 2019-12-07 | 2019-12-09 | 2019-12-10 | 2019-12-11 | 2019-12-12 | 2019-12-13 | 2019-12-14 | 2019-12-16 | 2019-12-17 | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21
| Release S.R.S |  | 2019-11-11 | 2019-11-16 | 6 | bar: 2019-11-11
| Release ConOp |  | 2019-11-13 | 2019-11-16 | 4
| Release Tracebility Matrix |  | 2019-11-14 | 2019-11-16 | 3
Architecture and Design
| Release Architecture Driver |  | 2019-11-18 | 2019-11-21 | 4
| Release Architecture Design |  | 2019-11-20 | 2019-11-22 | 3
| Release Details Design |  | 2019-11-21 | 2019-11-23 | 3
| Training |  | 2019-11-25 | 2019-12-21 | 27
Formulas:
Duration = DAYS([Due Date],[Start Date])+1

## WBS Phase 3
Project Title
Project Manager | Đạt Huỳnh
Phase Two | Implementation & Testing
WBS Number | Task Title | Task Owner | Start Date | Due Date | Duration | % of Task Complete | Week 11 | [5 empty] | Week 12 | [5 empty] | Week 13 | [5 empty] | Week 14 | [5 empty] | Week 15 | [5 empty] | Week 16 | [5 empty] | Week 17 | [5 empty] | Week 12 | [5 empty] | Week 13 | [5 empty] | Week 20 | [5 empty] | Week 21 | [5 empty] | Week 22 | [5 empty] | Week 23 | [5 empty] | Week 24 | [5 empty] | Week 25 | [5 empty] | Week 26 | [5 empty] | Week 27 | [5 empty] | Week 28 | [5 empty] | Week 29
[7 empty] | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa
Implementation | time axis 2019-12-23 to 2020-05-02
1
1
1
Testing
1
1
1
Deloyment
1
1
1
Formulas:
Duration = DAYS([Due Date],[Start Date])+1