## Summary
Actual | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Total
Đạt Huỳnh | 30 | 22 | 0 | [34 empty] | 52
Quốc Nhân | 26 | 30 | [35 empty] | 56
Vương Trương | 26.5 | 18.5 | [35 empty] | 45
Anh Minh | 24 | 27 | [35 empty] | 51
Như Phương | #REF! | #REF! | [35 empty] | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Planed | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Total
Đạt Huỳnh | 30 | 34 | 38 | [34 empty] | 102
Quốc Nhân | 26 | 30 | [35 empty] | 56
Vương Trương | 27.5 | 22 | [35 empty] | 49.5
Anh Minh | 28 | 30 | [35 empty] | 58
Như Phương | #REF! | #REF! | [35 empty] | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Đạt Huỳnh
Timelog: | Đạt Huỳnh
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
1 | Monday | Meeting Mentor |  | 14/10/2019 | 4 | 4 | Done
1 | Tuesday | Training | Resreach information WebGIS | 15/10/2019 | 6 | 6 | Inprogress
1 | Wednesday | Training | Resreach coding language | 16/10/2019 | 6 | 6 | Inprogress
1 | Thursday | Project Management | Resreach & Create template documments | 17/10/2019 | 4 | 4 | Done
1 | Friday | Meetting Customer |  | 18/10/2019 | 4 | 4 | Done
1 | Saturday | Project Management | Create Comunication plan | 19/10/2019 | 6 | 6 | Done
Total | Actual: | 30 |  |  |  | Plan: | 30
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
2 | Monday | Project Management | Create Configuration Management Plan | 21/10/2019 | 6 | 6 | Inprogress
2 | Tuesday | Project Management | Create Configuration Management Plan | 22/10/2019 | 6 | 6 | Inprogress | PM_ConfigurationManagementPlan_Ver1.0.docx
2 | Wednesday | Meeting Mentor |  | 23/10/2019 | 4 | 4 | Done
2 | Thursday | Project Management | Create TimeLog | 24/10/2019 | 6 | 6 | Done
2 | Friday | Training | Reading Customer Documments | 25/10/2019 |  | 6
2 | Saturday | Training | Presentation Customer Documments | 26/10/2029 |  | 6
Total | Actual: | 22 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
3 | Monday | Project Management | Create Control&Monitoring Project | 2019-10-28 |  | 6 | Inprogress
3 | Tuesday | Project Management | Create Control&Monitoring Project | 2019-10-29 |  | 6 | Done
3 | Tuesday | Meeting Mentor |  | 2019-11-29 |  | 4
3 | Wednesday | Meetting Customer |  | 2019-10-30 |  | 4
3 | Thursday | Project Management | Create Timeline | 2019-10-31 |  | 6
3 | Friday | Project Management | Create EVM | 2019-11-01 |  | 6
3 | Saturday | Project Management | Create EVM | 2019-11-02 |  | 6
Total | Actual: | 0 |  |  |  | Plan: | 38
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
4 | Monday |  |  | 2019-11-04
4 | Tuesday |  |  | 2019-11-05
4 | Wednesday |  |  | 2019-11-06
4 | Thursday |  |  | 2019-11-07
4 | Friday |  |  | 2019-11-08
4 | Saturday | Project Management | Review Documents | 2019-11-09
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
5 | Monday |  |  | 2019-11-11
5 | Tuesday |  |  | 2019-11-12
5 | Wednesday |  |  | 2019-11-13
5 | Thursday |  |  | 2019-11-14
5 | Friday |  |  | 2019-11-15
5 | Saturday |  |  | 2019-11-16
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
6 | Monday |  |  | 2019-11-18
6 | Tuesday |  |  | 2019-11-19
6 | Wednesday |  |  | 2019-11-20
6 | Thursday |  |  | 2019-11-21
6 | Friday |  |  | 2019-11-22
6 | Saturday |  |  | 2019-11-23
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
7 | Monday |  |  | 2019-11-25
7 | Tuesday |  |  | 2019-11-26
7 | Wednesday |  |  | 2019-11-27
7 | Thursday |  |  | 2019-11-28
7 | Friday |  |  | 2019-11-29
7 | Saturday |  |  | 2019-11-30
Total | Actual: | 0 |  |  |  | Plan: | 0

## Quốc Nhân
Timelog: | Quốc Nhân
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
1 | Monday | Meeting Mentor |  | 14/10/2019 | 4 | 4 | Done
1 | Tuesday | Training | Research Information WebGIS | 15/10/2019 | 4 | 4 | Inprogress
1 | Wednesday | Training | Research Information WebGIS | 16/10/2019 | 5 | 5 | Inprogress
1 | Thursday | Project Management | Create Member Charter | 17/10/2019 | 5 | 5 | Done
1 | Friday | Meetting Customer |  | 18/10/2019 | 4 | 4 | Done
1 | Saturday | Training | Research WebGIS, Database & Code | 19/10/2019 | 4 | 4 | Inprogress
Total | Actual: | 26 |  |  |  | Plan: | 26
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
2 | Monday | Project Management | Create Team Charter | 21/10/2019 | 6 | 6 | Done | PM_TeamCharter_Ver1.0.docx
2 | Tuesday | Training | Research Information WebGIS | 22/10/2019 | 5 | 5 | Inprogress
2 | Wednesday | Meeting Mentor |  | 23/10/2019 | 4 | 4 | Done
2 | Thursday | Project Management | Draw the steps submitted and changed github & gg drive | 24/10/2019 | 5 | 5 | Done | PM_ConfigurationManagementPlan_Ver1.0.docx
2 | Friday | Training | Reading Customer Documments | 25/10/2019 | 5 | 5 | Done
2 | Saturday | Training | Presentation Customer Documments | 26/10/2019 | 5 | 5 | Done
Total | Actual: | 30 |  |  |  | Plan: | 30
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
3 | Monday | Project Management | Create Project plan v1.0, Install Android studio, Genymotion | 2019-10-28 | 8 |  | Done
3 | Tuesday | Project Management | Research Information React Native, Update Project plan v1.1 | 2019-10-29 | 10 |  | Inprogress | PM_ProjectPlan_Ver1.1.docx
3 | Wednesday | Meetting Customer | Meeting with Customer, Update Project plan v1.2 | 2019-10-30 | 5 |  | Inprogress | PM_ProjectPlan_Ver1.2.docx
3 | Thursday | Project Management | Install React Native | 2019-10-31 | 10 |  | Inprogress
3 | Friday | Meetting Customer | Install React Native | 2019-11-01 | 5 |  | Inprogress
3 | Saturday | Project Management | Update Project plan v1.3, Create project charter v1.0 | 2019-11-02 | 4 |  | Inprogress | PM_ProjectPlan_Ver1.3.docx
3 | Sunday | Implementation | Install React Native | 2019-11-03 | 3 |  | Done
Total | Actual: | 45 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
4 | Monday | Project Management | Create Question function v1.0, update project charter v1.0, update Milestone v1.0 | 2019-11-04 | 7 |  |  | PM_ProjectCharter_Ver1.0.docx, PM_Question_Ver1.0.xlxs, PM_Milestone_Ver1.0.xlxs
4 | Tuesday | Meeting Mentor | Review documents | 2019-11-05 | 3
4 | Wednesday | Requirement | Create SRS v1.0, implement plan v1.0 | 2019-11-06 | 10 |  |  | PM_SRS_Ver1.0.docx, PM_Implementplan_Ver1.0.docx
4 | Thursday | Project Management | Update implement process v1.1 | 2019-11-07 | 5 |  |  | PM_Implementprocess_Ver1.0.docx
4 | Friday | Project Management | Update detail design, training plan, RE plan | 2019-11-08 | 8
4 | Saturday | Project Management | Review documents | 2019-11-09 | 5
2019-11-10
Total | Actual: | 38 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
5 | Monday |  |  | 2019-11-11
5 | Tuesday |  |  | 2019-11-12
5 | Wednesday |  |  | 2019-11-13
5 | Thursday |  |  | 2019-11-14
5 | Friday |  |  | 2019-11-15
5 | Saturday |  |  | 2019-11-16
2019-11-17
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
6 | Monday |  |  | 2019-11-18
6 | Tuesday |  |  | 2019-11-19
6 | Wednesday |  |  | 2019-11-20
6 | Thursday |  |  | 2019-11-21
6 | Friday |  |  | 2019-11-22
6 | Saturday |  |  | 2019-11-23
2019-11-24
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
7 | Monday | Project Management | Create UC description RE (UC 25-36) | 2019-11-25 | 10 |  |  | RE_UseCaseDescription_V1.0
7 | Tuesday | Meeting Mentor | Show UCDescription RE, Quality Attribute | 2019-11-26 | 3
7 | Wednesday | Architecture and Desgin | Update Architecture Drive V1.0 | 2019-11-27 | 10 |  |  | PM_architecturedrive_V1.0
7 | Thursday | Architecture and Desgin | Create detail design (module login/logout admin & website) | 2019-11-28 | 10
7 | Friday | Requirement | Create tracebility metrix | 2019-11-29 | 6 |  |  | RE_Tracebilitymetrix_V1.0
7 | Saturday | Requirement | Review ERD, datadictionary for RE | 2019-11-30 | 8 |  |  | RE_SRS_V1.1
7 | Sunday | Requirement | Update SRS document | 2019-12-01 | 3 |  |  | RE_SRS_V1.1
Total | Actual: | 50 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
8 | Monday | Architecture and Desgin | Create Business rule, massage list | 2019-12-02 | 10 |  |  | DE_BusinessRule_V1.0, DE_MessageList_V1.0
8 | Tuesday | Meeting Mentor |  | 2019-12-03
8 | Wednesday | Architecture and Desgin |  | 2019-12-04
8 | Thursday | Architecture and Desgin |  | 2019-12-05
8 | Friday | Requirement |  | 2019-12-06
8 | Saturday | Requirement |  | 2019-12-07
8 | Sunday | Requirement |  | 2019-12-08
Total | Actual: | 10 |  |  |  | Plan: | 0

## Vương Trương
Timelog:
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
1 | Monday | Meeting Mentor |  | 14/10/2019 | 4 | 4 | Done
1 | Tuesday | Training | research webgis | 15/10/2019 | 5 | 5 | Inprogress
1 | Wednesday | Training | research webgis | 16/10/2019 | 4.5 | 4.5 | Inprogress
1 | Thursday | Training | find another app like webgis | 17/10/2019 | 5 | 5 | Done
1 | Friday | Meetting Customer |  | 18/10/2019 | 4 | 4 | Done
1 | Saturday | Training |  | 2019-10-19 | 4 | 5 | Inprogress
Total | Actual: | 26.5 |  |  |  | Plan: | 27.5
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
2 | Monday | Project Management | choose model | 2019-10-21 | 5.5 | 6 | Done
2 | Tuesday | Training | Install qgis | 2019-10-22 | 5 | 6 | Done
2 | Wednesday | Meeting Mentor |  | 2019-10-23 | 4 | 4 | Done
2 | Thursday | Project Management | research webgis | 2019-10-24 |  |  | Done
2 | Friday | Training | Readding Customer Documments | 2019-10-25 |  |  | Done
2 | Saturday | Training | Presentation Customer Documments | 2019-10-26 | 4 | 6 | Done
Total | Actual: | 18.5 |  |  |  | Plan: | 22
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
3 | Monday
3 | Tuesday
3 | Wednesday
3 | Thursday
3 | Friday
3 | Saturday
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
4 | Monday
4 | Tuesday
4 | Wednesday
4 | Thursday
4 | Friday
4 | Saturday
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
5 | Monday
5 | Tuesday
5 | Wednesday
5 | Thursday
5 | Friday
5 | Saturday
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
6 | Monday
6 | Tuesday
6 | Wednesday
6 | Thursday
6 | Friday
6 | Saturday
Total | Actual: | 0 |  |  |  | Plan: | 0

## Anh Minh
Timelog:
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
1 | Monday | Meeting Mentor |  | 14/10/2019 | 4 | 4 | Done
1 | Tuesday | Training | Research WebGIS | 15/10/2019 | 5 | 5 | Inprogress
1 | Wednesday | Training | Research WebGIS | 16/10/2019 | 3 | 5 | Inprogress
1 | Thursday | Training | Research WebGIS | 17/10/2019 | 3 | 5 | Inprogress
1 | Friday | Meetting Customer |  | 18/10/2019 | 4 | 4 | Done
1 | Saturday | Training |  | 19/10/2019 | 5 | 5 | Inprogress
Total | Actual: | 24 |  |  |  | Plan: | 28
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
2 | Monday | Training | Readding Incremental Model | 21/10/2019 | 5 | 5 | Done
2 | Tuesday | Training | Readding Geodatabase | 22/10/2019 | 3 | 5 | Done
2 | Wednesday | Meeting Mentor |  | 23/10/2019 | 4 | 4 | Done
2 | Thursday | Training | Setting and research QGIS | 24/10/2019 | 7 | 5 | Done
2 | Friday | Training | Readding Customer Documments | 25/10/2019 | 4 | 5 | Done
2 | Saturday | Training | Presentation Customer Documments | 26/10/2019 | 4 | 6 | Done
Total | Actual: | 27 |  |  |  | Plan: | 30
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
3 | Monday
3 | Tuesday
3 | Wednesday
3 | Thursday
3 | Friday
3 | Saturday
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
4 | Monday
4 | Tuesday
4 | Wednesday
4 | Thursday
4 | Friday
4 | Saturday
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
5 | Monday
5 | Tuesday
5 | Wednesday
5 | Thursday
5 | Friday
5 | Saturday
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
6 | Monday
6 | Tuesday
6 | Wednesday
6 | Thursday
6 | Friday
6 | Saturday
Total | Actual: | 0 |  |  |  | Plan: | 0

## Như Phương
Timelog:
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
1 | Monday | Meeting Mentor |  | 14/10/2019 | 4 | 4 | Done
1 | Tuesday | Project Management | Research project | 15/10/2019 | 5 | 6 | Done
1 | Wednesday | Project Management | Research project | 16/10/2019 | 5 | 6 | Done
1 | Thursday | Project Management | Research project | 17/10/2019 | 5 | 5 | Done
1 | Friday | Meetting Customer |  | 18/10/2019 | 4 | 4 | Done
1 | Saturday | Project Management | Complete the meeting minutes | 19/10/2019 | 4 | 5 | Done | Meeting_Mentor_14/10/2019 Meeting-customer_18/10/2019
Total | Actual: | 27 |  |  |  | Plan: | 30
2 | Monday | Project Management | Userstory | 21/10/2019 | 5 | 4 | Done
2 | Tuesday | Project Management | research software process model | 22/10/2019 | 5 | 5 | Done
2 | Wednesday | Meeting Mentor |  | 23/10/2019 | 4 | 5 | Done
2 | Thursday | Project Management | Research GIS | 24/10/2019 | 5 | 5 | Done
2 | Friday | Project Management | Research GIS | 25/10/2019 | 5 | 5 | Done
2 | Saturday | Project Management | Complete the meeting minutes ; Present document GIS with team | 26/10/2019 | 5 | 6 | Done | Meeting_Mentor_23/10/2019
Total | Actual: | 29 |  |  |  | Plan: | 30
3 | Monday | Project Management | Research GIS , prepare question for customer Test plan | 28/10/2019 | 5.5 | 6 | Inprogress
3 | Tuesday | Meeting Mentor |  | 29/10/2019 | 4 | 4 | Done
3 | Wednesday | Meetting Customer |  | 30/10/2019 | 4.5 | 5 | Done
3 | Thursday | Project Management | Test plan | 31/10/2019 | 5 | 6 | Done | TE_Testplan_ver1.0
3 | Friday | Project Management | Research React | 2019-01-11 | 4.5 | 6 | Done
3 | Saturday | Project Management | Complete the meeting minutes ; Requiment plan | 2019-02-11 | 6 | 6 | Inprogress | Meeting_Customer_29/10/2019 Meeting_Mentor _30/10/2019
Total | Actual: | 29.5 |  |  |  | Plan: | 33
4 | Monday | Project Management | Requiment plan | 2019-11-04 | 5.5 | 6 | Done | RE_RequimentPlan_ver1.0
4 | Tuesday | Project Management | Requiment process | 2019-11-05 | 5 | 6 | Done | RE_RequimentProcess_ver1.0
4 | Wednesday | Meeting Mentor |  | 2019-11-06 | 4.5 | 4 | Done
4 | Thursday | Project Management | Test Process | 2019-11-07 | 5 | 6 | Inprogress
4 | Friday | Meetting Customer |  | 2019-11-08 | 4.5 | 6 | Done
4 | Saturday | Project Management | Complete the meeting minutes ; Review document , test process | 2019-11-09 | 7 | 6 | Inprogress | TE_Testprocess_ver1.0
Total | Actual: | 31.5 |  |  |  | Plan: | 34
5 | Monday | Project Management | Complete the meeting minutes ; Review document Analyst Requirement | 2019-11-10 | 6 | 6 | Done | Meeting_customer 8/10/2019 Meeting_mentor 6/10/2019
5 | Tuesday | Meeting Mentor |  | 2019-11-11 | 4 | 4 | Done
5 | Wednesday | Project Management | ConOP document | 2019-11-12 | 5 | 6 | Inprogress
5 | Thursday | Project Management | Usecase Decription | 2019-11-13 | 5 | 6 | Inprogress
5 | Friday | Project Management | Prepare EOMP #1 Update document | 2019-11-14 | 4.5 | 6 | Done
5 | Saturday | Project Management | Present EOMP1 Complete the meeting minutes Report document for customer | 2019-11-15 | 6 | 6 | Done
Total | Actual: | 30.5 |  |  |  | Plan: | 34
6 | Monday | Project Management |  | 2019-11-17 | 6 | 6 | Done
6 | Tuesday | Meeting Mentor |  | 2019-11-18 | 4 | 4 | Done
6 | Wednesday | Project Management |  | 2019-11-19 | 5 | 6 | Inprogress
6 | Thursday | Project Management |  | 2019-11-20 | 5 | 6 | Inprogress
6 | Friday | Project Management |  | 2019-11-21 | 4.5 | 6 | Done
6 | Saturday | Project Management | Complete the meeting minutes | 2019-11-22 | 6 | 6 | Done
Total | Actual: | 30.5 |  |  |  | Plan: | 34
7 | Monday | Project Management | Complete RE document | 2019-11-24 | 6 | 6 | Done
7 | Tuesday | Meeting Mentor |  | 2019-11-25 | 4 | 4 | Done
7 | Wednesday | Project Management | Architure Driver | 2019-11-26 | 5 | 6 | Done
7 | Thursday | Project Management | Architure Driver | 2019-11-27 | 6.5 | 6 | Done
7 | Friday | Project Management | Update ConOP | 2019-11-28 | 5 | 6 | Done
7 | Saturday | Project Management | Review document Complete the meeting minutes | 2019-11-29 | 6 | 6 | Done
Total | Actual: | 32.5 |  |  |  | Plan: | 34
8 | Monday | Project Management | Context Diagram | 2019-12-01 | 6 | 6 | Done
8 | Tuesday | Meeting Mentor |  | 2019-12-02 | 4 | 4 | Done
8 | Wednesday | Project Management | Architure Design | 2019-12-03 | 6 | 6 | Inprogress
8 | Thursday | Project Management | Usecase Decription | 2019-12-04 | 4 | 6 | Inprogress
8 | Friday | Project Management | ERD | 2019-12-05 | 5.5 | 6 | Done
8 | Saturday | Project Management | Complete the meeting minutes Review document | 2019-12-06 | 6 | 6 | Done
8
8 | Actual: | 31.5 |  |  |  | Plan: | 34
9 | Monday | Project Management | Install React Native | 2019-12-08 | 6 | 6 | Done
9 | Tuesday | Project Management | TEst Case | 2019-12-09 | 5 | 6 | Done
9 | Wednesday | Project Management | Detail Design | 2019-12-10 | 6 | 6 | Inprogress
9 | Thursday | Project Management | Test Case | 2019-12-11 | 6 | 6 | Done
9 | Friday | Meetting Customer |  | 2019-12-12 | 4 | 4 | Inprogress
9 | Saturday | Project Management | Complete the meeting minutes Review document | 2019-12-13 | 6 | 6 | Done
9
9 | Actual: | 33 |  |  |  | Plan: | 34
10 | Monday | Project Management | publish applications to AppStore | 2019-12-15 | 6 | 6 | Done
10 | Tuesday | Project Management | publish applications to GoogleStore | 2019-12-16 | 4 | 4 | Done
10 | Wednesday | Project Management | Research WebGIS | 2019-12-17 | 6 | 6 | Done
10 | Thursday | Meeting Mentor |  | 2019-12-18 | 4 | 6 | Done
10 | Friday | Project Management | Setting and research QGIS | 2019-12-19 | 5 | 6 | Done
10 | Saturday | Project Management | Complete the meeting minutes Review document | 2019-12-20 | 6 | 6 | Done
10
10 | Actual: | 31 |  |  |  | Plan: | 34