## Slide 1
Presentation For Capstone
CAPSTONE PROJECT
“App quản lý công ty BĐS”
Team 3: Hello World
Mentor: Đặng Đình Hòa

## Slide 2
Team introduction
1.
Project overview.
Architectural.
Agenda
Monitoring & control.
2.
3.
4.
5.
Summary test report.
6.
Risk management
7.
Problem project
Agenda
8.
Lesson learned & Demo.

## Slide 3
LOGO TEAM
STAKEHOLDERS
1. TEAM INTRODUCTION
Name | Role
Mr. Trần Minh Châu | Customer
Mr. Nguyễn Hữu Nhật | Customer

## Slide 4
TEAM MEMBER
Huỳnh Tuấn Đạt
Trương Quang Vương
Phạm Quốc Nhân
Trịnh Nhu Phương
Nguyễn Anh Minh
CODER
4
CODER
CODER
TESTER
DESIGNER

## Slide 5: 2. Project overview
Project introduction
Currently, housing demand is a big problem for people across the country, so homeowners are looking to provide housing through real estate applications.
Real Estate App, built for internal users to manage projects, manage statistics, reports and many other functions.
The App also helps employees know more about essential information about the real estate industry such as real estate projects, employee sales, group and room sales.
5

## Slide 6: 2. Project overview
Number of people in the company
Stakeholders | Number of people
Director | 1 people
Department Heads | ~10 people
Administrator | ~1 people
Employees | ~150 people
Deputy department | ~5 people
6

## Slide 7: 2. Project overview
Business constraints
7
# | Business Rules | Business Rules
1 | BR1 | When employees leave, the account will be hidden.
2 | BR2 | Staff only view and register applications
3 | BR3 | Only the administrator can update the information
4 | BR4 | Only director can approve employee applications
5 | BR5 | Unapproved applications will be canceled and not saved in history
6 | BR6 | Admin to update information continuously or when there is information from leaders and departments
7 | BR7 | Admin cannot use App Mobile to import files, etc.

## Slide 8: 2. Project overview
Technical constraints
8
System: | Programming language App: | Programming language Website: | Database: | Communication
Website (browser: Firefox, Chrome, Cốc cốc,..) | Code: Javascript | Code: javascript | Database: Firebase | Zalo and facebook
App (platform: Ios & Android). | Framework: React native | Framework: Vuejs | Document: github | 

## Slide 9: 3. Monitoring & control
9
Total work for module 1 | 58
Total work for module 2 | 28
Total work for module 3 | 79
Job chart

## Slide 10: 3. Monitoring & control
Plan chart (DK) (hours)
10
Total actual time of module completion 1 | 985 hours
Total actual time of module completion 2 | 744 hours
Total actual time of module completion 3 | 2047 hours

## Slide 11: 3. Monitoring & control
Actual chart (TT) (hours)
11
Total actual time of module completion 1 | 914 hours
Total actual time of module completion 2 | 669 hours
Total actual time of module completion 3 | 1909 hours

## Slide 12: 3. Monitoring & control
Actual chart (TT) (days)
12
Total actual time of module completion 1 | 43 day
Total actual time of module completion 2 | 20 day
Total actual time of module completion 3 | 65 day
Deducted 3 weeks for Tet holidays and 2 weeks for epidemic breaks | 

## Slide 13: 3. Monitoring & control
Membership time chart
13
Total time each member worked in 32 weeks

## Slide 14: 3. Monitoring & control
14

## Slide 15: 4. Architectural
15
# | ID | Quality Attributes | Priority
Usability |  |  | 
1 | QA1 | Users use the app to easier | High
Portability |  |  | 
2 | QA2 | Users can use the application on two platforms | High

## Slide 16: 4. Architectural
Context diagram
16

## Slide 17: 4. Architectural
Protability (dynamic)
17

## Slide 18: 4. Architectural
Protability (physics)
18

## Slide 19: 4. Architectural
Usability (static)
19

## Slide 20: 5. Summary test report.
20
Summary priority

## Slide 21: 5. Summary test report.
21
Summary priority
Summary | 
Pass | 364
Fail | 11
Number of test cases | 375

## Slide 22: 5. Summary test report.
22
Summary priority
Summary | 
Enforcement | 100%
Error found | 61
Corrected the error | 50
Error still | 11

## Slide 23: 7. Risk management
23
Number | Risk name | Possibility | Impact | Priority | How to prevent or minimize
1 | Difficulties with new technologies | Moderate | Moderate | Moderate | 1. Organize training sessions on new technologies for all members
2 | Lost data | High | High | High | 1. Online storage 2. Create a backup file
3 | Machinery and equipment had problems during the project's implementation | Moderate | Moderate | Moderate | 1.Implementation on many devices
4 | Performance is not guaranteed | High | High | High | 1. Keep members in the best state 2. Regularly interested and updated the working situation of the members.

## Slide 24: 7. Risk management
24
Number | Risk name | Possibility | Impact | Priority | How to prevent or minimize
5 | Customer change | High | Moderate | Moderate | 1. Having a contract, a written signature of the customer for specific requirements upon project receipt. 2. There is a specific process for customer change
6 | Member left the project | High | High | High | 1. Ensure all members are fully involved in the work of the project. 2. Regular meetings (outside work) to build solidarity 3. Having a mechanism to manage and archive work documents of all members.
7 | Members have unequal qualifications | High | High | High | 1. Training members from the beginning of the project. 2. Organize cross-training sessions for members.

## Slide 25: 7. Problem project
25
Number | Problem name | Possibility | Impact | Impact factor | How to fix
1 | Language code | High (occurred) | High | Objective | Spend much time for search (Forum, youtube, google, group facebook, question mentor, …)
2 | Database (firebase) | High (occurred) | High | Objective | Spend much time for search (Forum, youtube, google, group facebook, question mentor, …)
3 | Change requirement | Medium (occurred) | Medium | Objective | Contract signed (increased time)
4 | Disease cov19 | High (occurred) | High | Objective | Meeting online

## Slide 26: 8. Lesson learned & Demo.
Lesson learned
26
Kiến thức – kĩ năng | 
1 | Design - Hiểu biết sâu hơn về design. Có kiến thức thêm về làm dự án thực tế
2 | Code - Có thêm kiến thức mới về ngôn ngữ lập trình và kinh nghiệm làm dự án thực tế
3 | Test - Hiểu được tầm quan trọng của tester và cũng có được trải nghiệm thực tế
Teamwork | 
1 | Nhóm làm teamwork rất tốt không có gặp khó khăn.
2 | Mỗi người đều có trách nhiệm và ý thức không đun đẩy công việc
3 | Có những hoạt động xa đọa để nâng cao tinh thần đồng đội

## Slide 27: 8. Lesson learned & Demo.
27

## Slide 28
THANK YOU