## Summary
Actual | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Total
Đạt Huỳnh | #REF! | #REF! | [35 empty] | #REF!
0
0
0
0
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Planed | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Total
Đạt Huỳnh | #REF! | #REF! | [35 empty] | #REF!
0
0
0
0
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Week 1-2
Timelog: | Quốc Nhân
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
1 | Monday | Meeting Mentor |  | 14/10/2019 | 4 | 4 | Done
1 | Tuesday | Training | Research Information WebGIS | 15/10/2019 | 4 | 4 | Inprogress
1 | Wednesday | Training | Research Information WebGIS | 16/10/2019 | 5 | 5 | Inprogress
1 | Thursday | Project Management | Create Member Charter | 17/10/2019 | 5 | 5 | Done
1 | Friday | Meetting Customer |  | 18/10/2019 | 4 | 4 | Done
1 | Saturday | Training | Research WebGIS, Database & Code | 19/10/2019 | 4 | 4 | Inprogress
Total | Actual: | 26 |  |  |  | Plan: | 26
2 | Monday | Project Management | Create Team Charter | 21/10/2019 | 6 | 6 | Done | PM_TeamCharter_Ver1.0.docx
2 | Tuesday | Training | Research Information WebGIS | 22/10/2019 | 5 | 5 | Inprogress
2 | Wednesday | Meeting Mentor |  | 23/10/2019 | 4 | 4 | Done
2 | Thursday | Project Management | Draw the steps submitted and changed github & gg drive | 24/10/2019 | 5 | 5 | Done | PM_ConfigurationManagementPlan_Ver1.0.docx
2 | Friday | Training | Reading Customer Documments | 25/10/2019 | 5 | 5 | Done
2 | Saturday | Training | Presentation Customer Documments | 26/10/2029 | 5 | 5 | Done
Total | Actual: | 30 |  |  |  | Plan: | 30

## Week 3-4
Timelog: | Quốc Nhân
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
3 | Monday | Project Management | Create Project plan v1.0, Install Android studio, Genymotion | 2019-10-28 | 8 |  | Done
3 | Tuesday | Project Management | Research Information React Native, Update Project plan v1.1 | 2019-10-29 | 10 |  | Inprogress | PM_ProjectPlan_Ver1.1.docx
3 | Wednesday | Meetting Customer | Meeting with Customer, Update Project plan v1.2 | 2019-10-30 | 5 |  | Inprogress | PM_ProjectPlan_Ver1.2.docx
3 | Thursday | Project Management | Install React Native | 2019-10-31 | 10 |  | Inprogress
3 | Friday | Meetting Customer | Install React Native | 2019-11-01 | 5 |  | Inprogress
3 | Saturday | Project Management | Update Project plan v1.3, Create project charter v1.0 | 2019-11-02 | 4 |  | Inprogress | PM_ProjectPlan_Ver1.3.docx
3 | Sunday | Implementation | Install React Native | 2019-11-03 | 3 |  | Done
Total | Actual: | 45 |  |  |  | Plan: | 0
4 | Monday | Project Management | Create Question function v1.0, update project charter v1.0, update Milestone v1.0 | 2019-11-04 | 7 |  | Inprogress | PM_ProjectCharter_Ver1.0.docx, PM_Question_Ver1.0.xlxs, PM_Milestone_Ver1.0.xlxs
4 | Tuesday | Requirement | Create SRS v1.0, implement plan v1.0 | 2019-11-05 | 10 |  | Inprogress | PM_SRS_Ver1.0.docx, PM_Implementplan_Ver1.0.docx
4 | Wednesday | Meeting Mentor |  | 2019-11-06 |  |  | Done
4 | Thursday | Project Management |  | 2019-11-07 |  |  | Done
4 | Friday | Training |  | 2019-11-08 |  |  | Done
4 | Saturday | Training |  | 2019-11-09 |  |  | Done
4
Total | Actual: | 17 |  |  |  | Plan: | 0