## Summary
Actual | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Total
Đạt Huỳnh | 24 | 22 | [35 empty] | 46
0
0
0
0
| 24 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46
Planed | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Total
Đạt Huỳnh | 24 | 34 | [35 empty] | 58
0
0
0
0
| 24 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58

## Đạt Huỳnh
Timelog: | Đạt Huỳnh
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
1 | Monday | Meeting Mentor |  | 14/10/2019 | 4 | 4 | Done
1 | Tuesday | Training | Resreach information WebGIS | 15/10/2019 | 6 | 6 | Inprogress |  | 8
1 | Wednesday | Training | Resreach coding language | 16/10/2019 | 6 | 6 | Inprogress
1 | Thursday | Project Management | Resreach & Create template documments | 17/10/2019 | 4 | 4 | Done
1 | Friday | Meetting Customer |  | 18/10/2019 | 4 | 4 | Done
1 | Saturday |  |  | 19/10/2019
Total | Actual: | 24 |  |  |  | Plan: | 24
2 | Monday | Project Management | Create Configuration Management Plan | 21/10/2019 | 6 | 6 | Inprogress
2 | Tuesday | Project Management | Create Configuration Management Plan | 22/10/2019 | 6 | 6 | Inprogress | PM_ConfigurationManagementPlan_Ver1.0.docx
2 | Wednesday | Meeting Mentor |  | 23/10/2019 | 4 | 4 | Done
2 | Thursday | Project Management | Create TimeLog | 24/10/2019 | 6 | 6 | Done
2 | Friday | Training | Readding Customer Documments | 25/10/2019 |  | 6
2 | Saturday | Training | Presentation Customer Documments | 26/10/2029 |  | 6
Total | Actual: | 22 |  |  |  | Plan: | 34

## Anh Minh
Timelog:
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
1 | Monday | Meeting Mentor |  | 14/10/2019 | 4 | 4 | Done
1 | Tuesday | Research | Research WebGIS | 15/10/2019 | 5 | 5 | Inprogress
1 | Wednesday | Research | Research WebGIS | 16/10/2019 | 3 | 5 | Inprogress
1 | Thursday | Research | Research WebGIS | 17/10/2019 | 3 | 5 | Done
1 | Friday | Meetting Customer |  | 18/10/2019 | 4 | 4 | Done
1 | Saturday | Training |  | 19/10/2019 | 5 | 5 | Inprogress
Total | Actual: | 24 |  |  |  | Plan: | 28
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
2 | Monday | Research | Readding Incremental Model | 21/10/2019 | 5 | 5 | Done
2 | Tuesday | Research | Readding Geodatabase | 22/10/2019 | 3 | 5 | Done
2 | Wednesday | Meeting Mentor |  | 23/10/2019 | 4 | 4 | Done
2 | Thursday | Research | Setting and research QGIS | 24/10/2019 | 7 | 5 | Done
2 | Friday | Research | Readding Customer Documments | 25/10/2019 | 4 | 5 | Done
2 | Saturday | Research | Presentation Customer Documments | 26/10/2019 | 4 | 6 | Done
Total | Actual: | 27 |  |  |  | Plan: | 30
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
3 | Monday | Project Management | Create Risk Management Plan | 28/10/2019 | 6 | 6 | Done
3 | Tuesday | Meeting Mentor |  | 29/10/2019 | 4 | 4 | Done
3 | Wednesday | Meetting Customer |  | 30/10/2019 | 4 | 4 | Done
3 | Thursday | Project Management | Create Quality Management Plan | 31/10/2019 | 6 | 6 | Done
3 | Friday | Project Management | Update Risk Management Plan | 2019-01-11 | 5 | 5 | Done
3 | Saturday | Project Management | Update Quality Management Plan | 2019-02-11 | 5 | 5 | Done
Total | Actual: | 30 |  |  |  | Plan: | 30
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
4 | Monday | Project Management | Create Measurement Plan | 2019-11-04 | 5 | 5 | Done
4 | Tuesday | Project Management | Update Measurement Plan | 2019-11-05 | 4 | 5 | Done
4 | Wednesday | Meeting Mentor |  | 2019-11-06 | 4 | 4 | Done
4 | Thursday | Project Management | Usecase Decription | 2019-11-07 | 5 | 7 | Inprogress
4 | Friday | Meetting Customer |  | 2019-11-08 | 5 | 5 | Done
4 | Saturday | Project Management | Complete the meeting minutes ; Review document , test process | 2019-11-09 | 7 | 5 | Inprogress
Total | Actual: | 30 |  |  |  | Plan: | 31
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
5 | Monday | Project Management | Create Chage Management Plan | 2019-11-11 | 6 | 6 | Done
5 | Tuesday | Meeting Mentor |  | 2019-11-12 | 4 | 4 | Done
5 | Wednesday | Project Management | Update Chage Management Plan | 2019-11-13 | 5 | 5 | Done
5 | Thursday | Project Management | Usecase Decription | 2019-11-14 | 5 | 5 | Inprogress
5 | Friday | Project Management | Update Software Architecture Document | 2019-11-15 | 5 | 5 | Done
5 | Saturday | Project Management | Present EOMP1 Complete the meeting minutes Report document for customer | 2019-11-16 | 6 | 6 | Done
Total | Actual: | 31 |  |  |  | Plan: | 31
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
6 | Monday | Project Management |  | 2019-11-18 | 6 | 6 | Done
6 | Tuesday | Meeting Mentor |  | 2019-11-19 | 4 | 4 | Done
6 | Wednesday | Project Management |  | 2019-11-20 | 5 | 6 | Done
6 | Thursday | Project Management |  | 2019-11-21 | 5 | 6 | Done
6 | Friday | Project Management |  | 2019-11-22 | 5 | 6 | Done
6 | Saturday | Project Management | Complete the meeting minutes | 2019-11-23 | 6 | 6 | Done
Total | Actual: | 31 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
7 | Monday | Training | Install with React Native Development | 2019-11-25 | 6 | 6 | Done
7 | Tuesday | Meeting Mentor |  | 2019-11-26 | 4 | 4 | Done
7 | Wednesday | Training | Install the android virtual machine | 2019-11-27 | 5 | 6 | Done
7 | Thursday | Training | React Native application design process | 2019-11-28 | 6 | 6 | Done
7 | Friday | Training | Instructions to build applications on Android + iPhone devices | 2019-11-29 | 5 | 6 | Done
7 | Saturday | Project Management | Review document Complete the meeting minutes | 2019-11-30 | 6 | 6 | Done
Total | Actual: | 32 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
8 | Monday | Training | Install with React Native Development | 2019-12-02 | 5 | 6 | Done
8 | Tuesday | Meeting Mentor |  | 2019-12-03 | 4 | 4 | Done
8 | Wednesday | Training | Install the android virtual machine | 2019-12-04 | 5 | 6 | Done
8 | Thursday | Training | Component In React Native 1. Understand the sequence of a Component's operation 2. Text Component | 2019-12-05 | 5 | 6 | Done
8 | Friday | Training | Component In React Native (p1) 3. Image Component | 2019-12-06 | 5.5 | 6 | Done
8 | Saturday | Training | Component In React Native (p1) 4. View Component | 2019-12-07 | 5.5 | 6 | Done
8 | Actual: | 30 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
9 | Monday | Training | React Navigation | 2019-12-09 | 6 | 6 | Done
9 | Tuesday | Meeting Mentor |  | 2019-12-10 | 4 | 4 | Done
9 | Wednesday | Training | Component nested Component | 2019-12-11 | 6 | 6 | Done
9 | Thursday | Training | Export Component Pass parameters to Component | 2019-12-12 | 4 | 6 | Done
9 | Friday | Training | Debug with JavaScript Debug with React Native | 2019-12-13 | 5.5 | 6 | Done
9 | Saturday | Training | Debug with Beyond Javascript | 2019-12-14 | 6 | 6 | Done
9 | Actual: | 31.5 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
10 | Monday | Training | Publish Applications to AppStore | 2019-12-16 | 6 | 6 | Done
10 | Tuesday | Meeting Mentor |  | 2019-12-17 | 4 | 4 | Done
10 | Wednesday | Training | Publish Applications to Google Store | 2019-12-18 | 6 | 6 | Done
10 | Thursday | Training | Research WebGIS | 2019-12-19 | 4 | 4 | Done
10 | Friday | Training | Setting and research QGIS | 2019-12-20 | 5.5 | 5.5 | Done
10 | Saturday | Training | 1. Realtime Database 2. Authentication | 2019-12-21 | 6 | 6 | Done
10 | Actual: | 31.5 |  |  |  | Plan: | 31.5