## Revision History
Schedule Module 3 BDS Project
| Project Name: | BDS Project
| Team: | Team 03 - Hello World
| Document: | Schedule module 3
| Creator: | Nhan Pham
| Created Date: | 2019-04-01
Revision History
| Version | Date | Author | Content
| Version 1.0 | 2019-04-01 | Nhan Pham | Create schedule module 3

## Dữ liệu dự án
Bảng công việc
Nội dung công việc | Người phụ trách | Ngày bắt đầu | Ngày kết thúc | Số ngày (ngày) | Tình trạng | Số giờ hoàn thành công việc kế hoạch (Giờ) | Mức độ ưu tiên | Số giờ hoàn thành công việc cá nhân (Giờ)
Design prototype, sequence, use case description View business results the week "Employees" app | Quốc Nhân | 2020-04-06 | 2020-04-07 | 1 | Đã hoàn thành | 18 | Cao
Design prototype, sequence, use case description View details of the weekly business results the "Employees" app | Quốc Nhân | 2020-04-07 | 2020-04-08 | 1 | Đã hoàn thành | 18 | Cao
Design prototype, sequence, use case description View business results the week "Team" app | Quốc Nhân | 2020-04-08 | 2020-04-09 | 1 | Đã hoàn thành | 18 | Cao
Design prototype, sequence, use case description View business results the week "Room" app | Quốc Nhân | 2020-04-09 | 2020-04-10 | 1 | Đã hoàn thành | 18 | Cao
Design prototype, sequence, use case description View business results graph "Employees" app | Quốc Nhân | 2020-04-10 | 2020-04-11 | 1 | Đã hoàn thành | 18 | Cao
Design prototype, sequence, use case description Search business results graph "Employees" app | Quốc Nhân | 2020-04-13 | 2020-04-14 | 1 | Đã hoàn thành | 18 | Cao
Design prototype, sequence, use case description View the "Team" business results graph app | Quốc Nhân | 2020-04-14 | 2020-04-15 | 1 | Đã hoàn thành | 18 | Cao
Design prototype, sequence, use case description Search results graph "Team" app | Quốc Nhân | 2020-04-15 | 2020-04-16 | 1 | Đã hoàn thành | 18 | Cao
Design prototype, sequence, use case description View business results graph "Rooms" app | Quốc Nhân | 2020-04-16 | 2020-04-17 | 1 | Đã hoàn thành | 18 | Cao
Design prototype, sequence, use case description Search business results graph "Room" app | Quốc Nhân | 2020-04-17 | 2020-04-18 | 1 | Đã hoàn thành | 18 | Cao
Design prototype, sequence, use case description View compare business results "Employees" | Quốc Nhân | 2020-04-20 | 2020-04-21 | 1 | Đã hoàn thành | 18 | Cao
Design prototype, sequence, use case description Search compare business results "Employees" app | Quốc Nhân | 2020-04-21 | 2020-04-22 | 1 | Đã hoàn thành | 18 | Cao
Design prototype, sequence, use case description View the business results "Team" app | Quốc Nhân | 2020-04-22 | 2020-04-23 | 1 | Đã hoàn thành | 18 | Cao
Design prototype, sequence, use case description Search compare business results "Team" app | Quốc Nhân | 2020-04-23 | 2020-04-24 | 1 | Đã hoàn thành | 18 | Cao
Design prototype, sequence, use case description View compare business results "Rooms" app | Quốc Nhân | 2020-04-24 | 2020-04-25 | 1 | Đã hoàn thành | 18 | Cao
Design prototype, sequence, use case description Search compare business results "Rooms" app | Quốc Nhân | 2020-04-27 | 2020-04-28 | 1 | Đã hoàn thành | 18 | Cao
Design prototype, sequence, use case description View business results "Employees" website | Quốc Nhân | 2020-04-28 | 2020-04-29 | 1 | Đã hoàn thành | 18 | Cao
Design prototype, sequence, use case description View business results the week "Team" website | Quốc Nhân | 2020-04-29 | 2020-04-30 | 1 | Đã hoàn thành | 18 | Cao
Design prototype, sequence, use case description View business results the week "Room" website | Quốc Nhân | 2020-04-30 | 2020-05-01 | 1 | Đã hoàn thành | 18 | Cao
Design messages list module 3 | Quốc Nhân | 2020-05-04 | 2020-05-06 | 2 |  | 27 | Cao
Design business rule module 3 | Quốc Nhân | 2020-05-07 | 2020-05-09 | 2 |  | 27 | Cao
Design use case diagram module 3 | Quốc Nhân | 2020-05-11 | 2020-05-13 | 2 |  | 27 | Cao
Code Front-end View business results the week "Employees" app and "View personal information" app | Đạt Huỳnh | 2020-04-01 | 2020-04-02 | 1 |  | 18 | Cao
Code Front-end View details of the weekly business results the "Employees" app | Đạt Huỳnh | 2020-04-02 | 2020-04-03 | 1 |  | 18 | Cao
Code Front-end View business results the week "Team" app | Đạt Huỳnh | 2020-04-06 | 2020-04-07 | 1 |  | 18 | Cao
Code Front-end View business results the week "Room" app | Đạt Huỳnh | 2020-04-07 | 2020-04-08 | 1 |  | 18 | Cao
Code Front-end View business results graph "Employees" app | Đạt Huỳnh | 2020-04-08 | 2020-04-09 | 1 |  | 18 | Cao
Code Front-end Search business results graph "Employees" app | Đạt Huỳnh | 2020-04-10 | 2020-04-11 | 1 |  | 18 | Cao
Code Front-end View the "Team" business results graph app | Đạt Huỳnh | 2020-04-13 | 2020-04-14 | 1 |  | 18 | Cao
Code Front-end Search results graph "Team" app | Đạt Huỳnh | 2020-04-14 | 2020-04-16 | 2 |  | 27 | Cao
Code Front-end View business results graph "Rooms" app | Đạt Huỳnh | 2020-04-16 | 2020-04-17 | 1 |  | 18 | Cao
Code Front-end Search business results graph "Room" app | Đạt Huỳnh | 2020-04-20 | 2020-04-22 | 2 |  | 27 | Cao
Code Front-end View compare business results "Employees" | Đạt Huỳnh | 2020-04-22 | 2020-04-23 | 1 |  | 18 | Cao
Code Front-end Search and compare business results "Employees" app | Đạt Huỳnh | 2020-04-23 | 2020-04-25 | 2 |  | 27 | Cao
Code Front-end View the business results "Team" app | Đạt Huỳnh | 2020-04-27 | 2020-04-28 | 1 |  | 18 | Cao
Code Front-end Search and compare business results "Team" app | Đạt Huỳnh | 2020-04-28 | 2020-04-30 | 2 |  | 27 | Cao
Code Front-end View compare business results "Rooms" app | Đạt Huỳnh | 2020-04-30 | 2020-05-01 | 1 |  | 18 | Cao
Code Front-end Search and compare business results "Rooms" app | Đạt Huỳnh | 2020-05-04 | 2020-05-06 | 2 |  | 27 | Cao
Code Back-end View business results the week "Employees" app | Quang Vương | 2020-04-01 | 2020-04-02 | 1 |  | 18 | Cao
Code Back-end View details of the weekly business results the "Employees" app | Quang Vương | 2020-04-02 | 2020-04-03 | 1 |  | 18 | Cao
Code Back-end View business results the week "Team" app | Quang Vương | 2020-04-06 | 2020-04-07 | 1 |  | 18 | Cao
Code Back-end View business results the week "Room" app | Quang Vương | 2020-04-07 | 2020-04-08 | 1 |  | 18 | Cao
Code Back-end View business results graph "Employees" app | Quang Vương | 2020-04-08 | 2020-04-09 | 1 |  | 18 | Cao
Code Back-end Search business results graph "Employees" app | Quang Vương | 2020-04-10 | 2020-04-11 | 1 |  | 18 | Cao
Code Back-end View the "Team" business results graph app | Quang Vương | 2020-04-13 | 2020-04-14 | 1 |  | 18 | Cao
Code Back-end Search results graph "Team" app | Quang Vương | 2020-04-14 | 2020-04-16 | 2 |  | 27 | Cao
Code Back-end View business results graph "Rooms" app | Quang Vương | 2020-04-16 | 2020-04-17 | 1 |  | 18 | Cao
Code Back-end Search business results graph "Room" app | Quang Vương | 2020-04-20 | 2020-04-22 | 2 |  | 27 | Cao
Code Back-end View compare business results "Employees" | Quang Vương | 2020-04-22 | 2020-04-23 | 1 |  | 18 | Cao
Code Back-end Search and compare business results "Employees" app | Quang Vương | 2020-04-23 | 2020-04-25 | 2 |  | 27 | Cao
Code Back-end View the business results "Team" app | Quang Vương | 2020-04-27 | 2020-04-28 | 1 |  | 18 | Cao
Code Back-end Search and compare business results "Team" app | Quang Vương | 2020-04-28 | 2020-04-30 | 2 |  | 27 | Cao
Code Back-end View compare business results "Rooms" app | Quang Vương | 2020-04-30 | 2020-05-01 | 1 |  | 18 | Cao
Code Back-end Search and compare business results "Rooms" app | Quang Vương | 2020-05-04 | 2020-05-06 | 2 |  | 27 | Cao
Code Front-end, back-end View business results "Employees" website and "Forgot password" app | Anh Minh | 2020-04-01 | 2020-04-10 | 9 |  | 72 | Cao
Code Front-end, back-end View business results the week "Team" website and "Change Password" app | Anh Minh | 2020-04-13 | 2020-04-24 | 11 |  | 88 | Cao
Code Front-end, back-end View business results the week "Room" website | Anh Minh | 2020-04-27 | 2020-05-08 | 11 |  | 88 | Cao
Test View business results the week "Employees" app | Như Phương | 2020-04-01 | 2020-04-03 | 2 | Đã hoàn thành | 27 | Cao
Test View details of the weekly business results the "Employees" app | Như Phương | 2020-04-06 | 2020-04-07 | 1 | Đã hoàn thành | 18 | Cao
Test View business results the week "Team" app | Như Phương | 2020-04-08 | 2020-04-09 | 1 | Đã hoàn thành | 18 | Cao
Test View business results the week "Room" app | Như Phương | 2020-04-09 | 2020-04-10 | 1 | Đã hoàn thành | 18 | Cao
Test View business results graph "Employees" app | Như Phương | 2020-04-10 | 2020-04-11 | 1 | Đã hoàn thành | 18 | Cao
Test Search business results graph "Employees" app | Như Phương | 2020-04-13 | 2020-04-15 | 2 | Đã hoàn thành | 27 | Cao
Test View the "Team" business results graph app | Như Phương | 2020-04-16 | 2020-04-17 | 1 | Đã hoàn thành | 18 | Cao
Test Search results graph "Team" app | Như Phương | 2020-04-18 | 2020-04-20 | 2 | Đã hoàn thành | 27 | Cao
Test View business results graph "Rooms" app | Như Phương | 2020-04-21 | 2020-04-22 | 1 | Đã hoàn thành | 18 | Cao
Test Search business results graph "Room" app | Như Phương | 2020-04-23 | 2020-04-25 | 2 | Đã hoàn thành | 27 | Cao
Test View compare business results "Employees" | Như Phương | 2020-04-27 | 2020-04-28 | 1 | Đã hoàn thành | 18 | Cao
Test Search and compare business results "Employees" app | Như Phương | 2020-04-29 | 2020-05-01 | 2 | Đã hoàn thành | 27 | Cao
Test View the business results "Team" app | Như Phương | 2020-05-01 | 2020-05-02 | 1 | Đã hoàn thành | 18 | Cao
Test Search and compare business results "Team" app | Như Phương | 2020-05-04 | 2020-05-05 | 1 | Đã hoàn thành | 18 | Cao
Test View compare business results "Rooms" app | Như Phương | 2020-05-05 | 2020-05-06 | 1 | Đã hoàn thành | 18 | Cao
Test Search and compare business results "Rooms" app | Như Phương | 2020-05-06 | 2020-05-07 | 1 | Đã hoàn thành | 18 | Cao
Test View business results "Employees" website | Như Phương | 2020-05-07 | 2020-05-08 | 1 | Đã hoàn thành | 18 | Cao
Test View business results the week "Team" website | Như Phương | 2020-05-08 | 2020-05-09 | 1 | Đã hoàn thành | 18 | Cao
Test View business results the week "Room" website | Như Phương | 2020-05-11 | 2020-05-12 | 1 | Đã hoàn thành | 18 | Cao
Kết thúc planning, analysing & training |  |  |  | Tổng thời gian = 104 ngày |  | 1724 |  | 0
Phần trăm hoàn thành
Đã hoàn thành | 0%
Quá hạn | 0%
Đang thực hiện | 0%
Chưa thực hiện | 0%
Ngân sách
Theo kế hoạch
Theo thực tế
Cơ cấu công việc
Đạt Huỳnh | 6
Quốc Nhân | 21
Quang Vương | 6
Anh Minh | 11
Như Phương | 17