## Revision History
Schedule Module 3 BDS Project
| Project Name: | BDS Project
| Team: | Team 03 - Hello World
| Document: | Schedule module 3
| Creator: | Nhan Pham
| Created Date: | 2019-04-01
Revision History
| Version | Date | Author | Content
| Version 1.0 | 2019-04-01 | Nhan Pham | Create schedule module 3

## Dữ liệu dự án
Bảng công việc
ID | Nội dung công việc | Người phụ trách | Ngày bắt đầu | Ngày kết thúc | Số ngày (ngày) | Tình trạng | Số giờ hoàn thành công việc kế hoạch (Giờ) | Mức độ ưu tiên | Số giờ hoàn thành công việc cá nhân (Giờ)
1 | Design prototype, sequence, use case description View business results the week "Employees" app, Edit "Team & Room" Website | Quốc Nhân | 2020-04-06 | 2020-04-08 | 2 | Đã hoàn thành | 18 | Cao | 16
2 | Design prototype, sequence, use case description View details of the weekly business results the "Employees" app, Add "Team & Room" Website | Quốc Nhân | 2020-04-09 | 2020-04-10 | 1 | Đã hoàn thành | 9 | Cao | 16
3 | Design prototype, sequence, use case description View business results the week "Team" app | Quốc Nhân | 2020-04-11 | 2020-04-13 | 2 | Đã hoàn thành | 18 | Cao | 22
4 | Design prototype, sequence, use case description View business results the week "Room" app | Quốc Nhân | 2020-04-14 | 2020-04-16 | 2 | Đã hoàn thành | 18 | Cao | 15 | Formula
5 | Design prototype, sequence, use case description View business results graph "Employees" app, Delete "Team & Room" Website | Quốc Nhân | 2020-04-17 | 2020-04-20 | 3 | Đã hoàn thành | 27 | Cao | 22 | Số giờ hoàn thành công việc cá nhân = Thời gian cồng việc + Số công việc đã làm (cập nhật time log)
6 | Design prototype, sequence, use case description Search business results graph "Employees" app | Quốc Nhân | 2020-04-20 | 2020-04-22 | 2 | Đã hoàn thành | 18 | Cao | 16
7 | Design prototype, sequence, use case description View the "Team" business results graph app | Quốc Nhân | 2020-04-23 | 2020-04-25 | 2 | Đã hoàn thành | 18 | Cao | 18
8 | Design prototype, sequence, use case description Search results graph "Team" app | Quốc Nhân | 2020-04-27 | 2020-04-28 | 1 | Đã hoàn thành | 9 | Cao | 15
9 | Design prototype, sequence, use case description View business results graph "Rooms" app | Quốc Nhân | 2020-04-28 | 2020-04-29 | 1 | Đã hoàn thành | 9 | Cao | 14
10 | Design prototype, sequence, use case description Search business results graph "Room" app | Quốc Nhân | 2020-04-30 | 2020-05-01 | 1 | Đã hoàn thành | 9 | Cao | 11
11 | Design prototype, sequence, use case description View compare business results "Employees" | Quốc Nhân | 2020-05-04 | 2020-05-06 | 2 | Đã hoàn thành | 18 | Cao | 10
12 | Design prototype, sequence, use case description Search compare business results "Employees" app | Quốc Nhân | 2020-05-07 | 2020-05-09 | 2 | Đã hoàn thành | 18 | Cao | 18
13 | Design prototype, sequence, use case description View the business results "Team" app | Quốc Nhân | 2020-05-11 | 2020-05-13 | 2 | Đã hoàn thành | 18 | Cao | 14
14 | Design prototype, sequence, use case description Search compare business results "Team" app | Quốc Nhân | 2020-05-14 | 2020-05-16 | 2 | Đã hoàn thành | 18 | Cao | 23
15 | Design prototype, sequence, use case description View compare business results "Rooms" app | Quốc Nhân | 2020-05-18 | 2020-05-20 | 2 | Đã hoàn thành | 18 | Cao | 16
16 | Design prototype, sequence, use case description Search compare business results "Rooms" app | Quốc Nhân | 2020-05-21 | 2020-05-22 | 1 | Đã hoàn thành | 9 | Cao | 23
17 | Design prototype, sequence, use case description Delete room website, View room website | Quốc Nhân | 2020-05-25 | 2020-05-26 | 1 | Đã hoàn thành | 9 | Cao | 15
18 | Design prototype, sequence, use case description Import file website | Quốc Nhân | 2020-05-27 | 2020-05-28 | 1 | Đã hoàn thành | 9 | Cao | 16
19 | Design prototype, sequence, use case description View personal information app | Quốc Nhân | 2020-06-01 | 2020-06-02 | 1 | Đã hoàn thành | 18 | Cao | 16
20 | Design prototype, sequence, use case description Add room, Template excel website | Quốc Nhân | 2020-06-02 | 2020-06-03 | 1 | Đã hoàn thành | 16 | Medium
21 | Design prototype, sequence, use case description Edit room | Quốc Nhân | 2020-06-04 | 2020-06-06 | 2 | Đã hoàn thành | 16 | Medium
22 | Design prototype, sequence, use case description View happy birthday app | Quốc Nhân | 2020-06-07 | 2020-06-08 | 1 | Đã hoàn thành | 7 | Low | 16
23 | Design messages list module 3 | Quốc Nhân | 2020-06-09 | 2020-06-11 | 2 | Đã hoàn thành | 18 | Cao | 21
24 | Design business rule module 3 | Quốc Nhân | 2020-06-12 | 2020-06-13 | 1 | Đã hoàn thành | 9 | Cao | 24
25 | Design use case diagram module 3 | Quốc Nhân | 2020-06-14 | 2020-06-15 | 1 | Đã hoàn thành | 9 | Cao | 20
26 | Code layout and logic birthday | Đạt Huỳnh | 2020-04-06 | 2020-04-11 | 6 | Đã hoàn thành | 34 | Cao | 42
27 | Add music for ios and research chart | Đạt Huỳnh | 2020-04-13 | 2020-04-18 | 6 | Đã hoàn thành | 34 | Cao | 41
28 | Config chart and coding layout report sale | Đạt Huỳnh | 2020-04-20 | 2020-04-25 | 6 | Đã hoàn thành | 34 | Cao | 40
29 | coding layout chart sale result | Đạt Huỳnh | 2020-04-27 | 2020-05-02 | 6 | Đã hoàn thành | 22 | Cao | 25
30 | coding layout chart sale compare and handle data group sale result chart | Đạt Huỳnh | 2020-05-04 | 2020-05-09 | 6 | Đã hoàn thành | 34 | Cao | 42
31 | coding hande data personal sale result chart | Đạt Huỳnh | 2020-05-11 | 2020-05-16 | 6 | Đã hoàn thành | 34 | Cao | 49
32 | coding hande data team sale result chart | Đạt Huỳnh | 2020-05-18 | 2020-05-23 | 6 | Đã hoàn thành | 34 | Cao | 54
33 | coding hande data personal sale compare chart | Đạt Huỳnh | 2020-05-25 | 2020-05-30 | 6 | Đã hoàn thành | 34 | Cao | 54
34 | coding hande data team sale compare chart | Đạt Huỳnh | 2020-06-01 | 2020-06-06 | 6 | Đã hoàn thành | 34 | Cao | 54
35 | Review all | Đạt Huỳnh | 2020-06-08 | 2020-06-13 | 6 | Đã hoàn thành | 32 | Cao | 32
44 | View message birthday | Quang Vương | 2020-04-06 | 2020-04-11 | 6 | Đã hoàn thành | 44 | Cao | 44.5
45 | Play music happy birthday for android | Quang Vương | 2020-04-13 | 2020-04-18 | 6 | Đã hoàn thành | 44 | Cao | 45
46 | View data result business week for personal | Quang Vương | 2020-04-20 | 2020-04-25 | 6 | Đã hoàn thành | 44 | Cao | 45
47 | Show time of week result | Quang Vương | 2020-04-27 | 2020-05-02 | 6 | Đã hoàn thành | 28 | Cao | 33
48 | Update map with sattelite and standard mode | Quang Vương | 2020-05-04 | 2020-05-09 | 6 | Đã hoàn thành | 44 | Cao | 44.5
49 | View data result business week for personal | Quang Vương | 2020-05-11 | 2020-05-16 | 6 | Đã hoàn thành | 44 | Cao | 47
50 | View data result business week for team | Quang Vương | 2020-05-18 | 2020-05-23 | 6 | Đã hoàn thành | 44 | Cao | 45
51 | View sale result chart group | Quang Vương | 2020-05-25 | 2020-05-30 | 6 | Đã hoàn thành | 44 | Cao | 48
52 | View compare chart group | Quang Vương | 2020-06-01 | 2020-06-06 | 6 | Đã hoàn thành | 44 | Cao | 47
53 | Review all | Quang Vương | 2020-06-08 | 2020-06-13 | 6 | Đã hoàn thành | 35 | Cao | 34
62 | Code Front-end add, edit, view room | Anh Minh | 2020-04-02 | 2020-04-11 | 10 | Đã hoàn thành | 33 | Cao | 51
63 | Code Front-end edit, view room | Anh Minh | 2020-04-13 | 2020-04-18 | 6 | Đã hoàn thành | 33 | Cao | 37
64 | Code back-end add room | Anh Minh | 2020-04-20 | 2020-04-25 | 6 | Đã hoàn thành | 33 | Cao | 36
65 | Code back-end edit, view room | Anh Minh | 2020-04-27 | 2020-05-02 | 6 | Đã hoàn thành | 33 | Medium | 35
66 | Code back-end add team, front-end import | Anh Minh | 2020-05-04 | 2020-05-09 | 6 | Đã hoàn thành | 33 | Medium | 33
67 | Code back-end import sale user | Anh Minh | 2020-05-11 | 2020-05-16 | 6 | Đã hoàn thành | 33 | Medium | 41
| Code back-end import sale room | Anh Minh | 2020-05-18 | 2020-05-23 | 6 | Đã hoàn thành | 33 | Medium | 44
| Code back-end export sale user | Anh Minh | 2020-05-25 | 2020-05-30 | 6 | Đã hoàn thành | 33 | Medium | 44
| Code back-end export sale room | Anh Minh | 2020-06-01 | 2020-06-06 | 6 | Đã hoàn thành | 33 | Medium | 44
68 | Review all | Anh Minh | 2020-06-08 | 2020-06-13 | 6 | Đã hoàn thành | 29 | Medium | 35
69 | Test View business results the week "Employees" app | Như Phương | 2020-04-01 | 2020-04-03 | 2 | Đã hoàn thành | 18 | Cao
70 | Test View details of the weekly business results the "Employees" app | Như Phương | 2020-04-06 | 2020-04-08 | 2 | Đã hoàn thành | 18 | Cao
71 | Test View business results the week "Team" app | Như Phương | 2020-04-09 | 2020-04-11 | 2 | Đã hoàn thành | 9 | Cao
72 | Test View business results the week "Room" app | Như Phương | 2020-04-13 | 2020-04-14 | 1 | Đã hoàn thành | 9 | Cao
73 | Test View business results graph "Employees" app | Như Phương | 2020-04-16 | 2020-04-17 | 1 | Đã hoàn thành | 9 | Cao
74 | Test Search business results graph "Employees" app | Như Phương | 2020-04-20 | 2020-04-22 | 2 | Đã hoàn thành | 18 | Cao
75 | Test View the "Team" business results graph app | Như Phương | 2020-04-23 | 2020-04-25 | 2 | Đã hoàn thành | 18 | Cao
76 | Test Search results graph "Team" app | Như Phương | 2020-04-27 | 2020-04-28 | 1 | Đã hoàn thành | 9 | Cao
77 | Test View business results graph "Rooms" app | Như Phương | 2020-04-29 | 2020-05-01 | 2 | Đã hoàn thành | 18 | Cao
78 | Test Search business results graph "Room" app | Như Phương | 2020-05-04 | 2020-05-06 | 2 | Đã hoàn thành | 18 | Cao
79 | Test View compare business results "Employees" | Như Phương | 2020-05-07 | 2020-05-09 | 2 | Đã hoàn thành | 18 | Cao
80 | Test Search and compare business results "Employees" app | Như Phương | 2020-05-11 | 2020-05-13 | 2 | Đã hoàn thành | 18 | Cao
81 | Test View the business results "Team" app | Như Phương | 2020-05-14 | 2020-05-16 | 2 | Đã hoàn thành | 18 | Cao
82 | Test Search and compare business results "Team" app | Như Phương | 2020-05-18 | 2020-05-20 | 2 | Đã hoàn thành | 18 | Cao
83 | Test View compare business results "Rooms" app | Như Phương | 2020-05-21 | 2020-05-23 | 2 | Đã hoàn thành | 18 | Cao
84 | Test Search and compare business results "Rooms" app | Như Phương | 2020-05-25 | 2020-05-27 | 2 | Đã hoàn thành | 18 | Cao
85 | Test "View Room" Website | Như Phương | 2020-05-28 | 2020-05-29 | 1 | Đã hoàn thành | 9 | Cao
86 | Test Import file website | Như Phương | 2020-05-30 | 2020-05-31 | 1 | Đã hoàn thành | 9 | Cao
87 | Test View personal information app and "Forgot password" website | Như Phương | 2020-06-01 | 2020-06-02 | 1 | Đã hoàn thành | 9 | Cao
88 | Test Template excel website | Như Phương | 2020-06-02 | 2020-06-03 | 1 |  | 8 | Medium
89 | Test "Add Room" Website | Như Phương | 2020-06-04 | 2020-06-06 | 2 |  | 16 | Medium
90 | Test "Edit Room" Website | Như Phương | 2020-06-08 | 2020-06-10 | 2 |  | 16 | Medium
91 | Test "Delete Room" Website | Như Phương | 2020-06-11 | 2020-06-13 | 2 |  | 16 | Medium
92 | Test View happy birthday app | Như Phương | 2020-06-14 | 2020-06-15 | 1 |  | 16 | Low
Kết thúc planning, analysing & training |  |  |  |  | 263 |  | 1781 |  | 1663
Phần trăm hoàn thành
| Đã hoàn thành | 0%
| Quá hạn | 0%
| Đang thực hiện | 0%
| Chưa thực hiện | 0%
Ngân sách
Theo kế hoạch
Theo thực tế
Cơ cấu công việc
| Đạt Huỳnh | 6
| Quốc Nhân | 21
| Quang Vương | 6
| Anh Minh | 11
| Như Phương | 17