## Summary
Actual | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Total
Đạt Huỳnh | 30 | 31.5 | 36.5 | 36.5 | 35 | 32.5 | 33.5 | 33.5 | 33.5 | 33.5 | [27 empty] | 336
Quốc Nhân | 31 | 30 | [35 empty] | 61
Vương Trương | 26.5 | Research | [35 empty] | 26.5
Anh Minh | Task | Project Management | [35 empty] | 0
Như Phương | #REF! | #REF! | [35 empty] | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Planed | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Total
Đạt Huỳnh | 30 | 34 | 38 | 38 | 35 | 34 | 34 | 34 | 34 | 34 | [27 empty] | 345
Quốc Nhân | 31 | 30 | [35 empty] | 61
Vương Trương | 27.5 | Done | [35 empty] | 27.5
Anh Minh | Status | Done | [35 empty] | 0
Như Phương | #REF! | #REF! | [35 empty] | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Đạt Huỳnh
Timelog: | Đạt Huỳnh
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status
1 | Monday | Meeting Mentor |  | 14/10/2019 | 4 | 4 | Done
1 | Tuesday | Training | Resreach information WebGIS | 15/10/2019 | 6 | 6 | Done
1 | Wednesday | Training | Resreach coding language | 16/10/2019 | 6 | 6 | Done
1 | Thursday | Project Management | Resreach & Create template documments | 17/10/2019 | 4 | 4 | Done
1 | Friday | Meetting Customer |  | 18/10/2019 | 4 | 4 | Done
1 | Saturday | Project Management | Create Comunication plan | 19/10/2019 | 6 | 6 | Done
Total | Actual: | 30 |  |  |  | Plan: | 30
Week | Day | Task | Name Task | Date | Actual | Plan | Status
2 | Monday | Project Management | Create Configuration Management Plan | 21/10/2019 | 6 | 6 | Inprogress
2 | Tuesday | Project Management | Create Configuration Management Plan | 22/10/2019 | 6 | 6 | Done
2 | Wednesday | Meeting Mentor |  | 23/10/2019 | 4 | 4 | Done
2 | Thursday | Project Management | Create TimeLog, devlopment process | 24/10/2019 | 6 | 6 | Done
2 | Friday | Training | Reading Customer Documments, devlopment process | 25/10/2019 | 5 | 6 | Inprogress
2 | Saturday | Training | Presentation Customer Documments | 26/10/2029 | 4.5 | 6 | Done
Total | Actual: | 31.5 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
3 | Monday | Project Management | Create Control&Monitoring Project | 2019-10-28 | 6 | 6 | Inprogress
3 | Tuesday | Project Management | Create Control&Monitoring Project | 2019-10-29 | 5.5 | 6 | Done
3 | Tuesday | Meeting Mentor |  | 2019-11-29 | 4 | 4 | Done
3 | Wednesday | Meetting Customer |  | 2019-10-30 | 4 | 4 | Done
3 | Thursday | Project Management | Create Timeline | 2019-10-31 | 5.5 | 6 | Done
3 | Friday | Project Management | Create EVM | 2019-11-01 | 6 | 6 | Inprogress
3 | Saturday | Project Management | Create EVM | 2019-11-02 | 5.5 | 6 | Done
Total | Actual: | 36.5 |  |  |  | Plan: | 38
Week | Day | Task | Name Task | Date | Actual | Plan | Status
4 | Monday | Project Management | Create Implementation Process | 2019-11-04 | 6 | 6 | Inprogress
4 | Tuesday | Project Management | Create Implementation Process | 2019-11-05 | 5.5 | 6 | Done
4 | Wednesday | Meeting Mentor |  | 2019-11-06 | 4 | 4 | Done
4 | Thursday | Project Management | Create Test Process | 2019-11-07 | 6 | 6 | Inprogress
4 | Friday | Meetting Customer |  | 2019-11-08 | 4 | 4 | Done
4 | Friday | Project Management | Create Test Process | 2019-11-08 | 5.5 | 6 | Done
4 | Saturday | Project Management | Review Documents | 2019-11-09 | 5.5 | 6 | Done
Total | Actual: | 36.5 |  |  |  | Plan: | 38
Week | Day | Task | Name Task | Date | Actual | Plan | Status
5 | Monday | Requirement | Write Usecase Decription | 2019-11-11 | 6 | 6 | Inprogress
5 | Tuesday | Meeting Mentor |  | 2019-11-12 | 4 | 4 | Done
5 | Wednesday | Requirement | Write Usecase Decription | 2019-11-13 | 6 | 6 | Inprogress
5 | Thursday | Requirement | Create S.R.S | 2019-11-14 | 6 | 6 | Inprogress
5 | Friday | Requirement | Create S.R.S | 2019-11-15 | 6 | 6 | Inprogress
5 | Saturday | Project Management | Present EOM#1 | 2019-11-16 | 1.5 | 1 | Done
5 | Saturday | Project Management | Review Documents | 2019-11-16 | 5.5 | 6 | Done
Total | Actual: | 35 |  |  |  | Plan: | 35
Week | Day | Task | Name Task | Date | Actual | Plan | Status
6 | Monday | Requirement | Write Usecase Decription | 2019-11-18 | 5.5 | 6 | Done
6 | Tuesday | Meeting Mentor |  | 2019-11-19 | 4 | 4 | Done
6 | Wednesday | Requirement | Create S.R.S | 2019-11-20 | 5.5 | 6 | Done
6 | Thursday | Requirement | Create ConOp | 2019-11-21 | 6 | 6 | Done
6 | Friday | Requirement | Create Tracebility Matrix | 2019-11-22 | 6 | 6 | Done
6 | Saturday | Project Management | Review Documents | 2019-11-23 | 5.5 | 6 | Done
Total | Actual: | 32.5 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
7 | Monday | Architecture and Desgin | Create Architecture Driver | 2019-11-25 | 6 | 6 | Inprogress
7 | Tuesday | Meeting Mentor |  | 2019-11-26 | 4 | 4 | Done
7 | Wednesday | Architecture and Desgin | Create Architecture Driver | 2019-11-27 | 6 | 6 | Done
7 | Thursday | Training | Set up React Native Invironment | 2019-11-28 | 6 | 6 | Done
7 | Friday | Training | Set up React Native Invironment | 2019-11-29 | 6 | 6 | Done
7 | Saturday | Project Management | Review Documents | 2019-11-30 | 5.5 | 6 | Done
Total | Actual: | 33.5 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
8 | Monday | Architecture and Desgin | Create Architecture Design | 2019-12-02 | 6 | 6 | Inprogress
8 | Tuesday | Meeting Mentor |  | 2019-12-03 | 4 | 4 | Done
8 | Wednesday | Architecture and Desgin | Create Architecture Design | 2019-12-04 | 6 | 6 | Done
8 | Thursday | Training | Component In React Native 1. Understand the sequence of a Component's operation 2. Text Component | 2019-12-05 | 6 | 6 | Done
8 | Friday | Training | Component In React Native 1. Understand the sequence of a Component's operation 2. Text Component | 2019-12-06 | 6 | 6 | Done
8 | Saturday | Project Management | Reviews Documents | 2019-12-07 | 5.5 | 6 | Done
Total | Actual: | 33.5 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
9 | Monday | Training | Debug with JavaScript Debug with React Native | 2019-12-09 | 6 | 6 | Done
9 | Tuesday | Training | Debug with JavaScript Debug with React Native | 2019-12-10 | 6 | 6 | Done
9 | Wednesday | Training | Debug with JavaScript Debug with React Native | 2019-12-11 | 6 | 6 | Done
9 | Thursday | Training | Debug with JavaScript Debug with React Native | 2019-12-12 | 6 | 6 | Done
9 | Friday | Meeting Mentor |  | 2019-12-13 | 4 | 4 | Done
9 | Saturday | Project Management | Reviews Documents | 2019-12-14 | 5.5 | 6 | Done
Total | Actual: | 33.5 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
10 | Monday | Training | 1. Realtime Database 2. Authentication | 2019-12-16 | 6 | 6 | Done
10 | Tuesday | Training | 1. Realtime Database 2. Authentication | 2019-12-17 | 6 | 6 | Done
10 | Wednesday | Training | 1. Realtime Database 2. Authentication | 2019-12-18 | 6 | 6 | Done
10 | Thursday | Meeting Mentor |  | 2019-12-19 | 4 | 4 | Done
10 | Friday | Training | 1. Realtime Database 2. Authentication | 2019-12-20 | 6 | 6 | Done
10 | Saturday | Project Management | Reviews Documents | 2019-12-21 | 5.5 | 6 | Done
Total | Actual: | 33.5 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
11 | Monday | Implementation | Feature "login" (App) | 2019-12-23 | 7 | 6 | Inprogress
11 | Tuesday | Implementation | Homepage app, button | 2019-12-24 | 8 | 6 | Inprogress
11 | Wednesday | Implementation | Homepage app, button | 2019-12-25 | 6.5 | 6 | Inprogress
11 | Thursday | Implementation | Navigation "View Information" | 2019-12-26 | 7.5 | 6 | Inprogress
11 | Friday | Implementation | Function "Company policy" interface | 2019-12-27 | 7 | 6 | Inprogress
11 | Saturday | Meeting team | Function "Company policy" interface | 2019-12-28 | 7.5 | 6 | Inprogress
Total | Actual: | 43.5 |  |  |  | Plan: | 36
Week | Day | Task | Name Task | Date | Actual | Plan | Status
12 | Monday | Implementation | Function "Personnel" interface | 2019-12-30 | 7 | 6 | Inprogress
| Tuesday | Implementation | Function "Personnel" interface | 2019-12-31 | 8 | 6 | Inprogress
12 | Wednesday | Implementation | Function "Organazation chart" interface | 2020-01-01 | 7 | 6 | Inprogress
12 | Thursday | Implementation | Function "Organazation chart" interface | 2020-01-02 | 8 | 6 | Inprogress
12 | Friday | Implementation | Feature "List company policy" | 2020-01-03 | 7 | 6 | Inprogress
12 | Saturday | Meeting mentor | Review documents | 2020-01-04 | 4 | 4 | Inprogress
12 | Sunday | Meeting team | Perpare documents | 2020-01-05 | 5 |  | Inprogress
Total | Actual: | 46 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
19 | Monday | Implementation | Coding update "List personel" | 2020-02-17 | 4 | 4 | Inprogress
19 | Tuesday | Implementation | Coding update "List personel" | 2020-02-18 | 6.5 | 6 | Done
19 | Wednesday | Implementation | Coding update "Home Screen" | 2020-02-19 | 4 | 4 | Done
19 | Thursday | Implementation | Research "Tab View Component" | 2020-02-20 | 6.5 | 6 | Inprogress
19 | Friday | Implementation | Research "Tab View Component" | 2020-02-21 | 6.5 | 6 | Inprogress
19 | Saturday | Meeting Mentor |  | 2020-02-22 | 4 | 4 | Done
19 | Actual: | 31.5 |  |  |  | Plan: | 30
Week | Day | Task | Name Task | Date | Actual | Plan | Status
20 | Monday | Implementation | Research "Tab View Component" | 2020-02-24 | 6 | 6 | Inprogress
20 | Tuesday | Implementation | Research "Tab View Component" | 2020-02-25 | 6 | 6 | Done
20 | Wednesday | Implementation | Research "Passing Parameters" | 2020-02-26 | 6 | 6 | Inprogress
20 | Thursday | Implementation | Research "Passing Parameters" | 2020-02-27 | 6 | 6 | Inprogress
20 | Friday | Meeting Mentor |  | 2020-02-28 | 4 | 4 | Done
20 | Saturday | Implementation | Research "Passing Parameters" | 2020-02-29 | 6 | 6 | Done
20 | Actual: | 34 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
21 | Monday | Implementation | Reserch "Map View" | 2020-03-02 | 6 | 6 | Inprogress
21 | Tuesday | Implementation | Reserch "Map View" | 2020-03-03 | 6 | 6 | Done
21 | Wednesday | Implementation | Coding Layout "Project" | 2020-03-04 | 6 | 6 | Inprogress
21 | Thursday | Meeting Mentor |  | 2020-03-05 | 4 | 4 | Done
21 | Friday | Implementation | Coding Layout "Project" | 2020-03-06 | 6 | 6 | Inprogress
21 | Saturday | Implementation | Coding Layout "Project" | 2020-03-07 | 6 | 6 | Inprogress
21 | Actual: | 34 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
22 | Monday | Implementation | Coding Layout "Project" | 2020-03-09 | 8 | 6 | Done
22 | Tuesday | Implementation | Coding Handler Data Project | 2020-03-10 | 8 | 6 | Inprogress
22 | Wednesday | Meeting Mentor |  | 2020-03-11 | 4 | 4 | Done
22 | Thursday | Implementation | Coding Handler Data Project | 2020-03-12 | 8 | 6 | Inprogress
22 | Friday | Implementation | Coding Handler Data Project | 2020-03-13 | 8 | 6 | Inprogress
22 | Saturday | Implementation | Coding Handler Data Project | 2020-03-14 | 8 | 6 | Done
22 | Actual: | 44 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
23 | Monday | Implementation | Coding Layout “Report Personal” | 2020-03-16 | 7 | 6 | Inprogress
23 | Tuesday | Implementation | Coding Layout “Report Personal” | 2020-03-17 | 7 | 6 | Done
23 | Wednesday | Meeting Mentor |  | 2020-03-18 | 4 | 4 | Done
23 | Thursday | Implementation | Coding Layout “Report Team” | 2020-03-19 | 7 | 6 | Inprogress
23 | Friday | Implementation | Coding Layout “Report Team” | 2020-03-20 | 7 | 6 | Inprogress
23 | Saturday | Implementation | Coding Layout “Report Team” | 2020-03-21 | 7 | 6 | Done
23 | Actual: | 39 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
24 | Monday | Implementation | Coding Layout “Report Group” | 2020-03-23 | 7 | 6 | Inprogress
24 | Tuesday | Implementation | Coding Layout “Report Group” | 2020-03-24 | 7 | 6 | Done
24 | Wednesday | Meeting Mentor |  | 2020-03-25 | 4 | 4 | Done
24 | Thursday | Implementation | Research Web “Vue” | 2020-03-26 | 7 | 6 | Inprogress
24 | Friday | Implementation | Research Web “Vue” | 2020-03-27 | 7 | 6 | Done
24 | Saturday | Implementation | Research Web “Geolocation API” | 2020-03-28 | 7 | 6 | Done
24 | Actual: | 39 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
25 | Monday | Implementation | Coding Web Admin "Geolocation API" | 2020-03-30 | 8 | 6 | Inprogress
25 | Tuesday | Implementation | Coding Web Admin "Geolocation API" | 2020-03-31 | 8 | 6 | Inprogress
25 | Wednesday | Meeting Mentor |  | 2020-04-01 | 4 | 4 | Done
25 | Thursday | Implementation | Coding Web Admin "Geolocation API" | 2020-04-02 | 8 | 6 | Inprogress
25 | Friday | Implementation | Coding Web Admin "Geolocation API" | 2020-04-03 | 8 | 6 | Inprogress
25 | Saturday | Implementation | Coding Web Admin "Geolocation API" | 2020-04-04 | 8 | 6 | Done
25 | Actual: | 44 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
26 | Monday | Implementation | Coding Layout "Birthday" | 2020-04-06 | 7 | 6 | Inprogress
26 | Tuesday | Implementation | Coding Layout "Birthday" | 2020-04-07 | 7 | 6 | Done
26 | Wednesday | Meeting Mentor |  | 2020-04-08 | 4 | 4 | Done
26 | Thursday | Implementation | Coding Logic Get Day | 2020-04-09 | 8 | 6 | Done
26 | Friday | Implementation | Coding Logic Birthday | 2020-04-10 | 8 | 6 | Inprogress
26 | Saturday | Implementation | Coding Logic Birthday | 2020-04-11 | 8 | 6 | Done
26 | Actual: | 42 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
27 | Monday | Implementation | Research Add Music Birthday IOS | 2020-04-13 | 7 | 6 | Done
27 | Tuesday | Implementation | Music Birthday IOS | 2020-04-14 | 7 | 6 | Inprogress
27 | Wednesday | Meeting Mentor |  | 2020-04-15 | 4 | 4
27 | Thursday | Implementation | Music Birthday IOS | 2020-04-16 | 8 | 6 | Done
27 | Friday | Implementation | Config Music Birthday IOS | 2020-04-17 | 8 | 6 | Done
27 | Saturday | Implementation | Research “Chart” | 2020-04-18 | 7 | 6 | Done
27 | Actual: | 41 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
28 | Monday | Implementation | Research “Chart” | 2020-04-20 | 7 | 6 | Done
28 | Tuesday | Implementation | Config “Chart” | 2020-04-21 | 7 | 6 | Inprogress
28 | Wednesday | Meeting Mentor |  | 2020-04-22 | 4 | 4 | Done
28 | Thursday | Implementation | Config “Chart” | 2020-04-23 | 8 | 6 | Done
28 | Friday | Implementation | Coding Layout “Reports Sales” | 2020-04-24 | 8 | 6 | Inprogress
28 | Saturday | Meeting Customer |  | 2020-04-25 | 6 | 6 | Done
28 | Actual: | 40 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
29 | Monday | Implementation | Coding Layout “Reports Sales” | 2020-04-27 | 7 | 6 | Done
29 | Tuesday | Implementation | Coding Layout “Chart Sales Result” | 2020-04-28 | 7 | 6 | Inprogress
29 | Wednesday | Meeting Mentor |  | 2020-04-29 | 4 | 4 | Done
29 | Saturday | Implementation | Coding Layout “Chart Sales Result” | 2020-05-02 | 7 | 6 | Inprogress
29 | Actual: | 25 |  |  |  | Plan: | 22
Week | Day | Task | Name Task | Date | Actual | Plan | Status
30 | Monday | Implementation | Coding Layout “Chart Sales Compare” | 2020-05-04 | 7 | 6 | Inprogress
30 | Tuesday | Implementation | Coding Layout “Chart Sales Compare” | 2020-05-05 | 7 | 6 | Done
30 | Wednesday | Meeting Mentor |  | 2020-05-06 | 4 | 4 | Done
30 | Thursday | Implementation | Coding Handle Data “ Group Sales Result Report” | 2020-05-07 | 8 | 6 | Inprogress
30 | Friday | Implementation | Coding Handle Data “ Group Sales Result Report” | 2020-05-08 | 8 | 6 | Inprogress
30 | Saturday | Implementation | Coding Handle Data “ Group Sales Result Report” | 2020-05-09 | 8 | 6 | Done
30 | Actual: | 42 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
31 | Monday | Implementation | Coding Handle Data “ Personal Sales Result Chart” | 2020-05-11 | 9 | 6 | Inprogress
31 | Tuesday | Implementation | Coding Handle Data “ Personal Sales Result Chart” | 2020-05-12 | 9 | 6 | Inprogress
31 | Wednesday | Meeting Mentor |  | 2020-05-13 | 4 | 4 | Done
31 | Thursday | Implementation | Coding Handle Data “ Personal Sales Result Chart” | 2020-05-14 | 9 | 6 | Inprogress
31 | Friday | Implementation | Coding Handle Data “ Personal Sales Result Chart” | 2020-05-15 | 9 | 6 | Inprogress
31 | Saturday | Implementation | Coding Handle Data “ Personal Sales Result Chart” | 2020-05-16 | 9 | 6 | Done
31 | Actual: | 49 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
32 | Monday | Implementation | Coding Handle Data “ Team Sales Result Chart” | 2020-05-18 | 10 | 6 | Inprogress
32 | Tuesday | Implementation | Coding Handle Data “ Team Sales Result Chart” | 2020-05-19 | 10 | 6 | Inprogress
32 | Wednesday | Meeting Mentor |  | 2020-05-20 | 4 | 4 | Done
32 | Thursday | Implementation | Coding Handle Data “ Team Sales Result Chart” | 2020-05-21 | 10 | 6 | Inprogress
32 | Friday | Implementation | Coding Handle Data “ Team Sales Result Chart” | 2020-05-22 | 10 | 6 | Inprogress
32 | Saturday | Implementation | Coding Handle Data “ Team Sales Result Chart” | 2020-05-23 | 10 | 6 | Done
32 | Actual: | 54 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
33 | Monday | Implementation | Coding Handle Data “ Personal Sales Compare Chart” | 2020-05-25 | 10 | 6 | Inprogress
33 | Tuesday | Implementation | Coding Handle Data “ Personal Sales Compare Chart” | 2020-05-26 | 10 | 6 | Inprogress
33 | Wednesday | Meeting Mentor |  | 2020-05-27 | 4 | 4 | Done
33 | Thursday | Implementation | Coding Handle Data “ Personal Sales Compare Chart” | 2020-05-28 | 10 | 6 | Inprogress
33 | Friday | Implementation | Coding Handle Data “ Personal Sales Compare Chart” | 2020-05-29 | 10 | 6 | Inprogress
33 | Saturday | Implementation | Coding Handle Data “ Personal Sales Compare Chart” | 2020-05-30 | 10 | 6 | Done
33 | Actual: | 54 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
34 | Monday | Implementation | Coding Handle Data “ Team Sales Compare Chart” | 2020-06-01 | 10 | 6 | Inprogress
34 | Tuesday | Implementation | Coding Handle Data “ Team Sales Compare Chart” | 2020-06-02 | 10 | 6 | Inprogress
34 | Wednesday | Meeting Mentor |  | 2020-06-03 | 4 | 4 | Done
34 | Thursday | Implementation | Coding Handle Data “ Team Sales Compare Chart” | 2020-06-04 | 10 | 6 | Inprogress
34 | Friday | Implementation | Coding Handle Data “ Team Sales Compare Chart” | 2020-06-05 | 10 | 6 | Inprogress
34 | Saturday | Implementation | Coding Handle Data “ Team Sales Compare Chart” | 2020-06-06 | 10 | 6 | Done
34 | Actual: | 54 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
35 | Monday | Review Code |  | 2020-06-08 | 6 | 6 | Done
35 | Tuesday | Review Code |  | 2020-06-09 | 6 | 6 | Done
35 | Wednesday | Meeting Mentor |  | 2020-06-10 | 4 | 4 | Done
35 | Thursday | Meeting Customer |  | 2020-06-11 | 4 | 4 | Done
35 | Friday | Reivew Document |  | 2020-06-12 | 6 | 6 | Done
35 | Saturday | Reivew Document |  | 2020-06-13 | 6 | 6 | Done
35 | Actual: | 32 |  |  |  | Plan: | 32

## Quốc Nhân
Timelog: | Quốc Nhân
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
1 | Monday | Meeting Mentor |  | 14/10/2019 | 4 | 4 | Done
1 | Tuesday | Research | Research Information WebGIS | 15/10/2019 | 6 | 6 | Inprogress
1 | Wednesday | Research | Research Information WebGIS | 16/10/2019 | 7 | 5 | Inprogress
1 | Thursday | Project Management | Create Member Charter | 17/10/2019 | 5 | 5 | Done
1 | Friday | Meetting Customer |  | 18/10/2019 | 5 | 5 | Done
1 | Saturday | Research | Research WebGIS, Database & Code | 19/10/2019 | 4 | 6 | Inprogress
Total | Actual: | 31 |  |  |  | Plan: | 31
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
2 | Monday | Project Management | Create Team Charter, project charter, plan | 21/10/2019 | 6 | 6 | Done | PM_TeamCharter_Ver1.0.docx
2 | Tuesday | Research | Research Information WebGIS | 22/10/2019 | 5 | 5 | Inprogress
2 | Wednesday | Meeting Mentor |  | 23/10/2019 | 4 | 4 | Done
2 | Thursday | Project Management | Draw the steps submitted and changed github & gg drive | 24/10/2019 | 5 | 5 | Done | PM_ConfigurationManagementPlan_Ver1.0.docx
2 | Friday | Research | Reading Customer Documments | 25/10/2019 | 5 | 5 | Done
2 | Saturday | Research | Presentation Customer Documments | 26/10/2019 | 5 | 5 | Done
Total | Actual: | 30 |  |  |  | Plan: | 30
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
3 | Monday | Project Management | Create Project plan v1.0, Install Android studio, Genymotion, detail design plan | 2019-10-28 | 8 | 6 | Done
3 | Tuesday | Meeting Mentor |  | 2019-10-29 | 4 | 4 | Inprogress | PM_ProjectPlan_Ver1.1.docx
3 | Wednesday | Meetting Customer | Meeting with Customer, Update Project plan v1.2 | 2019-10-30 | 4.5 | 5 | Inprogress | PM_ProjectPlan_Ver1.2.docx
3 | Thursday | Project Management | Install React Native, detail desing process | 2019-10-31 | 10 | 6 | Inprogress
3 | Friday | Project Management | Install React Native, Research Information React Native, Update Project plan v1.1 | 2019-11-01 | 6 | 6 | Inprogress
3 | Saturday | Project Management | Update Project plan v1.3, Create project charter v1.0 | 2019-11-02 | 4 | 6 | Inprogress | PM_ProjectPlan_Ver1.3.docx
3 | Sunday | Implementation | Install React Native | 2019-11-03 | 3 |  | Done
Total | Actual: | 39.5 |  |  |  | Plan: | 33
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
4 | Monday | Project Management | Create Question function v1.0, update project charter v1.0, update Milestone v1.0 | 2019-11-04 | 7 | 6 | Done | PM_ProjectCharter_Ver1.0.docx, PM_Question_Ver1.0.xlxs, PM_Milestone_Ver1.0.xlxs
4 | Tuesday | Project Management | Create SRS v1.0, implement plan v1.0, Update detail design, training plan, RE plan | 2019-11-05 | 10 | 6 | Inprogress | PM_Implementprocess_Ver1.0.docx, PM_SRS_Ver1.0.docx, PM_Implementplan_Ver1.0.docx
4 | Wednesday | Meeting Mentor | Review documents | 2019-11-06 | 4 | 4 | Done
4 | Thursday | Project Management | Update implement process v1.1, Srs document | 2019-11-07 | 6.5 | 6 | Done | PM_Implementprocess_Ver1.0.docx
4 | Friday | Meetting Customer | Metting Customer | 2019-11-08 | 5 | 5 | Done
4 | Saturday | Project Management | Review documents | 2019-11-09 | 7 | 6 | Done
2019-11-10
Total | Actual: | 39.5 |  |  |  | Plan: | 33
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
5 | Monday | Meeting team | Prepare UCD, Prepare TracebilityMetrix | 2019-11-11 | 5 | 5 | Done | RE_TracebilityMetrix_Ver1.0, RE_UseCase_Ver1.0
5 | Tuesday | Meeting Mentor | Review documents | 2019-11-12 | 4 | 4 | Done
5 | Wednesday | Requirement | UCD 30-41 RE | 2019-11-13 | 7.5 | 6 | Inprogress | RE_UseCase_Ver1.1
5 | Thursday | Meeting team | research react | 2019-11-14 | 5.5 | 6 | Inprogress
5 | Friday | Requirement | Update data dictionary SRS RE | 2019-11-15 | 6.5 | 6 | Inprogress | RE_SRS_Ver1.1
5 | Saturday | Requirement | Update data dictionary SRS RE | 2019-11-16 | 6 | 6 | Inprogress | RE_SRS_Ver1.1
2019-11-17
Total | Actual: | 34.5 |  |  |  | Plan: | 33
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
6 | Monday | Meeting team | Document SRS | 2019-11-18 | 5.5 | 6 | Done
6 | Tuesday | Meetting Customer |  | 2019-11-19 | 4 | 4 | Done
6 | Wednesday | Architect | Architecture driver document (Testability), static view, Create tracebility metrix | 2019-11-20 | 4.5 | 5 | Inprogress | AR_ArchitectureDriversDocument_Ver1.0
6 | Thursday | Meeting team |  | 2019-11-21 | 5.5 | 6 | Done
6 | Friday | Architect | Architecture driver document (Testability) | 2019-11-22 | 6 | 5 | Inprogress | AR_ArchitectureDriversDocument_Ver1.0
6 | Saturday | Architect | Architecture driver document (Testability) | 2019-11-23 | 5.5 | 5 | Inprogress | AR_ArchitectureDriversDocument_Ver1.0
2019-11-24
Total | Actual: | 31 |  |  |  | Plan: | 31
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
7 | Monday | Project Management | Create UC description RE (UC 25-36) | 2019-11-25 | 10 | 6 | Done | RE_UseCaseDescription_V1.0
7 | Tuesday | Meeting Mentor | Show UCDescription RE, Quality Attribute | 2019-11-26 | 3 | 4 | Done
7 | Wednesday | Architecture and Desgin | Update Architecture Drive V1.0, install react native | 2019-11-27 | 10 | 6 | Inprogress | PM_architecturedrive_V1.0
7 | Thursday | Architecture and Desgin | Create detail design (module login/logout admin & website) | 2019-11-28 | 10 | 6 | Inprogress
7 | Friday | Requirement | Create tracebility metrix | 2019-11-29 | 6 | 6 | Done | RE_Tracebilitymetrix_V1.0
7 | Saturday | Requirement | Review ERD, datadictionary for RE | 2019-11-30 | 8 | 6 | Done | RE_SRS_V1.1
7 | Sunday | Requirement | Update SRS document | 2019-12-01 | 3 |  |  | RE_SRS_V1.1
Total | Actual: | 50 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
8 | Monday | Architecture and Desgin | Create Business rule, massage list | 2019-12-02 | 10 | 6 | Inprogress | DE_BusinessRule_V1.0, DE_MessageList_V1.0
8 | Tuesday | Meeting Mentor | Review documents | 2019-12-03 | 4 | 4 | Done
8 | Wednesday | Architecture and Desgin | DE_UseCaseDescription_Ver1.0 (module 1) | 2019-12-04 | 6.5 | 6 | Done | DE_UseCaseDescription_Ver1.0
8 | Thursday | Architecture and Desgin | Detail Desin app (module 1) | 2019-12-05 | 7.5 | 6 | Inprogress | https://www.figma.com/proto/MlQkRuC4HQOw51m9CU8kCB/App?node-id=2%3A18&scaling=scale-down
8 | Friday | Architecture and Desgin | Detail Desin app (module 1) | 2019-12-06 | 7.5 | 6 | Inprogress | https://www.figma.com/proto/MlQkRuC4HQOw51m9CU8kCB/App?node-id=2%3A18&scaling=scale-down
8 | Saturday | Architecture and Desgin | Detail Desin app (module 1) | 2019-12-07 | 7.5 | 6 | Inprogress | https://www.figma.com/proto/MlQkRuC4HQOw51m9CU8kCB/App?node-id=2%3A18&scaling=scale-down
2019-12-08
Total | Actual: | 43 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
9 | Monday | Architecture and Desgin | Business rule, massage list | 2019-12-09 | 10 | 6 | Done | DE_BusinessRule_V1.0, DE_MessageList_V1.0
9 | Tuesday | Architecture and Desgin | Sequence Module 1 | 2019-12-10 | 7.5 | 6 | Inprogress
9 | Wednesday | Architecture and Desgin | UC digram Module 1 | 2019-12-11 | 6.5 | 6 | Inprogress
9 | Thursday | Architecture and Desgin | UC digram Module 1 | 2019-12-12 | 5.5 | 6 | Inprogress
9 | Friday | Meeting Mentor | Review documents | 2019-12-13 | 4 | 4 | Done
9 | Saturday | Requirement | Sequence Module 1 | 2019-12-14 | 8.5 | 6 | Inprogress
2019-12-15
Total | Actual: | 42 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
10 | Monday | Architecture and Desgin |  | 2019-12-16 | 10 | 6 | Inprogress
10 | Tuesday | Architecture and Desgin | Detail Desin app (module 1) | 2019-12-17 | 4 | 4 | Done | https://www.figma.com/proto/MlQkRuC4HQOw51m9CU8kCB/App?node-id=2%3A18&scaling=scale-down
10 | Wednesday | Architecture and Desgin | Sequence Module 1 | 2019-12-18 | 5.5 | 6 | Inprogress
10 | Thursday | Architecture and Desgin | UC digram Module 1 | 2019-12-19 | 7.5 | 6 | Done
10 | Friday | Meeting Mentor | Review documents | 2019-12-20 | 4 | 4 | Done
10 | Saturday | Meeting team | Review documents | 2019-12-21 | 6 | 6 | Done
2019-12-22
Total | Actual: | 37 |  |  |  | Plan: | 32
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
11 | Monday | Architecture and Desgin | Sequence Module 1 | 2019-12-23 | 7 | 6 | Inprogress
11 | Tuesday | Architecture and Desgin | Sequence Module 1 | 2019-12-24 | 5 | 6 | Done
11 | Wednesday | Architecture and Desgin | Detail Desin app (module 2) | 2019-12-25 | 6.5 | 6 | Inprogress
11 | Thursday | Architecture and Desgin | Detail Desin app (module 2) | 2019-12-26 | 7.5 | 6 | Inprogress
11 | Friday | Architecture and Desgin | Detail Desin app (module 2) | 2019-12-27 | 5.5 | 6 | Inprogress
11 | Saturday | Meeting team | Review documents | 2019-12-28 | 7.5 | 6 | Inprogress
11 |  |  |  | 2019-12-29
Total | Actual: | 39 |  |  |  | Plan: | 36
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
12 | Monday | Architecture and Desgin | datadictionary for DD | 2019-12-30 | 7 | 6 | Inprogress
12 | Tuesday | Architecture and Desgin | Sequence Module 1 | 2019-12-31 | 8 | 6 | Inprogress
12 | Wednesday | Architecture and Desgin | Sequence Module 1 | 2020-01-01 | 7 | 6 | Inprogress
12 | Thursday | Architecture and Desgin | Use Case Description module 1 (1-17) | 2020-01-02 | 8 | 6 | Inprogress
12 | Friday | Architecture and Desgin | Use Case Description module 1 (1-17) | 2020-01-03 | 7 | 6 | Inprogress
12 | Saturday | Meeting mentor | Review documents | 2020-01-04 | 4 | 4 | Inprogress
12 | Sunday | Meeting team | Perpare documents, review | 2020-01-05 | 5 |  | Inprogress
Total | Actual: | 46 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
13 | Monday | Architecture and Desgin | Design prototype, sequence, use case description "Login" app | 2020-01-06 | 7 |  | Done
13 | Tuesday | Architecture and Desgin | Design prototype, sequence, use case description "Login" app | 2020-01-07 | 8 |  | Done
13 | Wednesday | Architecture and Desgin | Design prototype, sequence, use case description "Login" website | 2020-01-08 | 7 |  | Done
13 | Thursday | Architecture and Desgin | Design prototype, sequence, use case description "Login" website | 2020-01-09 | 8 |  | Done
13 | Friday | Architecture and Desgin | Design prototype, sequence, use case description "Logout" app | 2020-01-10 | 7 |  | Done
13 | Saturday | Architecture and Desgin | Design prototype, sequence, use case description "Logout" website | 2020-01-11 | 7 |  | Done
13 | Sunday |  |  | 2020-01-12
Total | Actual: | 44 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
14 | Monday | Architecture and Desgin | Design prototype, sequence, use case description "Search personnel" app | 2020-01-13 | 7 |  | Inprogress
14 | Tuesday | Architecture and Desgin | Design prototype, sequence, use case description "Search personnel" app | 2020-01-14 | 8 |  | Done
14 | Wednesday | Architecture and Desgin | Design prototype, sequence, use case description "View personnel" app | 2020-01-15 | 7 |  | Done
14 | Thursday | Architecture and Desgin | Design prototype, sequence, use case description "Upload organizational chart" website | 2020-01-16 | 8 |  | Inprogress
14 | Friday | Architecture and Desgin | Design prototype, sequence, use case description "Upload organizational chart" website | 2020-01-17 | 7 |  | Inprogress
14 | Saturday | Architecture and Desgin | Design prototype, sequence, use case description "Upload organizational chart" website | 2020-01-18 | 6 |  | Done
14 | Sunday |  |  | 2020-01-19
Total | Actual: | 43 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
15 | Monday | Architecture and Desgin | Design prototype, sequence, use case description "View organizational chart" app | 2020-01-20 | 7 | 6 | Done
15 | Tuesday | Architecture and Desgin | Design prototype, sequence, use case description "Add company policy" website | 2020-01-21 | 8 | 6 | Inprogress
15 | Wednesday | Architecture and Desgin | Design prototype, sequence, use case description "Add company policy" website | 2020-01-22 | 8 | 6 | Inprogress
15 | Thursday | Architecture and Desgin | Design prototype, sequence, use case description "Edit company policy" website | 2020-01-23 | 8 | 6 | Inprogress
15 | Friday | Architecture and Desgin | Design prototype, sequence, use case description "Edit company policy" website | 2020-01-24 | 8 | 6 | Inprogress
15 | Saturday | Architecture and Desgin | Design prototype, sequence, use case description "Delete company policy" website | 2020-01-25 | 10 |  | Inprogress
15 | Sunday |  |  | 2020-01-26 |  |  | Inprogress
Total | Actual: | 49 |  |  |  | Plan: | 30
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
16 | Monday |  | Nghỉ | 2020-01-27 |  |  | Inprogress
16 | Tuesday |  |  | 2020-01-28 |  |  | Inprogress
16 | Wednesday |  |  | 2020-01-29 |  |  | Inprogress
16 | Thursday |  |  | 2020-01-30 |  |  | Inprogress
16 | Friday |  |  | 2020-01-31 |  |  | Inprogress
16 | Saturday |  |  | 2020-02-01 |  |  | Inprogress
16 | Sunday |  |  | 2020-02-02 |  |  | Inprogress
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
17 | Monday |  | Nghỉ | 2020-02-03 |  |  | Inprogress
17 | Tuesday |  |  | 2020-02-04 |  |  | Inprogress
17 | Wednesday |  |  | 2020-02-05 |  |  | Inprogress
17 | Thursday |  |  | 2020-02-06 |  |  | Inprogress
17 | Friday |  |  | 2020-02-07 |  |  | Inprogress
17 | Saturday |  |  | 2020-02-08 |  |  | Inprogress
17 | Sunday |  |  | 2020-02-09 |  |  | Inprogress
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
18 | Monday |  | Nghỉ | 2020-02-10 |  |  | Inprogress
18 | Tuesday |  |  | 2020-02-11 |  |  | Inprogress
18 | Wednesday |  |  | 2020-02-12 |  |  | Inprogress
18 | Thursday |  |  | 2020-02-13 |  |  | Inprogress
18 | Friday |  |  | 2020-02-14 |  |  | Inprogress
18 | Saturday |  |  | 2020-02-15 |  |  | Inprogress
18 | Sunday |  |  | 2020-02-16 |  |  | Inprogress
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
19 | Monday | Architecture and Desgin | Design prototype, sequence, use case description "View company policy" app | 2020-02-17 | 10 |  | Inprogress
19 | Tuesday | Architecture and Desgin | Design prototype, sequence, use case description "View company policy" website | 2020-02-18 | 10.5 |  | Inprogress
19 | Wednesday | Architecture and Desgin | Design prototype, sequence, use case description "View personnel" website | 2020-02-19 | 6.5 |  | Inprogress
19 | Thursday | Architecture and Desgin | Design prototype, sequence, use case description "View organizational chart" website | 2020-02-20 | 8 |  | Inprogress
19 | Friday | Architecture and Desgin | Design prototype, sequence, use case description "View account information" website | 2020-02-21 | 4 |  | Inprogress
19 | Saturday | Meeting mentor | Design prototype, sequence, use case description "View account information" website | 2020-02-22 | 4 |  | Inprogress
19 |  |  |  | 2020-02-23 |  |  | Inprogress
Total | Actual: | 43 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
20 | Monday | Architecture and Desgin | Design prototype, sequence, use case description "Add account" website | 2020-02-24 | 6.5 |  | Inprogress
20 | Tuesday | Architecture and Desgin | Design prototype, sequence, use case description "Add account" website | 2020-02-25 | 6.5 |  | Inprogress
20 | Wednesday | Architecture and Desgin | Design prototype, sequence, use case description "Edit account" website | 2020-02-26 | 7 |  | Inprogress
20 | Thursday | Architecture and Desgin | Design prototype, sequence, use case description "Edit account" website | 2020-02-27 | 7 |  | Inprogress
20 | Friday | Meeting Mentor | Design messages list module 1 | 2020-02-28 | 5 |  | Inprogress
20 | Saturday | Architecture and Desgin | Design messages list module 1 | 2020-02-29 | 4 |  | Inprogress
20 | Sunday |  |  | 2020-03-01 |  |  | Inprogress
Total | Actual: | 36 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
21 | Monday | Architecture and Desgin | Design messages list module 1 | 2020-03-02 | 6 |  | Inprogress
21 | Tuesday | Architecture and Desgin | Design business rule module 1 | 2020-03-03 | 7.5 |  | Inprogress
21 | Wednesday | Architecture and Desgin | Design business rule module 1 | 2020-03-04 | 6.5 |  | Inprogress
21 | Thursday | Meeting Mentor | Design use case diagram module 1 | 2020-03-05 | 6.5 |  | Inprogress
21 | Friday |  | Design use case diagram module 1 | 2020-03-06 | 7.5 |  | Inprogress
21 | Saturday |  | Design use case diagram module 1 | 2020-03-07 | 6 |  | Inprogress
21 | Sunday |  |  | 2020-03-08 |  |  | Inprogress
Total | Actual: | 40 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
22 | Monday | Architecture and Desgin | Design prototype, sequence, use case description "View all project listings" app | 2020-03-09 | 7 |  | Inprogress
22 | Tuesday | Architecture and Desgin | Design prototype, sequence, use case description "View all project listings" app | 2020-03-10 | 8 |  | Inprogress
22 | Wednesday | Meeting Mentor |  | 2020-03-11 | 6 | 6 | Inprogress
22 | Thursday | Architecture and Desgin | Design prototype, sequence, use case description "View all project listings" app | 2020-03-12 | 7 |  | Inprogress
22 | Friday | Architecture and Desgin | Design prototype, sequence, use case description "View all project listings being implemented" app | 2020-03-13 | 7 |  | Inprogress
22 | Saturday | Architecture and Desgin | Design prototype, sequence, use case description "View all project listings being implemented" app | 2020-03-14 | 4 |  | Inprogress
22 | Sunday |  |  | 2020-03-15 | 5 |  | Inprogress
Total | Actual: | 44 |  |  |  | Plan: | 6
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
23 | Monday | Architecture and Desgin | Design prototype, sequence, use case description "View all project listings being implemented" app | 2020-03-16 | 8 |  | Inprogress
23 | Tuesday | Architecture and Desgin | Design prototype, sequence, use case description "View all project listings prepare to deploy" app | 2020-03-17 | 8 |  | Inprogress
23 | Wednesday | Meeting Mentor |  | 2020-03-18 | 6 | 6 | Inprogress
23 | Thursday | Architecture and Desgin | Design prototype, sequence, use case description "View all project listings prepare to deploy" app | 2020-03-19 | 8 |  | Inprogress
23 | Friday | Architecture and Desgin | Design prototype, sequence, use case description "View all project listings has deployed" app | 2020-03-20 | 7 |  | Inprogress
23 | Saturday | Architecture and Desgin | Design prototype, sequence, use case description "View all project listings has deployed" app | 2020-03-21 | 4 |  | Inprogress
23 | Sunday |  |  | 2020-03-22 | 5 |  | Inprogress
Total | Actual: | 46 |  |  |  | Plan: | 6
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
24 | Monday | Architecture and Desgin | Design prototype, sequence, use case description "View all project listings has deployed" app | 2020-03-23 | 7 |  | Inprogress
24 | Tuesday | Architecture and Desgin | Design prototype, sequence, use case description "View all project listings" website | 2020-03-24 | 8 |  | Inprogress
24 | Wednesday | Meeting Mentor |  | 2020-03-25 | 7 |  | Inprogress
24 | Thursday | Architecture and Desgin | Design prototype, sequence, use case description "View all project listings" website | 2020-03-26 | 8 |  | Inprogress
24 | Friday | Architecture and Desgin | Design prototype, sequence, use case description "Add projects" website | 2020-03-27 | 7 |  | Inprogress
24 | Saturday | Architecture and Desgin | Design prototype, sequence, use case description "Add projects" website | 2020-03-28 | 4 |  | Inprogress
24 | Sunday | Architecture and Desgin | Design use case diagram module 3 | 2020-03-29 | 5 |  | Inprogress
Total | Actual: | 46 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
25 | Monday | Architecture and Desgin | Design prototype, sequence, use case description "Add projects" website | 2020-03-30 | 8 |  | Inprogress
25 | Tuesday | Architecture and Desgin | Design prototype, sequence, use case description "Add projects" website | 2020-03-31 | 8 |  | Inprogress
25 | Wednesday | Meeting Mentor |  | 2020-04-01 | 6 | 6 | Inprogress
25 | Thursday | Architecture and Desgin | Design prototype, sequence, use case description "Edit projects" website | 2020-04-02 | 8 |  | Inprogress
25 | Friday | Architecture and Desgin | Design prototype, sequence, use case description "Edit projects" website | 2020-04-03 | 7 |  | Inprogress
25 | Saturday | Architecture and Desgin | Design prototype, sequence, use case description "Edit projects" website | 2020-04-04 | 7 |  | Inprogress
25 | Sunday | Architecture and Desgin | Design use case diagram module 3 | 2020-04-05 | 10 |  | Inprogress
Total | Actual: | 54 |  |  |  | Plan: | 6
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
26 | Monday | Architecture and Desgin | Design messages list module 2 | 2020-04-06 | 7 |  | Inprogress
26 | Tuesday | Architecture and Desgin | Design messages list module 2, Design business rule module 2 | 2020-04-07 | 8 |  | Inprogress
26 | Wednesday | Meeting Mentor | Design messages list module 3 | 2020-04-08 | 6 | 6 | Inprogress
26 | Thursday | Architecture and Desgin | Design messages list module 2 | 2020-04-09 | 8 |  | Inprogress
26 | Friday | Architecture and Desgin | Design business rule module 2 | 2020-04-10 | 7 |  | Inprogress
26 | Saturday | Architecture and Desgin | Design use case diagram module 2 | 2020-04-11 | 4 |  | Inprogress
26 | Sunday | Architecture and Desgin | Design use case diagram module 3 | 2020-04-12 | 5 |  | Inprogress
Total | Actual: | 45 |  |  |  | Plan: | 6
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
27 | Monday | Architecture and Desgin | Design use case diagram module 2 | 2020-04-13 | 7 |  | Inprogress
27 | Tuesday | Architecture and Desgin | Design use case diagram module 2 | 2020-04-14 | 8 |  | Inprogress
27 | Wednesday | Meeting Mentor | Design messages list module 3 | 2020-04-15 | 6 | 6 | Inprogress
27 | Thursday | Architecture and Desgin | Design prototype, sequence, use case description View business results the week "Employees" app | 2020-04-16 | 8 |  | Inprogress
27 | Friday | Architecture and Desgin | Design prototype, sequence, use case description View business results the week "Employees" app | 2020-04-17 | 8 |  | Inprogress
27 | Saturday | Architecture and Desgin | Design prototype, sequence, use case description View details of the weekly business results the "Employees" app | 2020-04-18 | 8 |  | Inprogress
27 | Sunday | Architecture and Desgin | Design business rule module 3 | 2020-04-19 | 5 |  | Inprogress
Total | Actual: | 50 |  |  |  | Plan: | 6
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
28 | Monday | Architecture and Desgin | Design prototype, sequence, use case description View details of the weekly business results the "Employees" app | 2020-04-20 | 8 |  | Inprogress
28 | Tuesday | Architecture and Desgin | Design prototype, sequence, use case description View business results the week "Team" app | 2020-04-21 | 8 |  | Inprogress
28 | Wednesday | Meeting Mentor | Design prototype, sequence, use case description View business results the week "Team" app | 2020-04-22 | 6 | 6 | Inprogress
28 | Thursday | Architecture and Desgin | Design prototype, sequence, use case description View business results the week "Team" app | 2020-04-23 | 8 |  | Inprogress
28 | Friday | Architecture and Desgin | Design prototype, sequence, use case description View business results the week "Room" app | 2020-04-24 | 7 |  | Inprogress
28 | Saturday | Architecture and Desgin | Design prototype, sequence, use case description View business results the week "Room" app | 2020-04-25 | 8 |  | Inprogress
28 | Sunday | Architecture and Desgin | Design business rule module 3 | 2020-04-26 | 10 |  | Inprogress
Total | Actual: | 55 |  |  |  | Plan: | 6
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
29 | Monday | Architecture and Desgin | Design prototype, sequence, use case description View business results graph "Employees" app | 2020-04-27 | 10 |  | Inprogress
29 | Tuesday | Architecture and Desgin | Design prototype, sequence, use case description View business results graph "Employees" app | 2020-04-28 | 12 |  | Inprogress
29 | Wednesday | Meeting Mentor | Design prototype, sequence, use case description Search business results graph "Employees" app | 2020-04-29 | 6 |  | Inprogress
29 | Thursday | Architecture and Desgin | Design prototype, sequence, use case description Search business results graph "Employees" app | 2020-04-30 | 10 |  | Inprogress
29 | Friday | Architecture and Desgin | Design prototype, sequence, use case description View the "Team" business results graph app | 2020-05-01 | 10 |  | Inprogress
29 | Saturday | Architecture and Desgin | Design prototype, sequence, use case description View the "Team" business results graph app | 2020-05-02 | 8 |  | Inprogress
29 | Sunday | Architecture and Desgin | Design messages list module 3, Design business rule module 3 | 2020-05-03 | 9 |  | Inprogress
Total | Actual: | 65 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
30 | Monday | Architecture and Desgin | Design prototype, sequence, use case description Search results graph "Team" app | 2020-05-04 | 10 |  | Inprogress
30 | Tuesday | Architecture and Desgin | Design prototype, sequence, use case description Search results graph "Team" app | 2020-05-05 | 5 |  | Inprogress
30 | Wednesday | Meeting Mentor | Design prototype, sequence, use case description View business results graph "Rooms" app | 2020-05-06 | 6 | 6 | Inprogress
30 | Thursday | Architecture and Desgin | Design prototype, sequence, use case description View business results graph "Rooms" app | 2020-05-07 | 8 |  | Inprogress
30 | Friday | Architecture and Desgin | Design prototype, sequence, use case description Search business results graph "Room" app | 2020-05-08 | 7 |  | Inprogress
30 | Saturday | Architecture and Desgin | Design prototype, sequence, use case description Search business results graph "Room" app | 2020-05-09 | 4 |  | Inprogress
30 | Sunday | Architecture and Desgin | Design prototype, sequence, use case description View compare business results "Employees" | 2020-05-10 | 10 |  | Inprogress
Total | Actual: | 50 |  |  |  | Plan: | 6
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
31 | Monday | Architecture and Desgin | Design prototype, sequence, use case description Search compare business results "Employees" app | 2020-05-10 | 10 |  | Inprogress
31 | Tuesday | Architecture and Desgin | Design prototype, sequence, use case description Search compare business results "Employees" app | 2020-05-11 | 8 |  | Inprogress
31 | Wednesday | Meeting Mentor | Design prototype, sequence, use case description View the business results "Team" app | 2020-05-12 | 6 | 6 | Inprogress
31 | Thursday | Architecture and Desgin | Design prototype, sequence, use case description View the business results "Team" app, Design prototype, sequence, use case description View personal information app | 2020-05-13 | 8 |  | Inprogress
31 | Friday | Architecture and Desgin | Design prototype, sequence, use case description Search compare business results "Team" app | 2020-05-14 | 7 |  | Inprogress
31 | Saturday | Architecture and Desgin | Design prototype, sequence, use case description Search compare business results "Team" app, Design prototype, sequence, use case description View personal information app | 2020-05-15 | 8 |  | Inprogress
31 | Sunday | Architecture and Desgin | Design prototype, sequence, use case description Search compare business results "Team" app | 2020-05-16 | 8 |  | Inprogress
Total | Actual: | 55 |  |  |  | Plan: | 6
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
32 | Monday | Architecture and Desgin | Design prototype, sequence, use case description View compare business results "Rooms" app, Design prototype, sequence, use case description Import file website | 2020-05-17 | 8 |  | Inprogress
32 | Tuesday | Architecture and Desgin | Design prototype, sequence, use case description View compare business results "Rooms" app, Design prototype, sequence, use case description Import file website | 2020-05-18 | 8 |  | Inprogress
32 | Wednesday | Meeting Mentor | Design prototype, sequence, use case description Search compare business results "Rooms" app | 2020-05-19 | 6 | 6 | Inprogress
32 | Thursday | Architecture and Desgin | Design prototype, sequence, use case description Search compare business results "Rooms" app | 2020-05-20 | 10 |  | Inprogress
32 | Friday | Architecture and Desgin | Design prototype, sequence, use case description Search compare business results "Rooms" app | 2020-05-21 | 7 |  | Inprogress
32 | Saturday | Architecture and Desgin | Design prototype, sequence, use case description View statistic - report website | 2020-05-22 | 10 |  | Inprogress
32 | Sunday | Architecture and Desgin | Design prototype, sequence, use case description View statistic - report website | 2020-05-23 | 5 |  | Inprogress
Total | Actual: | 54 |  |  |  | Plan: | 6

## Vương Trương
Timelog:
Work in period
Week | Day | Task | Name Task |  | Actual | Plan | Status
1 | Monday | Meeting Mentor |  | 14/10/2019 | 4 | 4 | Done
1 | Tuesday | Research | research webgis | 15/10/2019 | 5 | 5 | Inprogress
1 | Wednesday | Research | research webgis | 16/10/2019 | 4.5 | 4.5 | Inprogress
1 | Thursday | Research | find another app like webgis | 17/10/2019 | 5 | 5 | Done
1 | Friday | Meetting Customer |  | 18/10/2019 | 4 | 4 | Done
1 | Saturday | Research | Project | 19/10/2019 | 4 | 5 | Inprogress
Total | Actual: | 26.5 |  |  |  | Plan: | 27.5
Week | Day | Task | Name Task |  | Actual | Plan | Status
2 | Monday | Research | Research model | 21/10/2019 | 5.5 | 6 | Done
2 | Tuesday | Research | Install qgis | 22/10/2019 | 5 | 6 | Done
2 | Wednesday | Meeting Mentor |  | 23/10/2019 | 4 | 4 | Done
2 | Thursday | Project Management | research webgis | 24/10/2019 | 5 | 6 | Done
2 | Friday | Research | Readding Customer Documments | 25/10/2019 | 6 | 6 | Done
2 | Saturday | Research | Presentation Customer Documments | 26/10/2019 | 4 | 6 | Done
Total | Actual: | 29.5 |  |  |  | Plan: | 34
Week | Day | Task | Name Task |  | Actual | Plan | Status
3 | Monday | Plan | Architecter plan document | 28/10/2019 | 5 | 6 | Done
3 | Tuesday | Meeting Mentor |  | 29/10/2019 | 4 | 4 | Done
3 | Wednesday | Meetting Customer |  | 30/10/2019 | 4.5 | 5 | Done
3 | Thursday | Research | research react | 31/10/2019 | 5 | 5 | Done
3 | Friday | Research | Architecture process document | 2019-01-11 | 6 | 6 | Done
3 | Saturday | Project Management | Document quality management plan. | 2019-02-11 | 6.5 | 6 | Done
Total | Actual: | 31 |  |  |  | Plan: | 32
Week | Day | Task | Name Task |  | Actual | Plan | Status
4 | Monday | Meeting team |  | 2019-11-04 | 5.5 | 6 | Done
4 | Tuesday | Requirement | UC description | 2019-11-05 | 4 | 4 | Inprogress
4 | Wednesday | Meetting mentor |  | 2019-11-06 | 4 | 4 | Done
4 | Thursday | Meeting team | research react | 2019-11-07 | 5 | 5 | Done
4 | Friday | Meetting Customer |  | 2019-11-08 | 5 | 5 | Done
4 | Saturday | Requirement | UC description | 2019-11-09 | 6 | 6 | Done
Total | Actual: | 29.5 |  |  |  | Plan: | 30
Week | Day | Task | Name Task |  | Actual | Plan | Status
5 | Monday | Meeting team |  | 2019-11-11 | 5 | 5 | Done
5 | Tuesday | Meeting Mentor |  | 2019-11-12 | 4 | 4 | Done
5 | Wednesday | Requirement | Data design | 2019-11-13 | 4.5 | 5 | Done
5 | Thursday | Meeting team | research react | 2019-11-14 | 5.5 | 6 | Done
5 | Friday | Requirement | Data distionary | 2019-11-15 | 6 | 6 | Inprogress
5 | Saturday | Requirement | Data distionary | 2019-11-16 | 5.5 | 6 | Done
Total | Actual: | 30.5 |  |  |  | Plan: | 32
Week | Day | Task | Name Task |  | Actual | Plan | Status
6 | Monday | Meeting team |  | 2019-11-18 | 5.5 | 6 | Done
6 | Tuesday | Meetting Customer |  | 2019-11-19 | 4 | 4 | Done
6 | Wednesday | Architect | Architecture driver document | 2019-11-20 | 4.5 | 5 | Inprogress
6 | Thursday | Meeting team |  | 2019-11-21 | 5.5 | 6 | Done
6 | Friday | Architect | Architecture driver document | 2019-11-22 | 6 | 5 | Inprogress
6 | Saturday | Architect | Architecture driver document | 2019-11-23 | 5.5 | 5 | Done
Total | Actual: | 31 |  |  |  | Plan: | 31
Week | Day | Task | Name Task |  | Actual | Plan | Status
7 | Monday | Meeting team |  | 2019-11-25 | 5.5 | 6 | Done
7 | Tuesday | Meeting Mentor |  | 2019-11-26 | 4 | 4 | Done
7 | Wednesday | Architect | Architecture design document | 2019-11-27 | 4.5 | 5 | Done
7 | Thursday | Meeting team | research react | 2019-11-28 | 5.5 | 6 | Done
7 | Friday | Architect | Architecture design document | 2019-11-29 | 6 | 5 | Done
7 | Saturday | Architect | Architecture design document | 2019-11-30 | 5.5 | 5 | Done
Total | Actual: | 31 |  |  |  | Plan: | 31
Week | Day | Task | Name Task |  | Actual | Plan | Status
8 | Monday | Meeting team |  | 2019-12-02 | 5.5 | 6 | Done
8 | Tuesday | Meeting Mentor |  | 2019-12-03 | 4 | 4 | Done
8 | Wednesday | Detail design | UC description detail module 1 | 2019-12-04 | 6 | 6 | Done
8 | Thursday | Training | Install react native invironment | 2019-12-05 | 5 | 5 | Done
8 | Friday | Training | Install react native invironment | 2019-12-06 | 6 | 6 | Done
8 | Saturday | Training | Research JS | 2019-12-07 | 5.5 | 5 | Inprogress
Total | Actual: | 32 |  |  |  | Plan: | 32
Week | Day | Task | Name Task |  | Actual | Plan | Status
9 | Monday | Meeting team |  | 2019-12-09 | 5.5 | 6 | Done
9 | Tuesday | Training | Research JS, design architect | 2019-12-10 | 5.5 | 6 | Inprogress
9 | Wednesday | Training | Research JS, design architect | 2019-12-11 | 4.5 | 5 | Inprogress
9 | Thursday | Meeting team |  | 2019-12-12 | 5 | 5 | Done
9 | Friday | Meeting Mentor | Research JS | 2019-12-13 | 4 | 4 | Done
9 | Saturday | Meeting team | Review | 2019-12-14 | 5.5 | 5 | Done
Total | Actual: | 30 |  |  |  | Plan: | 31
Week | Day | Task | Name Task |  | Actual | Plan | Status
10 | Monday | Meeting team |  | 2019-12-16 | 5 | 5 | Done
10 | Tuesday | Training | Research firebase | 2019-12-17 | 5.5 | 6 | Inprogress
10 | Wednesday | Training | Research firebase | 2019-12-18 | 5.5 | 6 | Done
10 | Thursday | Meeting Mentor |  | 2019-12-19 | 4 | 4 | Done
10 | Friday | Training | Connect firebase with project | 2019-12-20 | 6 | 6 | Done
10 | Saturday | Meeting team | Review | 2019-12-21 | 6 | 6 | Done
Total | Actual: | 32 |  |  |  | Plan: | 33
Week | Day | Task | Name Task |  | Actual | Plan | Status
11 | Monday | Implementation | login and save on database | 2019-12-23 | 5 | 5 | Inprogress
11 | Tuesday | Implementation | login and save on database | 2019-12-24 | 5.5 | 6 | Inprogress
11 | Wednesday | Implementation | Research firebase | 2019-12-25 | 8 | 6 | Inprogress
11 | Thursday | Implementation | login and save on database | 2019-12-26 | 4 | 4 | Inprogress
11 | Friday | Implementation | Connect firebase with project | 2019-12-27 | 6 | 6 | Inprogress
11 | Saturday | Meeting team | Review documents | 2019-12-28 | 7.5 | 6 | Inprogress
Total | Actual: | 36 |  |  |  | Plan: | 33
Week | Day | Task | Name Task |  | Actual | Plan | Status
12 | Monday | Implementation | login and save on database module 1 | 2019-12-30 | 5 | 5 | Inprogress
12 | Tuesday | Implementation | login and save on database | 2019-12-31 | 5.5 | 6 | Inprogress
12 | Wednesday | Implementation | login and save on database module 1 | 2020-01-01 | 8 | 6 | Done
12 | Thursday | Implementation | Connect firebase with project | 2020-01-02 | 7 | 4 | Inprogress
12 | Friday | Implementation | Connect firebase with project | 2020-01-03 | 6 | 6 | Inprogress
12 | Saturday | Meeting mentor | Review documents | 2020-01-04 | 4 | 4 | Inprogress
Total | Actual: | 35.5 |  |  |  | Plan: | 31
Week | Day | Task | Name Task |  | Actual | Plan | Status
19 | Monday | Implementation | Funtion forgot password | 2020-02-17 | 5.5 | 5 | Inprogress
19 | Tuesday | Implementation | Funtion forgot password | 2020-02-18 | 5.5 | 6 | Inprogress
19 | Wednesday | Implementation | Funtion forgot password | 2020-02-19 | 6 | 6 | Inprogress
19 | Thursday | Implementation | Funtion forgot password | 2020-02-20 | 5 | 4 | Done
19 | Friday | Implementation | Funtion information staff | 2020-02-21 | 6 | 6 | Inprogress
19 | Saturday | Meeting mentor |  | 2020-02-22 | 4 | 4 | Done
Total | Actual: | 32 |  |  |  | Plan: | 31
Week | Day | Task | Name Task |  | Actual | Plan | Status
20 | Monday | Implementation | Funtion information staff | 2020-02-24 | 6 | 6 | Inprogress
20 | Tuesday | Implementation | Funtion information staff | 2020-02-25 | 6 | 6 | Inprogress
20 | Wednesday | Implementation | Funtion information staff | 2020-02-26 | 5 | 6 | Inprogress
20 | Thursday | Implementation | Funtion information staff | 2020-02-27 | 5 | 6 | Done
20 | Friday | Meeting Mentor |  | 2020-02-28 | 4 | 6 | Done
20 | Saturday | Implementation | Install api gg map | 2020-02-29 | 4.5 | 6 | Done
Total | Actual: | 30.5 |  |  |  | Plan: | 36
Week | Day | Task | Name Task |  | Actual | Plan | Status
21 | Monday | Meeting team | review | 2020-03-02 | 6 | 6 | Inprogress
21 | Tuesday | Implementation | Funtion mapview | 2020-03-03 | 5 | 6 | Inprogress
21 | Wednesday | Implementation | Funtion mapview | 2020-03-04 | 7 | 6 | Inprogress
21 | Thursday | Meeting Mentor |  | 2020-03-05 | 4 | 4 | Inprogress
21 | Friday | Implementation | Funtion mapview | 2020-03-06 | 6 | 6 | Done
21 | Saturday | Implementation | Install storage config | 2020-03-07 | 3.5 | 6 | Done
Total | Actual: | 31.5 |  |  |  | Plan: | 34
Week | Day | Task | Name Task |  | Actual | Plan | Status
22 | Monday | Implementation | Searching how to get location | 2020-03-09 | 6 | 6 | Inprogress
22 | Tuesday | Implementation | Searching how to get location | 2020-03-10 | 6 | 6 | Inprogress
22 | Wednesday | Meeting Mentor |  | 2020-03-11 | 4 | 4 | Inprogress
22 | Thursday | Implementation | upload image for all funtion information of project | 2020-03-12 | 5 | 5 | Inprogress
22 | Friday | Implementation | upload image for all funtion information of project | 2020-03-13 | 4.5 | 6 | Inprogress
22 | Saturday | Implementation | upload image for all funtion information of project | 2020-03-14 | 5.5 | 6 | Inprogress
Total | Actual: | 31 |  |  |  | Plan: | 33
Week | Day | Task | Name Task |  | Actual | Plan | Status
23 | Monday | Implementation | Searching how to get location | 2020-03-16 | 6 | 6 | Inprogress
23 | Tuesday | Implementation | Searching how to get location | 2020-03-17 | 6 | 6 | Inprogress
23 | Wednesday | Meeting Mentor |  | 2020-03-18 | 4 | 4 | Done
23 | Thursday | Implementation | move data & change Implementation get data from realtime to firestore firebase | 2020-03-19 | 5 | 5 | Inprogress
23 | Friday | Implementation | move data & change Implementation get data from realtime to firestore firebase | 2020-03-20 | 7 | 6 | Inprogress
23 | Saturday | Implementation | move data & change Implementation get data from realtime to firestore firebase | 2020-03-21 | 5.5 | 6 | Done
Total | Actual: | 33.5 |  |  |  | Plan: | 33
Week | Day | Task | Name Task |  | Actual | Plan | Status
24 | Monday | Implementation | get information lat,long from database and show map | 2020-03-23 | 6 | 6 | Inprogress
24 | Tuesday | Implementation | get information lat,long from database and show map | 2020-03-24 | 5.5 | 6 | Inprogress
24 | Wednesday | Meeting Mentor |  | 2020-03-25 | 4 | 4 | Done
24 | Thursday | Implementation | get information lat,long from database and show map | 2020-03-26 | 5 | 5 | Inprogress
24 | Friday | Implementation | get information lat,long from database and show map | 2020-03-27 | 6.5 | 6 | Inprogress
24 | Saturday | Implementation | pick location in map(marker) with description and title | 2020-03-28 | 5 | 6 | Inprogress
Total | Actual: | 32 |  |  |  | Plan: | 33
Week | Day | Task | Name Task |  | Actual | Plan | Status
25 | Monday | Implementation | pick location in map(marker) with description and title | 2020-03-30 | 6 | 6 | Inprogress
25 | Tuesday | Implementation | pick location in map(marker) with description and title | 2020-03-31 | 7 | 6 | Done
25 | Wednesday | Meeting Mentor |  | 2020-04-01 | 4 | 4 | Done
25 | Thursday | Implementation | get data project from database to project funtion | 2020-04-02 | 6.5 | 5 | Inprogress
25 | Friday | Implementation | get data project from database to project funtion | 2020-04-03 | 5.5 | 6 | Inprogress
25 | Saturday | Implementation | get data project from database to project funtion | 2020-04-04 | 6 | 6 | Done
Total | Actual: | 29 |  |  |  | Plan: | 33
Week | Day | Task | Name Task |  | Actual | Plan | Status
26 | Monday | Implementation | View message happy birthday | 2020-04-06 | 8.5 | 8 | Inprogress
26 | Tuesday | Implementation | View message happy birthday | 2020-04-07 | 9 | 8 | Inprogress
26 | Wednesday | Meeting Mentor |  | 2020-04-08 | 4 | 4 | Inprogress
26 | Thursday | Implementation | View message happy birthday | 2020-04-09 | 7.5 | 8 | Inprogress
26 | Friday | Implementation | View message happy birthday | 2020-04-10 | 7 | 8 | Inprogress
26 | Saturday | Implementation | View message happy birthday | 2020-04-11 | 8.5 | 8 | Inprogress
Total | Actual: | 44.5 |  |  |  | Plan: | 44
Week | Day | Task | Name Task |  | Actual | Plan | Status
27 | Monday | Implementation | View message happy birthday | 2020-04-13 | 7 | 8 | Done
27 | Tuesday | Searching | Music for android | 2020-04-14 | 8 | 8 | Inprogress
27 | Wednesday | Meeting Mentor |  | 2020-04-15 | 6 | 4 | Inprogress
27 | Thursday | Searching | Music for android | 2020-04-16 | 8 | 8 | Inprogress
27 | Friday | Implementation | Code music happy birthday with message android | 2020-04-17 | 8 | 8 | Inprogress
27 | Saturday | Implementation | Code music happy birthday with message android | 2020-04-18 | 8 | 8 | Inprogress
Total | Actual: | 45 |  |  |  | Plan: | 44
Week | Day | Task | Name Task |  | Actual | Plan | Status
28 | Monday | Implementation | Show time of week result business of pesonal | 2020-04-20 | 8 | 8 | Inprogress
28 | Tuesday | Implementation | View table result business week pesonal | 2020-04-21 | 8 | 8 | Inprogress
28 | Wednesday | Meeting Mentor |  | 2020-04-22 | 6 | 4 | Inprogress
28 | Thursday | Implementation | View data result business week pesonal | 2020-04-23 | 8 | 8 | Inprogress
28 | Friday | Implementation | View data result business week pesonal | 2020-04-24 | 7 | 8 | Inprogress
28 | Saturday | Implementation | View data result business week pesonal | 2020-04-25 | 8 | 8 | Inprogress
Total | Actual: | 45 |  |  |  | Plan: | 44
Week | Day | Task | Name Task |  | Actual | Plan | Status
29 | Monday | Implementation | Show time of week result business of team | 2020-04-27 | 10 | 8 | Inprogress
29 | Tuesday | Implementation | Show time of week result business of team | 2020-04-28 | 9 | 8 | Done
29 | Wednesday | Meeting Mentor |  | 2020-04-29 | 6 | 4 | Done
29 | Thursday |  |  | 2020-04-30 | 0 | 0
29 | Friday |  |  | 2020-05-01 | 0 | 0
29 | Saturday | Implementation | View data result business week team | 2020-05-02 | 8 | 8 | Inprogress
Total | Actual: | 33 |  |  |  | Plan: | 28
Week | Day | Task | Name Task |  | Actual | Plan | Status
30 | Monday | Implementation | View map mode sattelite | 2020-05-04 | 9.5 | 8 | Inprogress
30 | Tuesday | Implementation | View map mode sattelite | 2020-05-05 | 7 | 8 | Done
30 | Wednesday | Meeting Mentor |  | 2020-05-06 | 4 | 4 | Done
30 | Thursday | Implementation | View map mode sattelite | 2020-05-07 | 8.5 | 8 | Inprogress
30 | Friday | Implementation | View map mode sattelite | 2020-05-08 | 8 | 8 | Done
30 | Saturday | Implementation | Swich mode standart and sattelite | 2020-05-09 | 7.5 | 8 | Done
Total | Actual: | 44.5 |  |  |  | Plan: | 44
Week | Day | Task | Name Task |  | Actual | Plan | Status
31 | Monday | Implementation | View table result business sales personal | 2020-05-11 | 7.5 | 8 | Done
31 | Tuesday | Implementation | View table result business sales personal | 2020-05-12 | 8 | 8 | Done
31 | Wednesday | Meeting Mentor |  | 2020-05-13 | 4 | 4 | Done
31 | Thursday | Implementation | View table result business sales personal | 2020-05-14 | 9 | 8 | Inprogress
31 | Friday | Implementation | View table result business sales personal | 2020-05-15 | 10.5 | 8 | Inprogress
31 | Saturday | Implementation | View table result business sales personal | 2020-05-16 | 8 | 8 | Done
Total | Actual: | 47 |  |  |  | Plan: | 44
Week | Day | Task | Name Task |  | Actual | Plan | Status
32 | Monday | Implementation | View table result business sales team | 2020-05-18 | 10 | 8 | Inprogress
32 | Tuesday | Implementation | View table result business sales team | 2020-05-19 | 9 | 8 | Done
32 | Wednesday | Meeting Mentor |  | 2020-05-20 | 4 | 4 | Done
32 | Thursday | Implementation | View table result business sales team | 2020-05-21 | 8 | 8 | Inprogress
32 | Friday | Implementation | View table result business sales team | 2020-05-22 | 10 | 8 | Done
32 | Saturday | Meeting Customer |  | 2020-05-23 | 4 | 4 | Done
Total | Actual: | 45 |  |  |  | Plan: | 40
Week | Day | Task | Name Task |  | Actual | Plan | Status
33 | Monday | Implementation | View sale result chart group | 2020-05-25 | 8 | 8 | Inprogress
33 | Tuesday | Implementation | View sale result chart group | 2020-05-26 | 9 | 8 | Inprogress
33 | Wednesday | Meeting Mentor |  | 2020-05-27 | 4 | 4 | Done
33 | Thursday | Implementation | View sale result chart group | 2020-05-28 | 9.5 | 8 | Inprogress
33 | Friday | Implementation | View sale result chart group | 2020-05-29 | 8.5 | 8 | Inprogress
33 | Saturday | Implementation | View sale result chart group | 2020-05-30 | 9 | 8 | Done
Total | Actual: | 48 |  |  |  | Plan: | 44
Week | Day | Task | Name Task |  | Actual | Plan | Status
34 | Monday | Implementation | View compare chart group | 2020-06-01 | 7.5 | 8 | Inprogress
34 | Tuesday | Implementation | View compare chart group | 2020-06-02 | 9 | 8 | Inprogress
34 | Wednesday | Meeting Mentor |  | 2020-06-03 | 4 | 4 | Done
34 | Thursday | Implementation | View compare chart group | 2020-06-04 | 8.5 | 8 | Inprogress
34 | Friday | Implementation | View compare chart group | 2020-06-05 | 8.5 | 8 | Inprogress
34 | Saturday | Implementation | View compare chart group | 2020-06-06 | 9.5 | 8 | Done
Total | Actual: | 47 |  |  |  | Plan: | 44
Week | Day | Task | Name Task |  | Actual | Plan | Status
35 | Monday | Review Code |  | 2020-06-08 | 8 | 8 | Inprogress
35 | Tuesday | Review Code |  | 2020-06-09 | 8 | 8 | Done
35 | Wednesday | Meeting Mentor |  | 2020-06-10 | 4 | 4 | Done
35 | Thursday | Meeting Customer |  | 2020-06-11 | 3 | 3 | Done
35 | Friday | Review Document |  | 2020-06-12 | 7 | 8 | Done
35 | Saturday | Meeting Mentor |  | 2020-06-13 | 4 | 4 | Done
Total | Actual: | 34 |  |  |  | Plan: | 35

## Anh Minh
Timelog: | Nguyễn Anh Minh
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status
1 | Monday | Meeting Mentor |  | 14/10/2019 | 4 | 4 | Done
1 | Tuesday | Research | Research WebGIS | 15/10/2019 | 5 | 5 | Inprogress
1 | Wednesday | Research | Research WebGIS | 16/10/2019 | 3 | 5 | Inprogress
1 | Thursday | Research | Research WebGIS | 17/10/2019 | 3 | 5 | Done
1 | Friday | Meetting Customer |  | 18/10/2019 | 4 | 4 | Done
1 | Saturday | Training |  | 19/10/2019 | 5 | 5 | Inprogress
Total | Actual: | 24 |  |  |  | Plan: | 28
Week | Day | Task | Name Task | Date | Actual | Plan | Status
2 | Monday | Research | Readding Incremental Model | 21/10/2019 | 5 | 5 | Done
2 | Tuesday | Research | Readding Geodatabase | 22/10/2019 | 3 | 5 | Done
2 | Wednesday | Meeting Mentor |  | 23/10/2019 | 4 | 4 | Done
2 | Thursday | Research | Setting and research QGIS | 24/10/2019 | 7 | 5 | Done
2 | Friday | Research | Readding Customer Documments | 25/10/2019 | 4 | 5 | Done
2 | Saturday | Research | Presentation Customer Documments | 26/10/2019 | 4 | 6 | Done
Total | Actual: | 27 |  |  |  | Plan: | 30
Week | Day | Task | Name Task | Date | Actual | Plan | Status
3 | Monday | Project Management | Create Risk Management Plan | 28/10/2019 | 6 | 6 | Done
3 | Tuesday | Meeting Mentor |  | 29/10/2019 | 4 | 4 | Done
3 | Wednesday | Meetting Customer |  | 30/10/2019 | 4 | 4 | Done
3 | Thursday | Project Management | Create Quality Management Plan | 31/10/2019 | 6 | 6 | Done
3 | Friday | Project Management | Update Risk Management Plan | 2019-01-11 | 5 | 5 | Done
3 | Saturday | Project Management | Update Quality Management Plan | 2019-02-11 | 5 | 5 | Done
Total | Actual: | 30 |  |  |  | Plan: | 30
Week | Day | Task | Name Task | Date | Actual | Plan | Status
4 | Monday | Project Management | Create Measurement Plan | 2019-11-04 | 5 | 5 | Done
4 | Tuesday | Project Management | Update Measurement Plan | 2019-11-05 | 4 | 5 | Done
4 | Wednesday | Meeting Mentor |  | 2019-11-06 | 4 | 4 | Done
4 | Thursday | Project Management | Usecase Decription, tranning plan | 2019-11-07 | 5 | 7 | Inprogress
4 | Friday | Meetting Customer |  | 2019-11-08 | 5 | 5 | Done
4 | Saturday | Project Management | Complete the meeting minutes ; Review document , test process | 2019-11-09 | 7 | 5 | Inprogress
Total | Actual: | 30 |  |  |  | Plan: | 31
Week | Day | Task | Name Task | Date | Actual | Plan | Status
5 | Monday | Project Management | Create Chage Management Plan | 2019-11-11 | 6 | 6 | Done
5 | Tuesday | Meeting Mentor |  | 2019-11-12 | 4 | 4 | Done
5 | Wednesday | Project Management | Update Chage Management Plan | 2019-11-13 | 5 | 5 | Done
5 | Thursday | Project Management | Usecase Decription | 2019-11-14 | 5 | 5 | Inprogress
5 | Friday | Project Management | Update Software Architecture Document | 2019-11-15 | 5 | 5 | Done
5 | Saturday | Project Management | Present EOMP1 Complete the meeting minutes Report document for customer | 2019-11-16 | 6 | 6 | Done
Total | Actual: | 31 |  |  |  | Plan: | 31
Week | Day | Task | Name Task | Date | Actual | Plan | Status
6 | Monday | Project Management | SRS document | 2019-11-18 | 6 | 6 | Done
6 | Tuesday | Meeting Mentor |  | 2019-11-19 | 4 | 4 | Done
6 | Wednesday | Project Management | SRS document | 2019-11-20 | 5 | 6 | Done
6 | Thursday | Project Management | SRS document | 2019-11-21 | 5 | 6 | Done
6 | Friday | Project Management | SRS document | 2019-11-22 | 5 | 6 | Done
6 | Saturday | Project Management | Complete the meeting minutes | 2019-11-23 | 6 | 6 | Done
Total | Actual: | 31 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
7 | Monday | Training | Install with React Native Development | 2019-11-25 | 6 | 6 | Done
7 | Tuesday | Meeting Mentor |  | 2019-11-26 | 4 | 4 | Done
7 | Wednesday | Training | Install the android virtual machine | 2019-11-27 | 5 | 6 | Done
7 | Thursday | Training | React Native application design process | 2019-11-28 | 6 | 6 | Done
7 | Friday | Training | Instructions to build applications on Android + iPhone devices, design architect | 2019-11-29 | 5 | 6 | Done
7 | Saturday | Project Management | Review document Complete the meeting minutes | 2019-11-30 | 6 | 6 | Done
Total | Actual: | 32 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
8 | Monday | Training | Install with React Native Development | 2019-12-02 | 5 | 6 | Done
8 | Tuesday | Meeting Mentor |  | 2019-12-03 | 4 | 4 | Done
8 | Wednesday | Training | Install the android virtual machine, risk management | 2019-12-04 | 5 | 6 | Done
8 | Thursday | Training | Component In React Native 1. Understand the sequence of a Component's operation 2. Text Component | 2019-12-05 | 5 | 6 | Done
8 | Friday | Training | Component In React Native (p1) 3. Image Component | 2019-12-06 | 5.5 | 6 | Done
8 | Saturday | Training | Component In React Native (p1) 4. View Component | 2019-12-07 | 5.5 | 6 | Done
8 | Actual: | 30 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
9 | Monday | Training | React Navigation | 2019-12-09 | 6 | 6 | Done
9 | Tuesday | Meeting Mentor |  | 2019-12-10 | 4 | 4 | Done
9 | Wednesday | Training | Component nested Component | 2019-12-11 | 6 | 6 | Done
9 | Thursday | Training | Export Component Pass parameters to Component | 2019-12-12 | 4 | 6 | Done
9 | Friday | Training | Debug with JavaScript Debug with React Native | 2019-12-13 | 5.5 | 6 | Done
9 | Saturday | Training | Debug with Beyond Javascript | 2019-12-14 | 6 | 6 | Done
9 | Actual: | 31.5 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status
10 | Monday | Training | Publish Applications to AppStore | 2019-12-16 | 6 | 6 | Done
10 | Tuesday | Meeting Mentor |  | 2019-12-17 | 4 | 4 | Done
10 | Wednesday | Training | Publish Applications to Google Store | 2019-12-18 | 6 | 6 | Done
10 | Thursday | Training | Research WebGIS | 2019-12-19 | 4 | 4 | Done
10 | Friday | Training | Setting and research QGIS | 2019-12-20 | 5.5 | 5.5 | Done
10 | Saturday | Training | 1. Realtime Database 2. Authentication | 2019-12-21 | 6 | 6 | Done
10 | Actual: | 31.5 |  |  |  | Plan: | 31.5
Week | Day | Task | Name Task | Date | Actual | Plan | Status
11 | Monday | Code | Funciton "Đăng nhập/ Đăng xuất" front-end website | 2019-12-23 | 4 | 6 | Done
11 | Tuesday | Code | Funciton "Quản lý thông tin" front-end website | 2019-12-24 | 4 | 6 | Done
11 | Wednesday | Code | Funciton " Quản lý tài khoản" front-end website | 2019-12-25 | 5 | 6 | Done
11 | Thursday | Code | Funciton "Quản lý dự án bất động sản" front-end website | 2019-12-26 | 6 | 6 | Done
11 | Friday | Code | Funciton "Quản lý thống kê, báo cáo" front-end website | 2019-12-27 | 6 | 6 | Done
11 | Saturday | Code | Funciton "Quản lý công tác" front-end website | 2019-12-28 | 6 | 6 | Done
11 | Actual: | 31 |  |  |  | Plan: | 36
Week | Day | Task | Name Task | Date | Actual | Plan | Status
12 | Monday | Code | Funciton "Quản lý nghỉ việc" front-end website | 2019-12-30 | 6 | 6 | Inprogress
12 | Tuesday | Code | Funciton "List company policy" front-end website | 2019-12-31 | 7 | 6 | Inprogress
12 | Wednesday | Code | Funciton "List company policy" front-end website | 2020-01-01 | 5 | 6 | Inprogress
12 | Thursday | Implementation | Funciton "List account" front-end website | 2020-01-02 | 7 | 4 | Inprogress
12 | Friday | Implementation | Funciton "List account" front-end website | 2020-01-03 | 6 | 6 | Inprogress
12 | Saturday | Meeting mentor | Review documents | 2020-01-04 | 4 | 4 | Inprogress
12 | Sunday | Meeting team | Perpare documents, review | 2020-01-05 | 5 |  | Inprogress
12 | Actual: | 40 |  |  |  | Plan: | 32
Week | Day | Task | Name Task |  | Actual | Plan | Status
19 | Monday | Code | Code Front-end "Login, logout" website | 2020-02-17 | 5 | 6 | Inprogress
19 | Tuesday | Code | Code Front-end "Login, logout" website | 2020-02-18 | 5 | 6 | Inprogress
19 | Wednesday | Code | Code Back-end "Login, logout" website | 2020-02-19 | 5 | 6 | Inprogress
19 | Thursday | Code | Code Back-end "Login, logout" website | 2020-02-20 | 5 | 6 | Done
19 | Friday | Code | Code Back-end "Login, logout" website | 2020-02-21 | 5 | 6 | Inprogress
19 | Saturday | Meeting mentor |  | 2020-02-22 | 4 | 4 | Done
19 | Sunday | Meeting team | review | 2020-02-23 | 5 |  | Done
Total | Actual: | 34 |  |  |  | Plan: | 34
Week | Day | Task | Name Task |  | Actual | Plan | Status
20 | Monday | Code | Code Front-end "View account information" website | 2020-02-24 | 5 | 6 | Inprogress
20 | Tuesday | Code | Code Front-end "View account information" website | 2020-02-25 | 5 | 6 | Inprogress
20 | Wednesday | Code | Code Back-end "View account information" website | 2020-02-26 | 5 | 6 | Inprogress
20 | Thursday | Code | Code Back-end "View account information" website | 2020-02-27 | 5 | 6 | Done
20 | Friday | Meeting Mentor |  | 2020-02-28 | 4 | 6 | Done
20 | Saturday | Code | Code Back-end "View account information" website | 2020-02-29 | 3 | 6 | Done
20 | Sunday | Meeting team | review | 2020-03-01 | 4 |  | Done
Total | Actual: | 31 |  |  |  | Plan: | 36
Week | Day | Task | Name Task |  | Actual | Plan | Status
21 | Monday | Meeting team | Review | 2020-03-02 | 6 | 6 | Inprogress
21 | Tuesday | Code | Code Front-end "Add account" website | 2020-03-03 | 5 | 6 | Inprogress
21 | Wednesday | Code | Code Front-end "Edit account" website | 2020-03-04 | 5 | 6 | Inprogress
21 | Thursday | Meeting Mentor |  | 2020-03-05 | 4 | 4 | Inprogress
21 | Friday | Code | Code Back-end "Add account" website | 2020-03-06 | 6 | 6 | Done
21 | Saturday | Code | Code Back-end "Edit account" website | 2020-03-07 | 5 | 6 | Done
Total | Actual: | 31 |  |  |  | Plan: | 34
Week | Day | Task | Name Task |  | Actual | Plan | Status
22 | Monday | Code | Code Front-end "Add project" website | 2020-03-09 | 6 | 6 | Inprogress
22 | Tuesday | Code | Code Front-end "Add project" website | 2020-03-10 | 6 | 6 | Inprogress
22 | Wednesday | Meeting Mentor |  | 2020-03-11 | 4 | 4 | Inprogress
22 | Thursday | Code | Code Front-end "Add project" website | 2020-03-12 | 5 | 5 | Inprogress
22 | Friday | Code | Code Front-end "Edit project" website | 2020-03-13 | 7 | 6 | Inprogress
22 | Saturday | Code | Code Front-end "Edit project" website | 2020-03-14 | 5 | 6 | Done
Total | Actual: | 33 |  |  |  | Plan: | 33
Week | Day | Task | Name Task |  | Actual | Plan | Status
23 | Monday | Code | Code Front-end "View all project listings" website | 2020-03-16 | 6 | 6 | Inprogress
23 | Tuesday | Code | Code Front-end "View all project listings" website | 2020-03-17 | 7 | 6 | Done
23 | Wednesday | Meeting Mentor |  | 2020-03-18 | 4 | 4 | Done
23 | Thursday | Code | Code Back-end "Add project" website | 2020-03-19 | 7 | 5 | Inprogress
23 | Friday | Code | Code Back-end "Add project" website | 2020-03-20 | 7 | 6 | Inprogress
23 | Saturday | Code | Code Back-end "Add project" website | 2020-03-21 | 6 | 6 | Done
Total | Actual: | 37 |  |  |  | Plan: | 33
Week | Day | Task | Name Task |  | Actual | Plan | Status
24 | Monday | Code | Code Back-end "Add project" website | 2020-03-23 | 6 | 6 | Inprogress
24 | Tuesday | Code | Code Back-end "Add project" website | 2020-03-24 | 6 | 6 | Done
24 | Wednesday | Meeting Mentor |  | 2020-03-25 | 4 | 4 | Done
24 | Thursday | Code | Code Back-end "Add project (funciton add image)" website | 2020-03-26 | 5 | 5 | Inprogress
24 | Friday | Code | Code Back-end "Edit projects" website | 2020-03-27 | 7 | 6 | Inprogress
24 | Saturday | Code | Code Back-end "Edit projects" website | 2020-03-28 | 7 | 6 | Done
Total | Actual: | 35 |  |  |  | Plan: | 33
Week | Day | Task | Name Task |  | Actual | Plan | Status
25 | Monday | Code | Code Back-end "View account information" website | 2020-03-30 | 6 | 6 | Inprogress
25 | Tuesday | Code | Code Back-end "View account information" website | 2020-03-31 | 6 | 6 | Done
25 | Wednesday | Meeting Mentor |  | 2020-04-01 | 4 | 4 | Done
25 | Thursday | Code | Code Front-end "Add Room" | 2020-04-02 | 6 | 5 | Inprogress
25 | Friday | Code | Code Front-end "Add Room" | 2020-04-03 | 7 | 6 | Inprogress
25 | Saturday | Code | Code Front-end "Add Room" | 2020-04-04 | 6 | 6 | Inprogress
Total | Actual: | 35 |  |  |  | Plan: | 33
Week | Day | Task | Name Task |  | Actual | Plan | Status
26 | Monday | Code | Code Front-end "Edit Room" | 2020-04-06 | 4 | 6 | Inprogress
26 | Tuesday | Code | Code Front-end "Edit Room" | 2020-04-07 | 3 | 6 | Done
26 | Wednesday | Meeting Mentor |  | 2020-04-08 | 4 | 4 | Done
26 | Thursday | Code | Code Front-end "View Room" | 2020-04-09 | 7 | 5 | Inprogress
26 | Friday | Code | Code Front-end "View Room" | 2020-04-10 | 7 | 6 | Inprogress
26 | Saturday | Code | Code Front-end "View Room" | 2020-04-11 | 7 | 6 | Inprogress
Total | Actual: | 32 |  |  |  | Plan: | 33
Week | Day | Task | Name Task | Date | Actual | Plan | Status
27 | Monday | Code | Code Front-end "View Room" | 2020-04-13 | 7 | 6 | Inprogress
27 | Tuesday | Code | Code Front-end "View Room" | 2020-04-14 | 8 | 6 | Inprogress
27 | Wednesday | Meeting Mentor |  | 2020-04-15 | 4 | 4 | Inprogress
27 | Thursday | Code | Code Front-end "Edit Room" | 2020-04-16 | 5 | 5 | Inprogress
27 | Friday | Code | Code Front-end "Edit Room" | 2020-04-17 | 5 | 6 | Inprogress
27 | Saturday | Code | Code Front-end "Edit Room" | 2020-04-18 | 8 | 6 | Inprogress
Total | Actual: | 37 |  |  |  | Plan: | 33
Week | Day | Task | Name Task | Date | Actual | Plan | Status
28 | Monday | Code | Code Front-end "View Team" | 2020-04-20 | 6 | 6 | Inprogress
28 | Tuesday | Code | Code Front-end "View Team" | 2020-04-21 | 6 | 6 | Inprogress
28 | Wednesday | Meeting Mentor |  | 2020-04-22 | 4 | 4 | Inprogress
28 | Thursday | Code | Code Back-end "Add Room" | 2020-04-23 | 6 | 5 | Inprogress
28 | Friday | Code | Code Back-end "Add Room" | 2020-04-24 | 6 | 6 | Inprogress
28 | Saturday | Code | Code Back-end "Add Room" | 2020-04-25 | 8 | 6 | Inprogress
Total | Actual: | 36 |  |  |  | Plan: | 33
Week | Day | Task | Name Task | Date | Actual | Plan | Status
29 | Monday | Code | Code Back-end "Edit Room" | 2020-04-27 | 6 | 6 | Inprogress
29 | Tuesday | Code | Code Back-end "Edit Room" | 2020-04-28 | 6 | 6 | Inprogress
29 | Wednesday | Meeting Mentor |  | 2020-04-29 | 4 | 4 | Inprogress
29 | Thursday | Code | Code Back-end "Edit Room" | 2020-04-30 | 4 | 5 | Inprogress
29 | Friday | Code | Code Back-end "View Room" | 2020-05-01 | 8 | 6 | Inprogress
29 | Saturday | Code | Code Back-end "View Room" | 2020-05-02 | 7 | 6 | Inprogress
Total | Actual: | 35 |  |  |  | Plan: | 33
Week | Day | Task | Name Task | Date | Actual | Plan | Status
30 | Monday | Code | Code Back-end "Add Team" | 2020-05-04 | 5 | 6 | Inprogress
30 | Tuesday | Code | Code Back-end "Add Team" | 2020-05-05 | 5 | 6 | Inprogress
30 | Wednesday | Meeting Mentor |  | 2020-05-06 | 4 | 4 | Inprogress
30 | Thursday | Code | Code Back-end "Add Team" | 2020-05-07 | 8 | 5 | Inprogress
30 | Friday | Code | Code Front-end "Import" | 2020-05-08 | 7 | 6 | Inprogress
30 | Saturday | Code | Code Front-end "Import" | 2020-05-09 | 4 | 6 | Inprogress
Total | Actual: | 33 |  |  |  | Plan: | 33
Week | Day | Task | Name Task | Date | Actual | Plan | Status
31 | Monday | Code | Code Front-end "Import" | 2020-05-11 | 8 | 6 | Inprogress
31 | Tuesday | Code | Code Back-end "Import Sales User" | 2020-05-12 | 8 | 6 | Inprogress
31 | Wednesday | Meeting Mentor |  | 2020-05-13 | 4 | 4 | Inprogress
31 | Thursday | Code | Code Back-end "Import Sales User" | 2020-05-14 | 8 | 5 | Inprogress
31 | Friday | Code | Code Back-end "Import Sales User" | 2020-05-15 | 8 | 6 | Inprogress
31 | Saturday | Code | Code Back-end "Import Sales User" | 2020-05-16 | 5 | 6 | Inprogress
Total | Actual: | 41 |  |  |  | Plan: | 33
Week | Day | Task | Name Task | Date | Actual | Plan | Status
32 | Monday | Code | Code Back-end "Import Sales User" | 2020-05-18 | 8 | 6 | Inprogress
32 | Tuesday | Code | Code Back-end "Import Sales User" | 2020-05-19 | 8 | 6 | Inprogress
32 | Wednesday | Meeting Mentor |  | 2020-05-20 | 4 | 4 | Inprogress
32 | Thursday | Code | Code Back-end "Import Sales User" | 2020-05-21 | 8 | 5 | Inprogress
32 | Friday | Code | Code Back-end "Import Sales User" | 2020-05-22 | 8 | 6 | Inprogress
32 | Saturday | Code | Code Back-end "Import Sales User" | 2020-05-23 | 8 | 6 | Inprogress
Total | Actual: | 44 |  |  |  | Plan: | 33
Week | Day | Task | Name Task | Date | Actual | Plan | Status
33 | Monday | Code | Code Back-end "Import Sales Room" | 2020-05-25 | 8 | 6 | Inprogress
33 | Tuesday | Code | Code Back-end "Import Sales Room" | 2020-05-26 | 8 | 6 | Inprogress
33 | Wednesday | Meeting Mentor |  | 2020-05-27 | 4 | 4 | Inprogress
33 | Thursday | Code | Code Back-end "Export Sales User" | 2020-05-28 | 8 | 5 | Inprogress
33 | Friday | Code | Code Back-end "Export Sales User" | 2020-05-29 | 8 | 6 | Inprogress
33 | Saturday | Code | Code Back-end "Export Sales User" | 2020-05-30 | 8 | 6 | Inprogress
Total | Actual: | 44 |  |  |  | Plan: | 33
Week | Day | Task | Name Task | Date | Actual | Plan | Status
34 | Monday | Code | Code Back-end "Export Sales Team" | 2020-06-01 | 8 | 6 | Inprogress
34 | Tuesday | Code | Code Back-end "Export Sales Team" | 2020-06-02 | 8 | 6 | Inprogress
34 | Wednesday | Meeting Mentor |  | 2020-06-03 | 4 | 4 | Inprogress
34 | Thursday | Code | Code Back-end "Export Sales Room" | 2020-06-04 | 8 | 5 | Inprogress
34 | Friday | Code | Code Back-end "Export Sales Room" | 2020-06-05 | 8 | 6 | Inprogress
34 | Saturday | Code | Code Back-end "Export Sales Room" | 2020-06-06 | 8 | 6 | Inprogress
Total | Actual: | 44 |  |  |  | Plan: | 33
Week | Day | Task | Name Task | Date | Actual | Plan | Status
35 | Monday | Review Code |  | 2020-06-08 | 8 | 6 | Inprogress
35 | Tuesday | Review Code |  | 2020-06-09 | 8 | 6 | Inprogress
35 | Wednesday | Meeting Mentor |  | 2020-06-10 | 4 | 4 | Inprogress
35 | Thursday | Meeting Customer |  | 2020-06-11 | 3 | 3 | Inprogress
35 | Friday | Review Document |  | 2020-06-12 | 8 | 6 | Inprogress
35 | Saturday | Meeting Mentor |  | 2020-06-13 | 4 | 4 | Inprogress
Total | Actual: | 35 |  |  |  | Plan: | 29

## Như Phương
Timelog: | Trịnh Như Phương
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
1 | Monday | Meeting Mentor |  | 14/10/2019 | 4 | 4 | Done
1 | Tuesday | Project Management | Research project | 15/10/2019 | 5 | 6 | Done
1 | Wednesday | Project Management | Research project | 16/10/2019 | 5 | 6 | Done
1 | Thursday | Project Management | Research project | 17/10/2019 | 5 | 5 | Done
1 | Friday | Meetting Customer |  | 18/10/2019 | 4 | 4 | Done
1 | Saturday | Project Management | Complete the meeting minutes | 19/10/2019 | 4 | 5 | Done | Meeting_Mentor_14/10/2019 Meeting-customer_18/10/2019
Total | Actual: | 27 |  |  |  | Plan: | 30
2 | Monday | Project Management | Userstory | 21/10/2019 | 5 | 4 | Done
2 | Tuesday | Project Management | research software process model | 22/10/2019 | 5 | 5 | Done
2 | Wednesday | Meeting Mentor |  | 23/10/2019 | 4 | 5 | Done
2 | Thursday | Project Management | Research GIS | 24/10/2019 | 5 | 5 | Done
2 | Friday | Project Management | Research GIS | 25/10/2019 | 5 | 5 | Done
2 | Saturday | Project Management | Complete the meeting minutes ; Present document GIS with team | 26/10/2019 | 5 | 6 | Done | Meeting_Mentor_23/10/2019
Total | Actual: | 29 |  |  |  | Plan: | 30
3 | Monday | Project Management | Research GIS , prepare question for customer Test plan,Re plan | 28/10/2019 | 5.5 | 6 | Inprogress
3 | Tuesday | Meeting Mentor |  | 29/10/2019 | 4 | 4 | Done
3 | Wednesday | Meetting Customer |  | 30/10/2019 | 4.5 | 5 | Done
3 | Thursday | Project Management | Test plan, RE process | 31/10/2019 | 5 | 6 | Done | TE_Testplan_ver1.0
3 | Friday | Project Management | Research React | 2019-01-11 | 4.5 | 6 | Done
3 | Saturday | Project Management | Complete the meeting minutes ; Requiment plan | 2019-02-11 | 6 | 6 | Inprogress | Meeting_Customer_29/10/2019 Meeting_Mentor _30/10/2019
Total | Actual: | 29.5 |  |  |  | Plan: | 33
4 | Monday | Project Management | Requiment plan | 2019-11-04 | 5.5 | 6 | Done | RE_RequimentPlan_ver1.0
4 | Tuesday | Project Management | Requiment process | 2019-11-05 | 5 | 6 | Done | RE_RequimentProcess_ver1.0
4 | Wednesday | Meeting Mentor |  | 2019-11-06 | 4.5 | 4 | Done
4 | Thursday | Project Management | Test Process | 2019-11-07 | 5 | 6 | Inprogress
4 | Friday | Meetting Customer |  | 2019-11-08 | 4.5 | 6 | Done
4 | Saturday | Project Management | Complete the meeting minutes ; Review document , test process | 2019-11-09 | 7 | 6 | Inprogress | TE_Testprocess_ver1.0
Total | Actual: | 31.5 |  |  |  | Plan: | 34
5 | Monday | Project Management | Complete the meeting minutes ; Review document Analyst Requirement | 2019-11-10 | 6 | 6 | Done | Meeting_customer 8/10/2019 Meeting_mentor 6/10/2019
5 | Tuesday | Meeting Mentor |  | 2019-11-11 | 4 | 4 | Done
5 | Wednesday | Project Management | ConOP document | 2019-11-12 | 5 | 6 | Inprogress
5 | Thursday | Project Management | Usecase Decription | 2019-11-13 | 5 | 6 | Inprogress
5 | Friday | Project Management | Prepare EOMP #1 Update document | 2019-11-14 | 4.5 | 6 | Done
5 | Saturday | Project Management | Present EOMP1 Complete the meeting minutes Report document for customer | 2019-11-15 | 6 | 6 | Done
Total | Actual: | 30.5 |  |  |  | Plan: | 34
6 | Monday | Project Management | Conop document | 2019-11-17 | 6 | 6 | Done
6 | Tuesday | Meeting Mentor |  | 2019-11-18 | 4 | 4 | Done
6 | Wednesday | Project Management | Conop document | 2019-11-19 | 5 | 6 | Inprogress
6 | Thursday | Project Management | Conop document | 2019-11-20 | 5 | 6 | Inprogress
6 | Friday | Project Management | Conop document, architect design | 2019-11-21 | 4.5 | 6 | Done
6 | Saturday | Project Management | Complete the meeting minutes | 2019-11-22 | 6 | 6 | Done
Total | Actual: | 30.5 |  |  |  | Plan: | 34
7 | Monday | Project Management | Complete RE document | 2019-11-24 | 6 | 6 | Done
7 | Tuesday | Meeting Mentor |  | 2019-11-25 | 4 | 4 | Done
7 | Wednesday | Project Management | Architure Driver | 2019-11-26 | 5 | 6 | Done
7 | Thursday | Project Management | Architure Driver | 2019-11-27 | 6.5 | 6 | Done
7 | Friday | Project Management | Update ConOP | 2019-11-28 | 5 | 6 | Done
7 | Saturday | Project Management | Review document Complete the meeting minutes, Install react native | 2019-11-29 | 6 | 6 | Done
Total | Actual: | 32.5 |  |  |  | Plan: | 34
8 | Monday | Project Management | Context Diagram | 2019-12-02 | 6 | 6 | Done
8 | Tuesday | Meeting Mentor |  | 2019-12-03 | 4 | 4 | Done
8 | Wednesday | Project Management | Architure Design | 2019-12-04 | 6 | 6 | Inprogress
8 | Thursday | Project Management | Usecase Decription | 2019-12-05 | 4 | 6 | Inprogress
8 | Friday | Project Management | ERD | 2019-12-06 | 5.5 | 6 | Done
8 | Saturday | Project Management | Complete the meeting minutes Review document | 2019-12-07 | 6 | 6 | Done
8
| Actual: | 31.5 |  |  |  | Plan: | 34
9 | Monday | Project Management | Install React Native | 2019-12-08 | 6 | 6 | Done
9 | Tuesday | Project Management | TEst Case | 2019-12-09 | 5 | 6 | Done
9 | Wednesday | Project Management | Detail Design | 2019-12-10 | 6 | 6 | Inprogress
9 | Thursday | Project Management | Test Case | 2019-12-11 | 6 | 6 | Done
9 | Friday | Meetting Customer |  | 2019-12-12 | 4 | 4 | Inprogress
9 | Saturday | Project Management | Complete the meeting minutes Review document | 2019-12-13 | 6 | 6 | Done
9
9 | Actual: | 33 |  |  |  | Plan: | 34
10 | Monday | Project Management | publish applications to AppStore | 2019-12-16 | 6 | 6 | Done
10 | Tuesday | Project Management | publish applications to GoogleStore | 2019-12-17 | 4 | 4 | Done
10 | Wednesday | Project Management | Research WebGIS | 2019-12-18 | 6 | 6 | Done
10 | Thursday | Meeting Mentor |  | 2019-12-19 | 4 | 6 | Done
10 | Friday | Project Management | Setting and research QGIS | 2019-12-20 | 5 | 6 | Done
10 | Saturday | Project Management | Complete the meeting minutes Review document | 2019-12-21 | 6 | 6 | Done
10
10 | Actual: | 31 |  |  |  | Plan: | 34
11 | Monday | Training | Research firebase | 2019-12-23 | 5 | 5 | Done
11 | Tuesday | Test | Test case module 1 | 2019-12-24 | 5.5 | 6 | Inprogress
11 | Wednesday | Test | Test case module 1 | 2019-12-25 | 5.5 | 6 | Done
11 | Thursday | Meeting Mentor |  | 2019-12-26 | 4 | 4 | Done
11 | Friday | Training | Connect firebase with project | 2019-12-27 | 6 | 6 | Done
11 | Saturday | Meeting team | Complete the meeting minutes Review document | 2019-12-28 | 6 | 6 | Done
11
Total | Actual: | 32 |  |  |  | Plan: | 33
12 | Monday | Testing |  | 2019-12-30 | 6 | 6 | Inprogress
12 | Tuesday | Testing | Test case module 1 | 2019-12-31 | 7 | 6 | Inprogress
12 | Wednesday | Testing | Test case module 1 | 2020-01-01 | 5 | 6 | Inprogress
12 | Thursday | Testing | Test case module 1 | 2020-01-02 | 7 | 4 | Inprogress
12 | Friday | Testing | Update meeting minutes | 2020-01-03 | 6 | 6 | Inprogress
12 | Saturday | Meeting mentor | Complete the meeting minutes Review document | 2020-01-04 | 4 | 4 | Inprogress
12 | Sunday | Meeting team | Perpare documents, review | 2020-01-05 | 5 |  | Inprogress
12 | Actual: | 40 |  |  |  | Plan: | 32
19 | Monday | Testing | Test "View company policy" app | 2020-02-17 | 4 | 6 | Inprogress
19 | Tuesday | Testing | Test "View company policy" app | 2020-02-18 | 4 | 6 | Inprogress
19 | Wednesday | Testing | Test "View company policy" app | 2020-02-19 | 6 | 6 | Inprogress
19 | Thursday | Testing | Test "View company policy" website | 2020-02-20 | 5 | 4 | Inprogress
19 | Friday | Testing | Test "View company policy" website | 2020-02-21 | 6 | 6 | Inprogress
19 | Saturday | Meeting mentor |  | 2020-02-22 | 4 | 4 | Inprogress
19 | Sunday | Meeting team | review | 2020-02-23 | 5 |  | Inprogress
19 | Actual: | 34 |  |  |  | Plan: | 32
20 | Monday | Testing | Test "View personnel" website | 2020-02-24 | 4 | 6 | Inprogress
20 | Tuesday | Testing | Test "View personnel" website | 2020-02-25 | 6 | 6 | Inprogress
20 | Wednesday | Testing | Test "View organizational chart" website | 2020-02-26 | 5 | 6 | Inprogress
20 | Thursday | Testing | Test "View organizational chart" website | 2020-02-27 | 5 | 4 | Inprogress
20 | Friday | Meeting Mentor |  | 2020-02-28 | 4 | 6 | Inprogress
20 | Saturday | Testing | Test "View organizational chart" website | 2020-02-29 | 6 | 4 | Inprogress
20 | Sunday | Meeting team | review | 2020-03-01 | 4 |  | Inprogress
20 | Actual: | 34 |  |  |  | Plan: | 32
21 | Monday | Testing | Test "View account information" website | 2020-03-02 | 6 | 6 | Inprogress
21 | Tuesday | Testing | Test "Add account" website | 2020-03-03 | 5 | 6 | Inprogress
21 | Wednesday | Testing | Test "Add account" website | 2020-03-04 | 7 | 6 | Inprogress
21 | Thursday | Meeting Mentor |  | 2020-03-05 | 4 | 4 | Inprogress
21 | Friday | Testing | Test "Edit account" website | 2020-03-06 | 6 | 6 | Inprogress
21 | Saturday | Testing | Test "Edit account" website | 2020-03-07 | 7 | 4 | Inprogress
21 | Sunday | Testing | review | 2020-03-08 | 4 |  | Inprogress
21 | Actual: | 39 |  |  |  | Plan: | 32
22 | Monday | Testing | Test "View all project listings" app | 2020-03-09 | 6 | 6 | Inprogress
22 | Tuesday | Testing | Test "View all project listings" app | 2020-03-10 | 7 | 6 | Inprogress
22 | Wednesday | Meeting Mentor |  | 2020-03-11 | 4 | 6 | Inprogress
22 | Thursday | Testing | Test "View all project listings being implemented" app | 2020-03-12 | 4 | 4 | Inprogress
22 | Friday | Testing | Test "View all project listings being implemented" app | 2020-03-13 | 6 | 6 | Inprogress
22 | Saturday | Testing | Test "View all project listings prepare to deploy" app | 2020-03-14 | 6 | 4 | Inprogress
22 | Sunday | Testing | Test "View all project listings prepare to deploy" app | 2020-03-15 | 2 |  | Inprogress
22 | Actual: | 35 |  |  |  | Plan: | 32
23 | Monday | Testing | Test "View all project listings has deployed" app | 2020-03-16 | 6 | 6 | Inprogress
23 | Tuesday | Testing | Test "View all project listings has deployed" app | 2020-03-17 | 7 | 6 | Inprogress
23 | Wednesday | Meeting Mentor |  | 2020-03-18 | 4 | 6 | Inprogress
23 | Thursday | Testing | Test "View all project listings" website | 2020-03-19 | 4 | 4 | Inprogress
23 | Friday | Testing | Test "View all project listings" website | 2020-03-20 | 6 | 6 | Inprogress
23 | Saturday | Testing | Test "Add projects" website | 2020-03-21 | 4 | 4 | Inprogress
23 | Sunday | Testing | Test "Add projects" website | 2020-03-22 | 2 |  | Inprogress
23 | Actual: | 33 |  |  |  | Plan: | 32
24 | Monday | Testing | Test "Add projects" website | 2020-03-23 | 4 | 6 | Inprogress
24 | Tuesday | Testing | Test "Edit projects" website | 2020-03-24 | 4 | 6 | Inprogress
24 | Wednesday | Meeting Mentor |  | 2020-03-25 | 4 | 6 | Inprogress
24 | Thursday | Testing | Test "Edit projects" website | 2020-03-26 | 4 | 4 | Inprogress
24 | Friday | Testing | Test "Edit projects" website | 2020-03-27 | 6 | 6 | Inprogress
24 | Saturday | Testing | Intergration test | 2020-03-28 | 6 | 4 | Inprogress
24 | Sunday | Testing | Intergration test | 2020-03-29 | 2 |  | Inprogress
24 | Actual: | 30 |  |  |  | Plan: | 32
25 | Monday | Testing | Intergration test | 2020-03-30 | 4 | 6 | Inprogress
25 | Tuesday | Testing | Intergration test | 2020-03-31 | 7 | 6 | Inprogress
25 | Wednesday | Meeting Mentor |  | 2020-04-01 | 4 | 6 | Inprogress
25 | Thursday | Testing | Update Test case module 1 | 2020-04-02 | 4 | 4 | Inprogress
25 | Friday | Testing | Update Test case module 2 | 2020-04-03 | 6 | 6 | Inprogress
25 | Saturday | Testing | Test excution module 2 | 2020-04-04 | 6 | 4 | Inprogress
25 | Sunday | Testing | Test excution module 2 | 2020-04-05 | 2 |  | Inprogress
25 | Actual: | 33 |  |  |  | Plan: | 32
26 | Monday | Testing | Test excution module 2 | 2020-04-06 | 4 | 6 | Inprogress
26 | Tuesday | Testing | Test excution module 2 | 2020-04-07 | 4 | 6 | Inprogress
26 | Wednesday | Meeting Mentor |  | 2020-04-08 | 4 | 6 | Inprogress
26 | Thursday | Testing | Defect log module 2 | 2020-04-09 | 4 | 4 | Inprogress
26 | Friday | Testing | Defect log module 2 | 2020-04-10 | 6 | 6 | Inprogress
26 | Saturday | Testing | Defect log module 2 | 2020-04-11 | 6 | 4 | Inprogress
26 | Sunday | Testing | Defect log module 2 | 2020-04-12 | 2 |  | Inprogress
26 | Actual: | 30 |  |  |  | Plan: | 32