## Slide 1
2019
2020
Today
Week 1
4
7
10
13
16
19
22
32
37
6 days
100%
Oct 14 - Oct 19
Kick-Off
18 days
70%
Oct 21 - Nov 9
Planning
36 days
38%
Nov 11 - Dec 21
Analysing
170 days
40%
Dec 23 - June 15
Implementation & Testing
24 days
Jan 13 - Feb 9
Tet Holiday
Mar 28 - April 10
Disease COVID-19
24 days
Nov 25 - Dec 21
Training
End Phase Planning (Review Documments)
Nov 9
Close Project
June 30
EOMP#1
Nov 16
Baseline RE, AR
Nov 30
EOPM#2
Jan 7
Start Module 1
Dec 23
Start Module 2
Jan 6
35
36
Delivery (Module 1 & 2)
25
Start Module 2
Mar 9
Start Module 3
April 1
May 23
Delivery (Module 3)
June 11
Submit document
June 15
June 30
Close Project
14 days