## Report
Earned Value Analysis Report
| Prepared By: | Huỳnh Tuấn Đạt
| Date: | 2019-10-14
[42]
| For Period: | Week 5
[7 empty] | CPI | 1.0413 | Under Budget
[7 empty] | SPI | 0.9963 | Ahead Schedule
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | TBC | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28
1 | Planing | 0
1.1 | Project Management Plan & Process | 0
1.1.1 | Create Communication Plan | 12 | 12
1.1.2 | Create Configuration Plan | 12 | 12
1.1.3 | Create Project Charter | 18 | 18
1.1.4 | Create Project Plan | 18 |  | 18
1.1.5 | Create Development Process | 18 |  | 18
1.1.6 | Create Quality Management Plan | 18 |  | 18
1.1.7 | Create Measurement Plan | 18 |  |  | 18
1.1.8 | Create Risk Management Plan | 18 |  |  | 18
1.2 | Requirement Plan and Process | 0
1.2.1 | Create Requirement Plan | 18 |  | 18
1.2.2 | Create Requirement Process | 18 |  | 18
1.3 | Architecture Plan and Process | 0
1.3.1 | Create Architecture Plan | 24 |  |  | 24
1.3.2 | Create Architecture Process | 24 |  |  | 24
1.4 | Details Design Plan and Process | 0
1.4.1 | Create Details Design Process | 18 |  |  | 18
1.5 | Implementation Plan and Process | 0
1.5.1 | Create Implementation Plan | 18 |  |  |  | 18
1.5.2 | Create Implementation Process | 18 |  |  |  | 18
1.6 | Test Plan and Process | 0
1.6.1 | Create Test Plan | 18 |  |  |  | 18
1.6.2 | Create Test Process | 18 |  |  |  | 18
1.7 | Trainning Plan | 0
1.7.1 | Create Trainning Plan | 18 |  |  |  | 18
2 | Analysing & Training | 0
2.1 | Requirement | 0
2.1.1 | Release S.R.S | 30 |  |  |  |  | 30
2.1.2 | Release ConOp | 24 |  |  |  |  | 24
2.1.3 | Release Tracebility Matrix | 18 |  |  |  |  | 18
2.2 | Architecture and Design | 0
2.2.1 | Release Architecture Driver | 24 | [5 empty] | 24
2.2.2 | Release Architecture Design | 18 | [5 empty] | 18
2.2.3 | Release Details Design | 18 | [5 empty] | 18
2.3 | Risk Management | 30 | [6 empty] | 30
2.4 | Training | 30 | [6 empty] | 30 | 30 | 30 | 30
3 | Implementation & Testing | 0
3.1 |  | 0
3.2 |  | 0
3.3 |  | 0
3.4 |  | 0
3.5 |  | 0
0
0
0
0
| Total Budgeted Cost | 516 | 42 | 90 | 102 | 90 | 72 | 60 | 60 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Planned Value (PV) | 42 | 132 | 234 | 324 | 396 | 456 | 516 | 546 | 576 | 606 | 606 | 606 | 606 | 606 | 606 | 606 | 606 | 606 | 606 | 606 | 606 | 606 | 606 | 606 | 606 | 606 | 606 | 606
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 30.5 | 126 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310
|  | Cumulative Earned Value (EV) | 40.8 | 130.8 | 232.8 | 322.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | 10.3 | 4.8 | -77.2 | 12.8 | -310 | -310 | -310 | -310 | -310 | -310 | -310 | -310 | -310 | -310 | -310 | -310 | -310 | -310 | -310 | -310 | -310 | -310 | -310 | -310 | -310 | -310 | -310 | -310
|  | Schedule Variance (SV = EV - PV) | -1.2 | -1.2 | -1.2 | -1.2 | -396 | -456 | -516 | -546 | -576 | -606 | -606 | -606 | -606 | -606 | -606 | -606 | -606 | -606 | -606 | -606 | -606 | -606 | -606 | -606 | -606 | -606 | -606 | -606
|  | Cost Performance Index (CPI = EV/AC) | 1.3377 | 1.0381 | 0.75097 | 1.0413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Schedule Performance Index (SPI = EV/PV) | 0.97143 | 0.99091 | 0.99487 | 0.9963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Estimated Cost at Completion (EAC) | 385.7353 | 497.0642 | 687.1134 | 495.539 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Note on A21: Work Breakdown Structure (WBS)
Note on C21: Total Budgeted Cost (TBC)

## EV
Earned Value Worksheet
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP).
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV)
WBS | Task Name | TCB | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28
1 | Planing | 0
1.1 | Project Management Plan & Process | 0
1.1.1 | Create Communication Plan | 12 | 100% | 100% | 100% | 100%
1.1.2 | Create Configuration Plan | 12 | 90% | 90% | 90% | 90%
1.1.3 | Create Project Charter | 18 | 100% | 100% | 100% | 100%
1.1.4 | Create Project Plan | 18 |  | 100% | 100% | 100%
1.1.5 | Create Development Process | 18 |  | 100% | 100% | 100%
1.1.6 | Create Quality Management Plan | 18 |  | 100% | 100% | 100%
1.1.7 | Create Measurement Plan | 18 |  |  | 100% | 100%
1.1.8 | Create Risk Management Plan | 18 |  |  | 100% | 100%
1.2 | Requirement Plan and Process | 0
1.2.1 | Create Requirement Plan | 18 |  | 100% | 100% | 100%
1.2.2 | Create Requirement Process | 18 |  | 100% | 100% | 100%
1.3 | Architecture Plan and Process | 0
1.3.1 | Create Architecture Plan | 24 |  |  | 100% | 100%
1.3.2 | Create Architecture Process | 24 |  |  | 100% | 100%
1.4 | Details Design Plan and Process | 0
1.4.1 | Create Details Design Process | 18 |  |  | 100% | 100%
1.5 | Implementation Plan and Process | 0
1.5.1 | Create Implementation Plan | 18 |  |  |  | 100%
1.5.2 | Create Implementation Process | 18 |  |  |  | 100%
1.6 | Test Plan and Process | 0
1.6.1 | Create Test Plan | 18 |  |  |  | 100%
1.6.2 | Create Test Process | 18 |  |  |  | 100%
1.7 | Trainning Plan | 0
1.7.1 | Create Trainning Plan | 18 |  |  |  | 100%
2 | Analysing & Training | 0
2.1 | Requirement | 0
2.1.1 | Release S.R.S | 30
2.1.2 | Release ConOp | 0
2.1.3 | Release Tracebility Matrix | 18
2.2 | Architecture and Design | 0
2.2.1 | Release Architecture Driver | 24
2.2.2 | Release Architecture Design | 18
2.2.3 | Release Details Design | 18
2.3 | Risk Management | 30
2.4 | Training | 30
3 | Implementation & Testing | 0
3.1 |  | 0
3.2 |  | 0
3.3 |  | 0
3.4 |  | 0
3.5 |  | 0
Insert new rows above this one
|  | Cumulative EV | 40.8 | 130.8 | 232.8 | 322.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## AC
Actual Cost Worksheet
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period.
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Transfer the Cumulative Actual Cost to the Report worksheet.
Actual Cost (AC) of Work Performed
WBS | Task Name | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28
1 | Planing
1.1 | Project Management Plan & Process
1.1.1 | Create Communication Plan | W1: 8
1.1.2 | Create Configuration Plan | W1: 12
1.1.3 | Create Project Charter | W1: 10.5
1.1.4 | Create Project Plan | W2: 20.5
1.1.5 | Create Development Process | W2: 19
1.1.6 | Create Quality Management Plan | W2: 16.5
1.1.7 | Create Measurement Plan | W3: 15
1.1.8 | Create Risk Management Plan | W3: 15.5
1.2 | Requirement Plan and Process
1.2.1 | Create Requirement Plan | W2: 19
1.2.2 | Create Requirement Process | W2: 20.5
1.3 | Architecture Plan and Process
1.3.1 | Create Architecture Plan | W3: 20.5
1.3.2 | Create Architecture Process | W3: 16
1.4 | Details Design Plan and Process
1.4.1 | Create Details Design Process | W3: 17
1.5 | Implementation Plan and Process
1.5.1 | Create Implementation Plan | W3: 17.5
1.5.2 | Create Implementation Process | W3: 18
1.6 | Test Plan and Process
1.6.1 | Create Test Plan | W3: 18.5
1.6.2 | Create Test Process | W3: 29.5
1.7 | Trainning Plan
1.7.1 | Create Trainning Plan | W3: 16.5
2 | Analysing & Training
2.1 | Requirement
2.1.1 | Release S.R.S
2.1.2 | Release ConOp
2.1.3 | Release Tracebility Matrix
2.2 | Architecture and Design
2.2.1 | Release Architecture Driver
2.2.2 | Release Architecture Design
2.2.3 | Release Details Design
2.3 | Risk Management
2.4 | Training
3 | Implementation & Testing
3.1
3.2
3.3
3.4
3.5
Insert new rows above this one
|  | 30.5 | 95.5 | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cumulative Actual Cost (AC) | 30.5 | 126 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310 | 310

## ©
Earned Value Management (EVM) Template
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/critical-path-method.html
© 2012-2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet.