## Cover
Project: Capstone Project_Quản Lý Cty Bất Động Sản
Team Development : Hello World
Mentor: Mr . Đặng Đình Hòa
Document: Defect Log
Purpose: This document is used to classify the defect, how they are prioritizied, date raise defect and date closed
Version History
| Version | Date | Author | Comment
| 1 | 28/5/2020 | Như phương | Create document
| 1.1 | 30/5/2020 | Như phương | Update document
| 1.1 | 2020-06-06 | Như phương | Update defect
| 1.2 | 2020-08-06 | Như phương | Update defect
| 1.3 | 13/6/2020 | Team | Review

## Defect Log
DEFECT LOG MODULE 3
NO. | DEFECT ID | DEFECT DESCRIPTION | REFERENCE | VERSION | STEPS | DATE RASISED | DETECTED BY | STATUS | FIXED BY | DATE CLOSED | PRIORITY
1 | #1 | interface "view weekly business results" system does not allow users to slide on the screen so for small screens will not be able to see all business results |  | 1 | step1: user login to the app with employee account step 2: click "statistical report" step 3: select "view weekly business results" | 28/5/2020 | Như phuong | close | Quang Vương | 2020-06-06 | medium
2 | #2 | interface "view weekly results" when having the same business results but not in the same ranking |  | 1 | step1: user login to the app with employee account step 2: click "statistical report" step 3: select "view weekly business results" | 28/5/2020 | Như phuong | open | Quang Vương |  | medium
3 | #3 | "user compare" interface leaves the fields blank for years and months after confirming the "please enter what to look for" message, users can't continue to enter data to search |  | 2 | step1: User login to the Real Estate App with personal account step2: On the home page, click on the "Statistics report" step3: Click on the "Business results graph" step4: In the "Furniture" view "click" room " step5: Select" Year " step6: Select" Quarter " step7: Select" month step8: Click "search" step9: Enter year step10: enter Quarter step11: enter month | 2020-08-06 | Như phuong | open | Đạt Huỳnh |  | medium
3 | #4 | "user compare" interface leaves the fields blank for years and months after confirming the "please enter what to look for" message, users can't continue to enter data to search |  | 2 | step1: User login to the Real Estate App with personal account step2: On the home page, click on the "Statistics report" step3: Click on the "Business results graph" step4: In the "Furniture" view "click" employee " step5: Select" Year " step6: Select" Quarter " step7: Select" month step8: Click "search" step9: Enter year step10: enter Quarter step11: enter month | 2020-08-06 | Như phuong | open | Đạt Huỳnh |  | medium
3 | #5 | "user compare" interface leaves the fields blank for years and months after confirming the "please enter what to look for" message, users can't continue to enter data to search |  | 2 | step1: User login to the Real Estate App with personal account step2: On the home page, click on the "Statistics report" step3: Click on the "Business results graph" step4: In the "Furniture" view "click" employee " step5: Select" Year " step6: Select" Quarter " step7: Select" month step8: Click "search" step9: Enter year step10: enter Quarter step11: enter month | 2020-08-06 | Như phuong | open | Đạt Huỳnh |  | medium
4 | #6 | the "compare business results" interface displays graphs but the captions cannot show them all yet |  | 2 | step1: User login to the Real Estate App with personal account step2: On the home page, click on the "Statistics report" step3: Click on the "Business results graph" step4: In the "Furniture" view "click" employee " step5: Select" Year " step6: Select" Quarter " step7: Select" month step8: Click "search" | 2020-08-06 | Như phuong | open | Đạt Huỳnh |  | Medium
4 | #7 | the "compare business results" interface displays graphs but the captions cannot show them all yet |  | 2 | step1: User login to the Real Estate App with personal account step2: On the home page, click on the "Statistics report" step3: Click on the "Business results graph" step4: In the "Furniture" view "click" group " step5: Select" Year " step6: Select" Quarter " step7: Select" month step8: Click "search" | 2020-08-06 | Như phuong | open | Đạt Huỳnh |  | Medium
4 | #8 | the "compare business results" interface displays graphs but the captions cannot show them all yet |  | 2 | step1: User login to the Real Estate App with personal account step2: On the home page, click on the "Statistics report" step3: Click on the "Business results graph" step4: In the "Furniture" view "click" room " step5: Select" Year " step6: Select" Quarter " step7: Select" month step8: Click "search | 2020-08-06 | Như phuong | open | Đạt Huỳnh |  | Medium
5 | #9 | WebAdmin's "import" interface displays three frames to import the excel file |  | 2 | Step 1: Admin login to Real Estate WebAdmin Step 2: on the homepage, select myc5 "statistical report" Step 3: in the dropbox, select "import" Step 4: In the interface: import | 2020-08-06 | Như phuong | open | Đạt Huỳnh |  | low
6 | #6
7 | #7
8 | #8
9 | #9
10 | #10
11 | #11
12 | #12
13 | #13
14 | #14
15 | #15
11 | #16
#17
#18
#19
18 | #19
19 | #20
20 | #21
21 | #22
22 | #23
23 | #24
24 | #25
25 | #26
26 | #27
27 | #28
28 | #29
29 | #30
30 | #31