## Summary
Actual | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Total
Đạt Huỳnh | 30 | 22 | 0 | [34 empty] | 52
Quốc Nhân | 26 | 30 | [35 empty] | 56
Vương Trương | 26.5 | 18.5 | [35 empty] | 45
Anh Minh | 24 | 27 | [35 empty] | 51
Như Phương | 27 | 29 | [35 empty] | 56
| 133.5 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260
Planed | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Total
Đạt Huỳnh | 30 | 34 | 38 | [34 empty] | 102
Quốc Nhân | 26 | 30 | [35 empty] | 56
Vương Trương | 27.5 | 22 | [35 empty] | 49.5
Anh Minh | 28 | 30 | [35 empty] | 58
Như Phương | 28 | 29 | [35 empty] | 57
| 139.5 | 284.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5 | 322.5

## Đạt Huỳnh
Timelog: | Đạt Huỳnh
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
1 | Monday | Meeting Mentor |  | 14/10/2019 | 4 | 4 | Done
1 | Tuesday | Training | Resreach information WebGIS | 15/10/2019 | 6 | 6 | Inprogress
1 | Wednesday | Training | Resreach coding language | 16/10/2019 | 6 | 6 | Inprogress
1 | Thursday | Project Management | Resreach & Create template documments | 17/10/2019 | 4 | 4 | Done
1 | Friday | Meetting Customer |  | 18/10/2019 | 4 | 4 | Done
1 | Saturday | Project Management | Create Comunication plan | 19/10/2019 | 6 | 6 | Done
Total | Actual: | 30 |  |  |  | Plan: | 30
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
2 | Monday | Project Management | Create Configuration Management Plan | 21/10/2019 | 6 | 6 | Inprogress
2 | Tuesday | Project Management | Create Configuration Management Plan | 22/10/2019 | 6 | 6 | Inprogress | PM_ConfigurationManagementPlan_Ver1.0.docx
2 | Wednesday | Meeting Mentor |  | 23/10/2019 | 4 | 4 | Done
2 | Thursday | Project Management | Create TimeLog | 24/10/2019 | 6 | 6 | Done
2 | Friday | Training | Reading Customer Documments | 25/10/2019 |  | 6
2 | Saturday | Training | Presentation Customer Documments | 26/10/2029 |  | 6
Total | Actual: | 22 |  |  |  | Plan: | 34
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
3 | Monday | Project Management | Create Control&Monitoring Project | 2019-10-28 |  | 6 | Inprogress
3 | Tuesday | Project Management | Create Control&Monitoring Project | 2019-10-29 |  | 6 | Done
3 | Tuesday | Meeting Mentor |  | 2019-11-29 |  | 4
3 | Wednesday | Meetting Customer |  | 2019-10-30 |  | 4
3 | Thursday | Project Management | Create Timeline | 2019-10-31 |  | 6
3 | Friday | Project Management | Create EVM | 2019-11-01 |  | 6
3 | Saturday | Project Management | Create EVM | 2019-11-02 |  | 6
Total | Actual: | 0 |  |  |  | Plan: | 38
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
4 | Monday |  |  | 2019-11-04
4 | Tuesday |  |  | 2019-11-05
4 | Wednesday |  |  | 2019-11-06
4 | Thursday |  |  | 2019-11-07
4 | Friday |  |  | 2019-11-08
4 | Saturday | Project Management | Review Documents | 2019-11-09
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
5 | Monday |  |  | 2019-11-11
5 | Tuesday |  |  | 2019-11-12
5 | Wednesday |  |  | 2019-11-13
5 | Thursday |  |  | 2019-11-14
5 | Friday |  |  | 2019-11-15
5 | Saturday |  |  | 2019-11-16
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
6 | Monday |  |  | 2019-11-18
6 | Tuesday |  |  | 2019-11-19
6 | Wednesday |  |  | 2019-11-20
6 | Thursday |  |  | 2019-11-21
6 | Friday |  |  | 2019-11-22
6 | Saturday |  |  | 2019-11-23
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
7 | Monday |  |  | 2019-11-25
7 | Tuesday |  |  | 2019-11-26
7 | Wednesday |  |  | 2019-11-27
7 | Thursday |  |  | 2019-11-28
7 | Friday |  |  | 2019-11-29
7 | Saturday |  |  | 2019-11-30
Total | Actual: | 0 |  |  |  | Plan: | 0

## Quốc Nhân
Timelog: | Quốc Nhân
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
1 | Monday | Meeting Mentor |  | 14/10/2019 | 4 | 4 | Done
1 | Tuesday | Training | Research Information WebGIS | 15/10/2019 | 4 | 4 | Inprogress
1 | Wednesday | Training | Research Information WebGIS | 16/10/2019 | 5 | 5 | Inprogress
1 | Thursday | Project Management | Create Member Charter | 17/10/2019 | 5 | 5 | Done
1 | Friday | Meetting Customer |  | 18/10/2019 | 4 | 4 | Done
1 | Saturday | Training | Research WebGIS, Database & Code | 19/10/2019 | 4 | 4 | Inprogress
Total | Actual: | 26 |  |  |  | Plan: | 26
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
2 | Monday | Project Management | Create Team Charter | 21/10/2019 | 6 | 6 | Done | PM_TeamCharter_Ver1.0.docx
2 | Tuesday | Training | Research Information WebGIS | 22/10/2019 | 5 | 5 | Inprogress
2 | Wednesday | Meeting Mentor |  | 23/10/2019 | 4 | 4 | Done
2 | Thursday | Project Management | Draw the steps submitted and changed github & gg drive | 24/10/2019 | 5 | 5 | Done | PM_ConfigurationManagementPlan_Ver1.0.docx
2 | Friday | Training | Reading Customer Documments | 25/10/2019 | 5 | 5 | Done
2 | Saturday | Training | Presentation Customer Documments | 26/10/2019 | 5 | 5 | Done
Total | Actual: | 30 |  |  |  | Plan: | 30
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
3 | Monday |  |  | 2019-10-28
3 | Tuesday |  |  | 2019-10-29
3 | Wednesday |  |  | 2019-10-30
3 | Thursday |  |  | 2019-10-31
3 | Friday |  |  | 2019-11-01
3 | Saturday |  |  | 2019-11-02
2019-11-03
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
4 | Monday |  |  | 2019-11-04
4 | Tuesday |  |  | 2019-11-05
4 | Wednesday |  |  | 2019-11-06
4 | Thursday |  |  | 2019-11-07
4 | Friday |  |  | 2019-11-08
4 | Saturday |  |  | 2019-11-09
2019-11-10
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
5 | Monday |  |  | 2019-11-11
5 | Tuesday |  |  | 2019-11-12
5 | Wednesday |  |  | 2019-11-13
5 | Thursday |  |  | 2019-11-14
5 | Friday |  |  | 2019-11-15
5 | Saturday |  |  | 2019-11-16
2019-11-17
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
6 | Monday |  |  | 2019-11-18
6 | Tuesday |  |  | 2019-11-19
6 | Wednesday |  |  | 2019-11-20
6 | Thursday |  |  | 2019-11-21
6 | Friday |  |  | 2019-11-22
6 | Saturday |  |  | 2019-11-23
2019-11-24
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
7 | Monday |  |  | 2019-11-25
7 | Tuesday |  |  | 2019-11-26
7 | Wednesday |  |  | 2019-11-27
7 | Thursday |  |  | 2019-11-28
7 | Friday |  | Create tracebility metrix | 2019-11-29 | 6
7 | Saturday |  |  | 2019-11-30
2019-12-01
Total | Actual: | 6 |  |  |  | Plan: | 0

## Vương Trương
Timelog:
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
1 | Monday | Meeting Mentor |  | 14/10/2019 | 4 | 4 | Done
1 | Tuesday | Training | research webgis | 15/10/2019 | 5 | 5 | Inprogress
1 | Wednesday | Training | research webgis | 16/10/2019 | 4.5 | 4.5 | Inprogress
1 | Thursday | Training | find another app like webgis | 17/10/2019 | 5 | 5 | Done
1 | Friday | Meetting Customer |  | 18/10/2019 | 4 | 4 | Done
1 | Saturday | Training |  | 2019-10-19 | 4 | 5 | Inprogress
Total | Actual: | 26.5 |  |  |  | Plan: | 27.5
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
2 | Monday | Project Management | choose model | 2019-10-21 | 5.5 | 6 | Done
2 | Tuesday | Training | Install qgis | 2019-10-22 | 5 | 6 | Done
2 | Wednesday | Meeting Mentor |  | 2019-10-23 | 4 | 4 | Done
2 | Thursday | Project Management | research webgis | 2019-10-24 |  |  | Done
2 | Friday | Training | Readding Customer Documments | 2019-10-25 |  |  | Done
2 | Saturday | Training | Presentation Customer Documments | 2019-10-26 | 4 | 6 | Done
Total | Actual: | 18.5 |  |  |  | Plan: | 22
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
3 | Monday
3 | Tuesday
3 | Wednesday
3 | Thursday
3 | Friday
3 | Saturday
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
4 | Monday
4 | Tuesday
4 | Wednesday
4 | Thursday
4 | Friday
4 | Saturday
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
5 | Monday
5 | Tuesday
5 | Wednesday
5 | Thursday
5 | Friday
5 | Saturday
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
6 | Monday
6 | Tuesday
6 | Wednesday
6 | Thursday
6 | Friday
6 | Saturday
Total | Actual: | 0 |  |  |  | Plan: | 0

## Anh Minh
Timelog:
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
1 | Monday | Meeting Mentor |  | 14/10/2019 | 4 | 4 | Done
1 | Tuesday | Training | Research WebGIS | 15/10/2019 | 5 | 5 | Inprogress
1 | Wednesday | Training | Research WebGIS | 16/10/2019 | 3 | 5 | Inprogress
1 | Thursday | Training | Research WebGIS | 17/10/2019 | 3 | 5 | Inprogress
1 | Friday | Meetting Customer |  | 18/10/2019 | 4 | 4 | Done
1 | Saturday | Training |  | 19/10/2019 | 5 | 5 | Inprogress
Total | Actual: | 24 |  |  |  | Plan: | 28
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
2 | Monday | Training | Readding Incremental Model | 21/10/2019 | 5 | 5 | Done
2 | Tuesday | Training | Readding Geodatabase | 22/10/2019 | 3 | 5 | Done
2 | Wednesday | Meeting Mentor |  | 23/10/2019 | 4 | 4 | Done
2 | Thursday | Training | Setting and research QGIS | 24/10/2019 | 7 | 5 | Done
2 | Friday | Training | Readding Customer Documments | 25/10/2019 | 4 | 5 | Done
2 | Saturday | Training | Presentation Customer Documments | 26/10/2019 | 4 | 6 | Done
Total | Actual: | 27 |  |  |  | Plan: | 30
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
3 | Monday
3 | Tuesday
3 | Wednesday
3 | Thursday
3 | Friday
3 | Saturday
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
4 | Monday
4 | Tuesday
4 | Wednesday
4 | Thursday
4 | Friday
4 | Saturday
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
5 | Monday
5 | Tuesday
5 | Wednesday
5 | Thursday
5 | Friday
5 | Saturday
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
6 | Monday
6 | Tuesday
6 | Wednesday
6 | Thursday
6 | Friday
6 | Saturday
Total | Actual: | 0 |  |  |  | Plan: | 0

## Như Phương
Timelog:
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
1 | Monday | Meeting Mentor |  | 14/10/2019 | 4 | 4 | Done
1 | Tuesday | Project Management | Research project | 15/10/2019 | 5 | 5 | Done
1 | Wednesday | Project Management | Research project | 16/10/2019 | 5 | 5 | Done
1 | Thursday | Project Management | Research project | 17/10/2019 | 5 | 5 | Done
1 | Friday | Meetting Customer |  | 18/10/2019 | 4 | 4 | Done
1 | Saturday | Project Management | Complete the meeting minutes | 19/10/2019 | 4 | 5 | Done
Total | Actual: | 27 |  |  |  | Plan: | 28
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
2 | Monday | Project Management | Userstory | 21/10/2019 | 5 | 5 | Done
2 | Tuesday | Project Management | research software process model | 22/10/2019 | 5 | 5 | Done
2 | Wednesday | Meeting Mentor |  | 23/10/2019 | 4 | 4 | Done
2 | Thursday | Project Management | Research GIS | 24/10/2019 | 5 | 5 | Done
2 | Friday | Project Management | Research GIS | 25/10/2019 | 5 | 5 | Done
2 | Saturday | Project Management | Complete the meeting minutes ; Present document GIS with team | 26/10/2019 | 5 | 5 | Done
Total | Actual: | 29 |  |  |  | Plan: | 29
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
3 | Monday
3 | Tuesday
3 | Wednesday
3 | Thursday
3 | Friday
3 | Saturday
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
4 | Monday
4 | Tuesday
4 | Wednesday
4 | Thursday
4 | Friday
4 | Saturday
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
5 | Monday
5 | Tuesday
5 | Wednesday
5 | Thursday
5 | Friday
5 | Saturday
Total | Actual: | 0 |  |  |  | Plan: | 0
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
6 | Monday
6 | Tuesday
6 | Wednesday
6 | Thursday
6 | Friday
6 | Saturday
Total | Actual: | 0 |  |  |  | Plan: | 0