## WBS Phase 1
Project Title | Real Estate App
Project Manager | Đạt Huỳnh
Phase One | Planning
WBS Number | Task Title | Task Owner | Start Date | Due Date | Duration | % of Task Complete | Week 1 | [5 empty] | Week 2 | [5 empty] | Week 3 | [5 empty] | Week 4 | [5 empty] | Week 5
[7 empty] | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa
1 | Project Management Plan & Process | [5 empty] | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18 | 2019-10-19 | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-26 | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31 | 2019-11-01 | 2019-11-02 | 2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14 | 2019-11-15 | 2019-11-16
1.1 | Communication Plan | Đạt Huỳnh | 2019-10-14 | 2019-10-15 | 2 | 100% | bar: 2019-10-14 to 2019-10-15; 2019-11-04 to 2019-11-05
1.2 | Configuration Plan | Đạt Huỳnh | 2019-10-15 | 2019-10-16 | 2 | 100% | bar: 2019-10-15 to 2019-10-16; 2019-11-04 to 2019-11-05
1.3 | Project Charter | Quốc Nhân | 2019-10-17 | 2019-10-19 | 3 | 10% | bar: 2019-10-17 to 2019-10-26; 2019-11-04 to 2019-11-05
1.4 | Project Plan | Quốc Nhân | 2019-10-21 | 2019-10-23 | 3 | 90% | bar: 2019-11-04 to 2019-11-05
1.5 | Development Process | Đạt Huỳnh | 2019-10-21 | 2019-10-23 | 3 | 100% | bar: 2019-11-04 to 2019-11-05
1.6 | Quality Management Plan | Quang Vương | 2019-10-24 | 2019-10-26 | 3 | 100% | bar: 2019-11-04 to 2019-11-05
1.7 | Measurement Plan | Anh Minh | 2019-10-28 | 2019-10-30 | 3 | 5% | bar: 2019-10-21 to 2019-10-30; 2019-11-04 to 2019-11-05
1.8 | Risk Management Plan | Anh Minh | 2019-10-28 | 2019-10-30 | 3 | 100% | bar: 2019-10-21 to 2019-10-30; 2019-11-04 to 2019-11-05
2 | Requirement Plan and Process
2.1 | Requirement Plan | Như Phương | 2019-10-24 | 2019-10-26 | 3 | 100% | bar: 2019-11-04 to 2019-11-05
2.2 | Requirement Process | Như Phương | 2019-10-24 | 2019-10-26 | 3 | 0% | bar: 2019-11-04 to 2019-11-05
3 | Architecture Plan and Process
3.1 | Architecture Plan | Quang Vương | 2019-10-28 | 2019-10-31 | 4 | 0% | bar: 2019-10-21 to 2019-10-30; 2019-11-04 to 2019-11-05
3.2 | Architecture Process | Quốc Nhân | 2019-10-28 | 2019-10-31 | 4 | 0% | bar: 2019-10-21 to 2019-10-30; 2019-11-04 to 2019-11-05
4 | Details Design Plan and Process
4.1 | Details Design Process | Đạt Huỳnh | 2019-10-31 | 2019-11-02 | 3 | 0% | bar: 2019-10-31 to 2019-11-05
5 | Implementation Plan and Process
5.1 | Implementation Plan |  | 2019-11-04 | 2019-11-06 | 3 | 0% | bar: 2019-11-04 to 2019-11-05
5.2 | Implementation Process |  | 2019-11-04 | 2019-11-06 | 3 | 0% | bar: 2019-11-04 to 2019-11-05
6 | Test Plan and Process
6.1 | Test Plan |  | 2019-11-07 | 2019-11-09 | 3 | 0% | bar: 2019-11-04 to 2019-11-05
6.2 | Test Process |  | 2019-11-07 | 2019-11-09 | 3 | 0% | bar: 2019-11-04 to 2019-11-05
7 | Trainning Plan
7.1 | Trainning Plan |  | 2019-11-07 | 2019-11-09 | 3 | 0% | bar: 2019-11-04 to 2019-11-05
Formulas:
Duration = DAYS([Due Date],[Start Date])+1

## WBS Phase 2
Project Title | Real Estate App
Project Manager | Đạt Huỳnh
Phase Two | Analysing
WBS Number | Task Title | Task Owner | Start Date | Due Date | Duration | % of Task Complete | Week 1 | [5 empty] | Week 2 | [5 empty] | Week 3 | [5 empty] | Week 4 | [5 empty] | Week 5
[7 empty] | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa | Mo | Tu | We | Th | Fr | Sa
1 | Requirement |  |  |  |  | 100%
1.1 | SRS |  |  |  | 1 | 10%
1.2 | ConOp |  |  |  | 1 | 1%
1.3 | Tracebility Matrix |  |  |  | 1 | 1%
2 | Architecture and Design |  |  |  |  | 1%
2.1 | Architecture Driver |  |  |  | 1 | 1%
2.2 | Architecture Design |  |  |  | 1 | 1%
2.3 | Details Design |  |  |  | 1 | 1%
Formulas:
Duration = DAYS([Due Date],[Start Date])+1

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.