## Summary
Actual | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Total
Đạt Huỳnh | 24 | 22 | [35 empty] | 46
0
0
0
0
| 24 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46
Planed | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Total
Đạt Huỳnh | 24 | 34 | [35 empty] | 58
0
0
0
0
| 24 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58

## Đạt Huỳnh
Timelog: | Đạt Huỳnh
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
1 | Monday | Meeting Mentor |  | 14/10/2019 | 4 | 4 | Done
1 | Tuesday | Training | Resreach information WebGIS | 15/10/2019 | 6 | 6 | Inprogress |  | 8
1 | Wednesday | Training | Resreach coding language | 16/10/2019 | 6 | 6 | Inprogress
1 | Thursday | Project Management | Resreach & Create template documments | 17/10/2019 | 4 | 4 | Done
1 | Friday | Meetting Customer |  | 18/10/2019 | 4 | 4 | Done
1 | Saturday |  |  | 19/10/2019
Total | Actual: | 24 |  |  |  | Plan: | 24
2 | Monday | Project Management | Create Configuration Management Plan | 21/10/2019 | 6 | 6 | Inprogress
2 | Tuesday | Project Management | Create Configuration Management Plan | 22/10/2019 | 6 | 6 | Inprogress | PM_ConfigurationManagementPlan_Ver1.0.docx
2 | Wednesday | Meeting Mentor |  | 23/10/2019 | 4 | 4 | Done
2 | Thursday | Project Management | Create TimeLog | 24/10/2019 | 6 | 6 | Done
2 | Friday | Training | Readding Customer Documments | 25/10/2019 |  | 6
2 | Saturday | Training | Presentation Customer Documments | 26/10/2029 |  | 6
Total | Actual: | 22 |  |  |  | Plan: | 34

## Vương Trương
Timelog:
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
1 | Monday | Meeting Mentor |  | 14/10/2019 | 4 | 4 | Done
1 | Tuesday | Training | research webgis | 15/10/2019 | 5 | 5 | Inprogress
1 | Wednesday | Training | research webgis | 16/10/2019 | 4.5 | 4.5 | Inprogress
1 | Thursday | Training | find another app like webgis | 17/10/2019 | 5 | 5 | Done
1 | Friday | Meetting Customer |  | 18/10/2019 | 4 | 4 | Done
1 | Saturday | Training |  | 2019-10-19 | 4 | 5 | Inprogress
Total | Actual: | 26.5 |  |  |  | Plan: | 27.5
2 | Monday | Project Management | choose model | 2019-10-21 | 5.5 | 6 | Done
2 | Tuesday | Training | Install qgis | 2019-10-22 | 5 | 6 | Done
2 | Wednesday | Meeting Mentor |  | 2019-10-23 | 4 | 4 | Done
2 | Thursday | Project Management | research webgis | 2019-10-24 |  |  | Done
2 | Friday | Training | Readding Customer Documments | 2019-10-25 |  |  | Done
2 | Saturday | Training | Presentation Customer Documments | 2019-10-26 | 4 | 6 | Done
Total | Actual: | 18.5 |  |  |  | Plan: | 22
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
3 | Monday | Training | Research GIS | 2019-10-28 | 5 | 5 | Done
3 | Tuesday | Meeting Mentor |  | 2019-10-29 | 4 | 4 | Done
3 | Wednesday | Meetting Customer |  | 2019-10-30 | 4.5 | 5 | Done
3 | Thursday | Training | research react | 2019-10-31 | 5 | 5 | Done
3 | Friday | Training | Install react | 2019-10-01 | 6 | 5 | Done
3 | Saturday | Project Management | Document quality management | 2019-10-02 | 5.5 | 5 | Done
Total | Actual: | 30 |  |  |  | Plan: | 29

## Sheet2
Timelog:
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
1 | Monday | Training | Research GIS | 2019-10-28 | 5 | 5 | Done
1 | Tuesday | Meeting Mentor |  | 2019-10-29 | 4 | 4 | Done
1 | Wednesday | Meetting Customer |  | 2019-10-30 | 4.5 | 5 | Done
1 | Thursday | Training | research react | 2019-10-31 | 5 | 5 | Done
1 | Friday | Training | Install react | 2019-10-01 | 6 | 5 | Done
1 | Saturday | Project Management | Document quality management | 2019-10-02 | 5.5 | 5 | Done
Total | Actual: | 30 |  |  |  | Plan: | 29
2 | Monday | Project Management |  | 20/10/2019 |  |  | Done
2 | Tuesday | Project Management |  | 21/10/2019 |  |  | Done
2 | Wednesday | Meeting Mentor |  | 22/10/2019 |  |  | Done
2 | Thursday | Project Management |  | 23/10/2019 |  |  | Done
2 | Friday | Project Management |  | 24/10/2019 |  |  | Done
2 | Saturday | Project Management |  |  |  |  | Done
Total | Actual: | 0 |  |  |  | Plan: | 0