## Milestone Chart
Date | Activity | Date | Activity | Text Placement
2019-10-14 | Kick-off | 2019-10-14 | Kick-off | 10
2019-11-04 | Trainning code | 2019-11-04 | Trainning code | -10
2019-11-18 | Start Function: Account management | 2019-11-18 | Start Function: Account management | 10
2019-11-24 | End Function: Account management | 2019-11-24 | End Function: Account management | -10
2019-11-25 | Start Function: Project management | 2019-11-25 | Start Function: Project management | 10
2019-11-01 | End Function: Project management | 2019-11-01 | End Function: Project management | -10
2019-11-16 | EOMP#1 | 2019-11-16 | EOMP#1 | 10
2019-12-02 | Start Function: Statistical management, reporting | 2019-12-02 | Start Function: Statistical management, reporting | -10
2019-12-08 | End Function: Statistical management, reporting | 2019-12-08 | End Function: Statistical management, reporting | 10
2019-12-09 | Start Function: Business trip manager. Management quit, Other functions | 2019-12-09 | Start Function: Business trip manager. Management quit, Other functions | -15
2019-12-14 | End Function: Business trip manager. Management quit, Other functions | 2019-12-14 | End Function: Business trip manager. Management quit, Other functions | 15
2019-12-15 | End phase 1 | 2019-12-15 | End phase 1 | -15
2019-12-22 |  | 2019-12-22 | #N/A | #N/A
Formulas:
Date = IF([Date]<>"",[Date],"")
Milestone Chart