## Revision History
WORK BREAKDOWN STRUCTURE 3 BDS Project
| Project Name: | BDS Project
| Team: | Team 03 - Hello World
| Document: | Work breakdown structure 3
| Creator: | Nhan Pham
| Created Date: | 2019-04-01
Revision History
| Version | Date | Author | Content
| Version 1.0 | 2019-04-01 | Nhan Pham | Create work breakdown structure 3
| 1.1 | 2020-06-20 | Nhan Pham | Review

## Dữ liệu dự án
Bảng công việc
ID | Nội dung công việc | Người phụ trách | Ngày bắt đầu | Ngày kết thúc | Số ngày (ngày) | Tình trạng | Số giờ hoàn thành công việc kế hoạch (Giờ) | Mức độ ưu tiên | Số giờ hoàn thành công việc cá nhân (Giờ)
1 | Design prototype, sequence, use case description View business results the week "Employees" app, Edit "Team & Room" Website | Quốc Nhân | 2020-04-06 | 2020-04-08 | 2 | Đã hoàn thành | 18 | Cao | 16
2 | Design prototype, sequence, use case description View details of the weekly business results the "Employees" app, Add "Team & Room" Website | Quốc Nhân | 2020-04-09 | 2020-04-10 | 1 | Đã hoàn thành | 9 | Cao | 16
3 | Design prototype, sequence, use case description View business results the week "Team" app | Quốc Nhân | 2020-04-11 | 2020-04-13 | 2 | Đã hoàn thành | 18 | Cao | 22
4 | Design prototype, sequence, use case description View business results the week "Room" app | Quốc Nhân | 2020-04-14 | 2020-04-16 | 2 | Đã hoàn thành | 18 | Cao | 15 | Formula
5 | Design prototype, sequence, use case description View business results graph "Employees" app, Delete "Team & Room" Website | Quốc Nhân | 2020-04-17 | 2020-04-20 | 3 | Đã hoàn thành | 27 | Cao | 22 | Số giờ hoàn thành công việc cá nhân = Thời gian cồng việc + Số công việc đã làm (cập nhật time log)
6 | Design prototype, sequence, use case description Search business results graph "Employees" app | Quốc Nhân | 2020-04-20 | 2020-04-22 | 2 | Đã hoàn thành | 18 | Cao | 16
7 | Design prototype, sequence, use case description View the "Team" business results graph app | Quốc Nhân | 2020-04-23 | 2020-04-25 | 2 | Đã hoàn thành | 18 | Cao | 18
8 | Design prototype, sequence, use case description Search results graph "Team" app | Quốc Nhân | 2020-04-27 | 2020-04-28 | 1 | Đã hoàn thành | 9 | Cao | 15
9 | Design prototype, sequence, use case description View business results graph "Rooms" app | Quốc Nhân | 2020-04-28 | 2020-04-29 | 1 | Đã hoàn thành | 9 | Cao | 14
10 | Design prototype, sequence, use case description Search business results graph "Room" app | Quốc Nhân | 2020-04-30 | 2020-05-01 | 1 | Đã hoàn thành | 9 | Cao | 11
11 | Design prototype, sequence, use case description View compare business results "Employees" | Quốc Nhân | 2020-05-04 | 2020-05-06 | 2 | Đã hoàn thành | 18 | Cao | 10
12 | Design prototype, sequence, use case description Search compare business results "Employees" app | Quốc Nhân | 2020-05-07 | 2020-05-09 | 2 | Đã hoàn thành | 18 | Cao | 18
13 | Design prototype, sequence, use case description View the business results "Team" app | Quốc Nhân | 2020-05-11 | 2020-05-13 | 2 | Đã hoàn thành | 18 | Cao | 14
14 | Design prototype, sequence, use case description Search compare business results "Team" app | Quốc Nhân | 2020-05-14 | 2020-05-16 | 2 | Đã hoàn thành | 18 | Cao | 23
15 | Design prototype, sequence, use case description View compare business results "Rooms" app | Quốc Nhân | 2020-05-18 | 2020-05-20 | 2 | Đã hoàn thành | 18 | Cao | 16
16 | Design prototype, sequence, use case description Search compare business results "Rooms" app | Quốc Nhân | 2020-05-21 | 2020-05-22 | 1 | Đã hoàn thành | 9 | Cao | 23
17 | Design prototype, sequence, use case description Delete room website, View room website | Quốc Nhân | 2020-05-25 | 2020-05-26 | 1 | Đã hoàn thành | 9 | Cao | 15
18 | Design prototype, sequence, use case description Import file website | Quốc Nhân | 2020-05-27 | 2020-05-28 | 1 | Đã hoàn thành | 9 | Cao | 16
19 | Design prototype, sequence, use case description View personal information app | Quốc Nhân | 2020-06-01 | 2020-06-02 | 1 | Đã hoàn thành | 18 | Cao | 16
20 | Design prototype, sequence, use case description Add room, Template excel website | Quốc Nhân | 2020-06-02 | 2020-06-03 | 1 | Đã hoàn thành | 8 | Medium | 16
21 | Design prototype, sequence, use case description Edit room | Quốc Nhân | 2020-06-04 | 2020-06-06 | 2 | Đã hoàn thành | 16 | Medium | 16
22 | Design prototype, sequence, use case description View happy birthday app | Quốc Nhân | 2020-06-07 | 2020-06-08 | 1 | Đã hoàn thành | 7 | Low | 10
23 | Design messages list module 3 | Quốc Nhân | 2020-06-09 | 2020-06-11 | 2 | Đã hoàn thành | 18 | Cao | 21
24 | Design business rule module 3 | Quốc Nhân | 2020-06-12 | 2020-06-13 | 1 | Đã hoàn thành | 9 | Cao | 24
25 | Design use case diagram module 3 | Quốc Nhân | 2020-06-14 | 2020-06-15 | 1 | Đã hoàn thành | 9 | Cao | 20
26 | Code layout and logic birthday | Đạt Huỳnh | 2020-04-06 | 2020-04-11 | 5 | Đã hoàn thành | 45 | Cao | 42
27 | Add music for ios and research chart | Đạt Huỳnh | 2020-04-13 | 2020-04-18 | 5 | Đã hoàn thành | 45 | Cao | 41
28 | Config chart and coding layout report sale | Đạt Huỳnh | 2020-04-20 | 2020-04-25 | 5 | Đã hoàn thành | 45 | Cao | 40
29 | coding layout chart sale result | Đạt Huỳnh | 2020-04-27 | 2020-05-02 | 5 | Đã hoàn thành | 45 | Cao | 25
30 | coding layout chart sale compare and handle data group sale result chart | Đạt Huỳnh | 2020-05-04 | 2020-05-09 | 5 | Đã hoàn thành | 45 | Cao | 42
31 | coding hande data personal sale result chart | Đạt Huỳnh | 2020-05-11 | 2020-05-16 | 5 | Đã hoàn thành | 45 | Cao | 49
32 | coding hande data team sale result chart | Đạt Huỳnh | 2020-05-18 | 2020-05-23 | 5 | Đã hoàn thành | 45 | Cao | 54
33 | coding hande data personal sale compare chart | Đạt Huỳnh | 2020-05-25 | 2020-05-30 | 5 | Đã hoàn thành | 45 | Cao | 54
34 | coding hande data team sale compare chart | Đạt Huỳnh | 2020-06-01 | 2020-06-06 | 5 | Đã hoàn thành | 45 | Cao | 54
35 | Review all | Đạt Huỳnh | 2020-06-08 | 2020-06-13 | 5 | Đã hoàn thành | 45 | Cao | 32
36 | View message birthday | Quang Vương | 2020-04-06 | 2020-04-11 | 5 | Đã hoàn thành | 45 | Cao | 44.5
37 | Play music happy birthday for android | Quang Vương | 2020-04-13 | 2020-04-18 | 5 | Đã hoàn thành | 45 | Cao | 45
38 | View data result business week for personal | Quang Vương | 2020-04-20 | 2020-04-25 | 5 | Đã hoàn thành | 45 | Cao | 45
39 | Show time of week result | Quang Vương | 2020-04-27 | 2020-05-02 | 5 | Đã hoàn thành | 45 | Cao | 33
40 | Update map with sattelite and standard mode | Quang Vương | 2020-05-04 | 2020-05-09 | 5 | Đã hoàn thành | 45 | Cao | 44.5
41 | View data result business week for personal | Quang Vương | 2020-05-11 | 2020-05-16 | 5 | Đã hoàn thành | 45 | Cao | 47
42 | View data result business week for team | Quang Vương | 2020-05-18 | 2020-05-23 | 5 | Đã hoàn thành | 45 | Cao | 45
43 | View sale result chart group | Quang Vương | 2020-05-25 | 2020-05-30 | 5 | Đã hoàn thành | 45 | Cao | 48
44 | View compare chart group | Quang Vương | 2020-06-01 | 2020-06-06 | 5 | Đã hoàn thành | 45 | Cao | 47
45 | Review all | Quang Vương | 2020-06-08 | 2020-06-13 | 5 | Đã hoàn thành | 45 | Cao | 34
46 | Code Front-end add, edit, view room | Anh Minh | 2020-04-02 | 2020-04-11 | 9 | Đã hoàn thành | 45 | Cao | 51
47 | Code Front-end edit, view room | Anh Minh | 2020-04-13 | 2020-04-18 | 5 | Đã hoàn thành | 45 | Cao | 37
48 | Code back-end add room | Anh Minh | 2020-04-20 | 2020-04-25 | 5 | Đã hoàn thành | 45 | Cao | 36
49 | Code back-end edit, view room | Anh Minh | 2020-04-27 | 2020-05-02 | 5 | Đã hoàn thành | 45 | Medium | 35
50 | Code back-end add team, front-end import | Anh Minh | 2020-05-04 | 2020-05-09 | 5 | Đã hoàn thành | 45 | Medium | 33
51 | Code back-end import sale user | Anh Minh | 2020-05-11 | 2020-05-16 | 5 | Đã hoàn thành | 45 | Medium | 41
52 | Code back-end import sale room | Anh Minh | 2020-05-18 | 2020-05-23 | 5 | Đã hoàn thành | 45 | Medium | 44
53 | Code back-end export sale user | Anh Minh | 2020-05-25 | 2020-05-30 | 5 | Đã hoàn thành | 45 | Medium | 44
54 | Code back-end export sale room | Anh Minh | 2020-06-01 | 2020-06-06 | 5 | Đã hoàn thành | 45 | Medium | 44
55 | Review all | Anh Minh | 2020-06-08 | 2020-06-13 | 5 | Đã hoàn thành | 45 | Medium | 35
56 | Test View business results the week "Employees" app | Như Phương | 2020-04-01 | 2020-04-03 | 2 | Đã hoàn thành | 18 | Cao | 10
57 | Test View details of the weekly business results the "Employees" app | Như Phương | 2020-04-06 | 2020-04-08 | 2 | Đã hoàn thành | 18 | Cao | 8
58 | Test View business results the week "Team" app | Như Phương | 2020-04-09 | 2020-04-11 | 2 | Đã hoàn thành | 9 | Cao | 8
59 | Test View business results the week "Room" app | Như Phương | 2020-04-13 | 2020-04-14 | 1 | Đã hoàn thành | 9 | Cao | 8
60 | Test View business results graph "Employees" app | Như Phương | 2020-04-16 | 2020-04-17 | 1 | Đã hoàn thành | 9 | Cao | 8
61 | Test Search business results graph "Employees" app | Như Phương | 2020-04-20 | 2020-04-22 | 2 | Đã hoàn thành | 18 | Cao | 10
62 | Test View the "Team" business results graph app | Như Phương | 2020-04-23 | 2020-04-25 | 2 | Đã hoàn thành | 18 | Cao | 8
63 | Test Search results graph "Team" app | Như Phương | 2020-04-27 | 2020-04-28 | 1 | Đã hoàn thành | 9 | Cao | 9
64 | Test View business results graph "Rooms" app | Như Phương | 2020-04-29 | 2020-05-01 | 2 | Đã hoàn thành | 18 | Cao | 8
65 | Test Search business results graph "Room" app | Như Phương | 2020-05-04 | 2020-05-06 | 2 | Đã hoàn thành | 18 | Cao | 7
66 | Test View compare business results "Employees" | Như Phương | 2020-05-07 | 2020-05-09 | 2 | Đã hoàn thành | 18 | Cao | 8
67 | Test Search and compare business results "Employees" app | Như Phương | 2020-05-11 | 2020-05-13 | 2 | Đã hoàn thành | 18 | Cao | 10
68 | Test View the business results "Team" app | Như Phương | 2020-05-14 | 2020-05-16 | 2 | Đã hoàn thành | 18 | Cao | 10
69 | Test Search and compare business results "Team" app | Như Phương | 2020-05-18 | 2020-05-20 | 2 | Đã hoàn thành | 18 | Cao | 12
70 | Test View compare business results "Rooms" app | Như Phương | 2020-05-21 | 2020-05-23 | 2 | Đã hoàn thành | 18 | Cao | 10
71 | Test Search and compare business results "Rooms" app | Như Phương | 2020-05-25 | 2020-05-27 | 2 | Đã hoàn thành | 18 | Cao | 10
72 | Test "View Room" Website | Như Phương | 2020-05-28 | 2020-05-29 | 1 | Đã hoàn thành | 9 | Cao | 12
73 | Test Import file website | Như Phương | 2020-05-30 | 2020-05-31 | 1 | Đã hoàn thành | 9 | Cao | 13
74 | Test View personal information app | Như Phương | 2020-06-01 | 2020-06-02 | 1 | Đã hoàn thành | 9 | Cao | 8
75 | Test Template excel website | Như Phương | 2020-06-02 | 2020-06-03 | 1 | Đã hoàn thành | 8 | Medium | 10
76 | Test "Add Room" Website | Như Phương | 2020-06-04 | 2020-06-06 | 2 | Đã hoàn thành | 16 | Medium | 10
77 | Test "Edit Room" Website | Như Phương | 2020-06-08 | 2020-06-10 | 2 | Đã hoàn thành | 16 | Medium | 8
78 | Test "Delete Room" Website | Như Phương | 2020-06-11 | 2020-06-13 | 2 | Đã hoàn thành | 16 | Medium | 7
79 | Test View happy birthday app | Như Phương | 2020-06-14 | 2020-06-15 | 1 | Đã hoàn thành | 7 | Low | 8
Kết thúc planning, analysing & training |  |  | 2020-04-01 | 2020-06-15 | 233 |  | 2047 |  | 1909
| Phần trăm hoàn thành |  |  | Thời gian kế hoạch | Thời gian thực tế | Kết Quả
| Đã hoàn thành | 100% |  | 2047 | 1909 | 138
| Quá hạn | 0% |  | Kiểm soát được kết hoach tốt
| Đang thực hiện | 0%
| Chưa thực hiện | 0%
| Ngân sách |  |  | Mức độ | Thời gian (giờ) | Chú thích
| Theo kế hoạch |  |  | High | 500-1000 | Trễ tiến độ so với lịch trình nghiêm trọng cần cải cách
| Theo thực tế |  |  | Medium | 250-500 | Kiểm soát lịch trình cần làm tốt hơn
|  |  |  | Low | ~250 | Bám sát lịch trình và làm tốt vẫn giữ trạng thái tích cực
Cơ cấu công việc
| Đạt Huỳnh | 10 |  | Mức độ | Thời gian (giờ) | Chú thích
| Quốc Nhân | 25 |  | Good | Kết hoạch > thực tế | Làm dự án tốt hơn so với dự kiến
| Quang Vương | 10 |  | Bad | Kết hoạch < thực tế | Làm dự án tệ và dẫn đến kết quả xấu
| Anh Minh | 10
| Như Phương | 24 |  | Tổng ngày làm dự án (ngày) | Thời gian nghỉ dịch (Covid-19) | Kết quả (ngày)
|  |  |  | 76 | 11 | 65
| Độ ưu tiên | Giờ
| High | 9 |  | Tổng ngày làm dự án kế hoạch (ngày) | Thời gian bù (ngày) | Kết quả (ngày)
| Medium | 8 |  | 56 | 15 | 71
| Low | 7

## Burndown chart
Số tuần | Ngày | Tháng | Số công việc | ID
1 | 1 | 4 | 79 | 1
| 2 |  | 78 | 2
| 3 |  | 77 | 3
| 4 |  | 76 | 4
| 5 |  | 75 | 5
| 6 |  | 74 | 6
2 | 7 |  | 73 | 7
| 8 |  | 72 | 8
| 9 |  | 71 | 9
| 10 |  | 70 | 10
| 11 |  | 69 | 11
| 12 |  | 68 | 12
3 | 13 |  | 67 | 13
| 14 |  | 66 | 14
| 15 |  | 65 | 15
| 16 |  | 64 | 16
| 17 |  | 63 | 17
| 18 |  | 62 | 18
4 | 19 |  | 61 | 19
| 20 |  | 60 | 20
| 21 |  | 59 | 21
| 22 |  | 58 | 22
| 23 |  | 57 | 23
| 24 |  | 56 | 24
5 | 25 |  | 55 | 25
| 26 |  | 54 | 26
| 27 |  | 53 | 27
| 28 |  | 52 | 28
| 29 |  | 51 | 29
| 30 |  | 50 | 30
6 | 1 | 5 | 49 | 31
| 2 |  | 48 | 32
| 3 |  | 47 | 33
| 4 |  | 46 | 34
| 5 |  | 45 | 35
| 6 |  | 44 | 36
7 | 7 |  | 43 | 37
| 8 |  | 42 | 38
| 9 |  | 41 | 39
| 10 |  | 40 | 40
| 11 |  | 39 | 41
| 12 |  | 38 | 42
| 13 |  | 37 | 43
8 | 14 |  | 36 | 44
| 15 |  | 35 | 45
| 16 |  | 34 | 46
| 17 |  | 33 | 47
| 18 |  | 32 | 48
| 19 |  | 31 | 49
| 20 |  | 30 | 50
| 21 |  | 29 | 51
| 22 |  | 28 | 52
9 | 23 |  | 27 | 53
| 24 |  | 26 | 54
| 25 |  | 25 | 55
| 26 |  | 24 | 56
| 27 |  | 23 | 57
| 28 |  | 22 | 58
| 29 |  | 21 | 59
| 30 |  | 20 | 60
10 | 31 |  | 19 | 61
| 1 | 6 | 18 | 62
| 2 |  | 17 | 63
| 3 |  | 16 | 64
| 4 |  | 15 | 65
| 5 |  | 14 | 66
| 6 |  | 13 | 67
| 7 |  | 12 | 68
| 8 |  | 10 | 69
11 | 9 |  | 8 | 70
| 10 |  | 6 | 71
| 11 |  | 4 | 72
| 12 |  | 3 | 73
| 13 |  | 2 | 74
| 14 |  | 1 | 75
| 15 |  | 0 | 76