## Cover Page
GUI & FUNCTIONAL TEST CASES
for BDS
Document History – To maintain a list of changes being made
Version | Date | Author | Description of Changes
1.0 | 2020-04-12 | Trịnh như Phương | Initial Draft
1.1 | 2020-05-28 | Trịnh như Phương | Issue official
1.2 | 2020-06-08 | Trịnh như Phương | Complete version
1.3 | 2020-06-13 | Tean | review
This document has been generated from template ST-FunctionalTestCase-Template, version 1.1
Reference Documents – Clearly mark the document used as an input to create the test case
Version | Date | Document Name

## Test Requirements
General Information
Project |  | Real estate company management |  | Module | View Web Department
Test Designed By |  | Trịnh Như Phương |  | Reviewed By
Test Designed Date |  | 2019-08-08 |  | Reviewed Date | 13/06/2020
List of Test Requirements
No. | Test Requirement ID | Requirement Reference Document Index | Test Requirement Description | Test Type | Importance | Status | Note
1 | TR-BDS-XPB-1 | GUI | Display list of departments and groups including: department name, group name, button | LooknFeel | High
2 | TR-BDS-XPB-2 | GUI | Display the "Thêm phòng " button above the list | LooknFeel | High
3 | TR-BDS-XPB-3 | GUI | Display the "Edit" "delete" button in the bottom column of the list | LooknFeel | Medium
4 | TR-BDS-XPB-4 | GUI | may display with 0.1 or more groups in the same row as the department information field | LooknFeel | Medium
5 | TR-BDS-XPB-5 | GUI | Information fields are sorted by department name order from AZ | LooknFeel | Low
6 | TR-BDS-XPB-6 | GUI | The group information field can display data or not | LooknFeel | Low
7 | TR-BDS-XPB-7 | GUI | Display the " xuất file " button above the list | LooknFeel | Low
4 | TR-BDS-XPB-8 | GUI | the system automatically downloads excel file "Department list" when the user presses the "export file" button | Positive | Medium

## Test Cases
Test Cases for '' View departments "
No. | Test Requirement ID | Test Case ID | Test Objective | Pre-conditions |  | Step Action | Test Data | Expected Result | status
Look and Feel (GUI) TCs
1 | TR-BDS-XPB-1 | TRCBDS-XPB-1 | Check 'Show list of departments and groups including: department name, group name, button | Have an Admin account to log in to WebAdmin | 1 | Admin login to WebAdmin Real Estate with admin account |  | Shows the homepage interface | pass
[5 empty] | 2 | On the home page, click the "Information" |  | Display 3 items Company policies, Departments, organizational chart
[5 empty] | 3 | Select "Department" |  | Display list of departments and groups including: department name, group name, button
2 | TR-BDS-XPB-2 | TRCBDS-XPB-2 | Check the 'Show more departments' button above the list | Have an Admin account to log in to WebAdmin | 1 | Admin login to WebAdmin Real Estate with admin account |  | Shows the homepage interface | pass
[5 empty] | 2 | On the home page, click the "Information" |  | Display 3 items Company policies, Departments, organizational chart
[5 empty] | 3 | Select "Department" |  | Display the "Add department" button above the list
3 | TR-BDS-XPB-3 | TRCBDS-XPB-3 | Check the Show "Edit" "delete" button at the bottom of the " | Have an Admin account to log in to WebAdmin | 1 | Admin login to WebAdmin Real Estate with admin account |  | Shows the homepage interface | pass
[5 empty] | 2 | On the home page, click the "Information" |  | Display 3 items Company policies, Departments, organizational chart
[5 empty] | 3 | Select "Department" |  | Display the "Edit" "delete" button in the bottom column of the list "
4 | TR-BDS-XPB-4 | TRCBDS-XPB-4 | Tests may display consisting of 0.1 or more groups in the same row as the department information field | Have an Admin account to log in to WebAdmin | 1 | Admin login to WebAdmin Real Estate with admin account |  | Shows the homepage interface | pass
[5 empty] | 2 | On the home page, click the "Information" |  | Display 3 items Company policies, Departments, organizational chart
[5 empty] | 3 | Select "Department" |  | may display with 0.1 or more groups in the same row as the department information field
5 | TR-BDS-XPB-5 | TRCBDS-XPB-5 | Check Information field sorted by department name order from AZ | Have an Admin account to log in to WebAdmin | 1 | Admin login to WebAdmin Real Estate with admin account |  | Shows the homepage interface | pass
[5 empty] | 2 | On the home page, click the "Information" |  | Display 3 items Company policies, Departments, organizational chart
[5 empty] | 3 | Select "Department" |  | Information fields are sorted by department name order from AZ
6 | TR-BDS-XPB-6 | TRCBDS-XPB-6 | Check whether the Group Information field may display or not | Have an Admin account to log in to WebAdmin | 1 | Admin login to WebAdmin Real Estate with admin account |  | Shows the homepage interface | pass
[5 empty] | 2 | On the home page, click the "Information" |  | Display 3 items Company policies, Departments, organizational chart
[5 empty] | 3 | Select "Department" |  | Display The group information field may or may not be displayed
6 | TR-BDS-XPB-7 | TRCBDS-XPB-7 | Display the " xuất file " button above the list | Have an Admin account to log in to WebAdmin | 1 | Admin login to WebAdmin Real Estate with admin account |  | Shows the homepage interface | pass
[5 empty] | 2 | On the home page, click the "Information" |  | Display 3 items Company policies, Departments, organizational chart
[5 empty] | 3 | Select "Department" |  | Display The group information field may or may not be displayed
Funciton TCs
21 | TR-BDS-XTTTK-8 | TC-BDS-XTTTK-8 | the system automatically downloads excel file "Department list" when the user presses the "export file" button | Have an Admin account to log in to WebAdmin | 1 | On the home page, click the "Information Management" |  | Shows the homepage interface | pass
[5 empty] | 2 | On the home page, click the "Information" |  | display the "export file" button above the account list and the same row as the "add, lock, activate" buttons
[5 empty] | 3 | Select "Department" |  | Display The group information field may or may not be displayed
[5 empty] | 4 | press the "export file" button |  | the system automatically downloads excel file "Department list" when the user presses the "export file" button

## Sheet2 (hidden)
Priority | Status | Type
High | Not Executed | LooknFeel
Medium | Passed | Positive
Low | Failed | Negative
Boundary