## Revision History
Schedule Module 2 BDS Project
| Project Name: | BDS Project
| Team: | Team 03 - Hello World
| Document: | Schedule module 2
| Creator: | Nhan Pham
| Created Date: | 2019-02-12
Revision History
| Version | Date | Author | Content
| Version 1.0 | 2019-02-12 | Nhan Pham | Create schedule module 2

## Dữ liệu dự án
Bảng công việc
ID | Nội dung công việc | Người phụ trách | Ngày bắt đầu | Ngày kết thúc | Số ngày (ngày) | Tình trạng | Số giờ hoàn thành công việc kế hoạch (Giờ) | Mức độ ưu tiên | Số giờ hoàn thành công việc cá nhân (Giờ)
1 | Design prototype, sequence, use case description "View all project listings" app | Quốc Nhân | 2020-03-09 | 2020-03-11 | 2 | Đã hoàn thành | 20 | Cao | 22
2 | Design prototype, sequence, use case description "View all project listings being implemented" app | Quốc Nhân | 2020-03-12 | 2020-03-14 | 2 | Đã hoàn thành | 20 | Cao | 19
3 | Design prototype, sequence, use case description "View all project listings prepare to deploy" app | Quốc Nhân | 2020-03-16 | 2020-03-17 | 1 | Đã hoàn thành | 10 | Cao | 16 | Formula
4 | Design prototype, sequence, use case description "View all project listings has deployed" app | Quốc Nhân | 2020-03-18 | 2020-03-19 | 1 | Đã hoàn thành | 10 | Cao | 19 | Số giờ hoàn thành công việc cá nhân = Thời gian cồng việc + Số công việc đã làm (cập nhật time log)
5 | Design prototype, sequence, use case description "View all project listings" website | Quốc Nhân | 2020-03-20 | 2020-03-21 | 1 | Đã hoàn thành | 10 | Cao | 16
6 | Design prototype, sequence, use case description "Add projects" website | Quốc Nhân | 2020-03-23 | 2020-03-25 | 2 | Đã hoàn thành | 20 | Cao | 27
7 | Design prototype, sequence, use case description "Edit projects" website | Quốc Nhân | 2020-03-26 | 2020-03-28 | 2 | Đã hoàn thành | 20 | Cao | 22
8 | Design messages list module 2 | Quốc Nhân | 2020-03-10 | 2020-03-14 | 4 | Đã hoàn thành | 28 | Cao | 23
9 | Design business rule module 2 | Quốc Nhân | 2020-03-30 | 2020-04-01 | 2 | Đã hoàn thành | 20 | Cao | 15
10 | Design use case diagram module 2 | Quốc Nhân | 2020-04-02 | 2020-04-04 | 2 | Đã hoàn thành | 20 | Cao | 19
11 | Reseach Map view and layout project | Đạt Huỳnh | 2020-03-02 | 2020-03-07 | 6 | Đã hoàn thành | 34 | Cao | 34
12 | handle data project | Đạt Huỳnh | 2020-03-09 | 2020-03-14 | 6 | Đã hoàn thành | 34 | Cao | 44
13 | Coding layout report team | Đạt Huỳnh | 2020-03-16 | 2020-03-21 | 6 | Đã hoàn thành | 34 | Cao | 39
14 | Coding layout report group, research vuejs, location api | Đạt Huỳnh | 2020-03-23 | 2020-03-28 | 6 | Đã hoàn thành | 34 | Cao | 39
15 | Reseach Map view and config | Quang Vương | 2020-03-02 | 2020-03-07 | 6 | Đã hoàn thành | 34 | Cao | 31.5
16 | Searching how to get location and upload image for project | Quang Vương | 2020-03-09 | 2020-03-14 | 6 | Đã hoàn thành | 33 | Cao | 31
17 | handle data project | Quang Vương | 2020-03-16 | 2020-03-21 | 6 | Đã hoàn thành | 33 | Cao | 33.5
18 | get data location and marker | Quang Vương | 2020-03-23 | 2020-03-28 | 6 | Đã hoàn thành | 33 | Cao | 32
19 | Code Front-end "Add project" website | Anh Minh | 2020-03-09 | 2020-03-12 | 4 | Đã hoàn thành | 21 | Cao | 21
20 | Code Front-end "Edit project" website | Anh Minh | 2020-03-13 | 2020-03-14 | 2 | Đã hoàn thành | 12 | Cao | 12
21 | Code Front-end "View all project listings" website | Anh Minh | 2020-03-16 | 2020-03-17 | 2 | Đã hoàn thành | 12 | Cao | 13
22 | Code Back-end "Add project" website | Anh Minh | 2020-03-19 | 2020-03-24 | 6 | Đã hoàn thành | 29 | Cao | 36
23 | Code Back-end "Add project (funciton add image)" website | Anh Minh | 2020-03-26 | 2020-03-26 | 1 | Đã hoàn thành | 5 | Cao | 5
24 | Code Back-end "Edit projects" website | Anh Minh | 2020-03-27 | 2020-03-27 | 1 | Đã hoàn thành | 7 | Cao | 7
25 | Code Back-end "View account information" website | Anh Minh | 2020-03-30 | 2020-03-31 | 2 | Đã hoàn thành | 12 | Cao | 12
22 | Test "View all project listings" app | Như Phương | 2020-03-09 | 2020-03-11 | 2 | Đã hoàn thành | 20 | Cao
23 | Test "View all project listings being implemented" app | Như Phương | 2020-03-12 | 2020-03-13 | 1 | Đã hoàn thành | 10 | Cao
24 | Test "View all project listings prepare to deploy" app | Như Phương | 2020-03-16 | 2020-03-18 | 2 | Đã hoàn thành | 20 | Cao
25 | Test "View all project listings has deployed" app | Như Phương | 2020-03-19 | 2020-03-20 | 1 | Đã hoàn thành | 10 | Cao
26 | Test "View all project listings" website | Như Phương | 2020-03-23 | 2020-03-25 | 2 | Đã hoàn thành | 20 | Cao
27 | Test "Add projects" website | Như Phương | 2020-03-26 | 2020-03-28 | 2 | Đã hoàn thành | 20 | Cao
28 | Test "Edit projects" website | Như Phương | 2020-03-30 | 2020-04-01 | 2 | Đã hoàn thành | 20 | Cao
Kết thúc module 2 |  |  |  |  | 97 |  | 665 |  | 588
Phần trăm hoàn thành
| Đã hoàn thành | 0%
| Quá hạn | 33%
| Đang thực hiện | 21%
| Chưa thực hiện | 46%
Ngân sách
Theo kế hoạch
Theo thực tế
Cơ cấu công việc
| Đạt Huỳnh | 4
| Quốc Nhân | 10
| Quang Vương | 4
| Anh Minh | 3
| Như Phương | 7