## Revision History
Schedule Module 3 BDS Project
| Project Name: | BDS Project
| Team: | Team 03 - Hello World
| Document: | Schedule module 3
| Creator: | Nhan Pham
| Created Date: | 2019-04-01
Revision History
| Version | Date | Author | Content
| Version 1.0 | 2019-04-01 | Nhan Pham | Create schedule module 3

## Dữ liệu dự án
Bảng công việc
ID | Nội dung công việc | Người phụ trách | Ngày bắt đầu | Ngày kết thúc | Số ngày (ngày) | Tình trạng | Số giờ hoàn thành công việc kế hoạch (Giờ) | Mức độ ưu tiên | Số giờ hoàn thành công việc cá nhân (Giờ)
1 | Design prototype, sequence, use case description View business results the week "Employees" app, Edit "Team & Room" Website | Quốc Nhân | 2020-04-06 | 2020-04-08 | 2 | Đã hoàn thành | 18 | Cao | 16
2 | Design prototype, sequence, use case description View details of the weekly business results the "Employees" app, Add "Team & Room" Website | Quốc Nhân | 2020-04-09 | 2020-04-10 | 1 | Đã hoàn thành | 9 | Cao | 16
3 | Design prototype, sequence, use case description View business results the week "Team" app | Quốc Nhân | 2020-04-11 | 2020-04-13 | 2 | Đã hoàn thành | 18 | Cao | 22
4 | Design prototype, sequence, use case description View business results the week "Room" app | Quốc Nhân | 2020-04-14 | 2020-04-16 | 2 | Đã hoàn thành | 18 | Cao | 15
5 | Design prototype, sequence, use case description View business results graph "Employees" app, Delete "Team & Room" Website | Quốc Nhân | 2020-04-17 | 2020-04-20 | 3 | Đã hoàn thành | 27 | Cao | 22
6 | Design prototype, sequence, use case description Search business results graph "Employees" app | Quốc Nhân | 2020-04-20 | 2020-04-22 | 2 | Đã hoàn thành | 18 | Cao | 16
7 | Design prototype, sequence, use case description View the "Team" business results graph app | Quốc Nhân | 2020-04-23 | 2020-04-25 | 2 | Đã hoàn thành | 18 | Cao | 18
8 | Design prototype, sequence, use case description Search results graph "Team" app | Quốc Nhân | 2020-04-27 | 2020-04-28 | 1 | Đã hoàn thành | 9 | Cao | 15
9 | Design prototype, sequence, use case description View business results graph "Rooms" app | Quốc Nhân | 2020-04-28 | 2020-04-29 | 1 | Đã hoàn thành | 9 | Cao | 14
10 | Design prototype, sequence, use case description Search business results graph "Room" app | Quốc Nhân | 2020-04-30 | 2020-05-01 | 1 | Đã hoàn thành | 9 | Cao | 11
11 | Design prototype, sequence, use case description View compare business results "Employees" | Quốc Nhân | 2020-05-04 | 2020-05-06 | 2 | Đã hoàn thành | 18 | Cao | 10
12 | Design prototype, sequence, use case description Search compare business results "Employees" app | Quốc Nhân | 2020-05-07 | 2020-05-09 | 2 | Đã hoàn thành | 18 | Cao | 18
13 | Design prototype, sequence, use case description View the business results "Team" app | Quốc Nhân | 2020-05-11 | 2020-05-13 | 2 | Đã hoàn thành | 18 | Cao | 14
14 | Design prototype, sequence, use case description Search compare business results "Team" app | Quốc Nhân | 2020-05-14 | 2020-05-16 | 2 | Đã hoàn thành | 18 | Cao | 23
15 | Design prototype, sequence, use case description View compare business results "Rooms" app | Quốc Nhân | 2020-05-18 | 2020-05-20 | 2 | Đã hoàn thành | 18 | Cao | 16
16 | Design prototype, sequence, use case description Search compare business results "Rooms" app | Quốc Nhân | 2020-05-21 | 2020-05-22 | 1 | Đã hoàn thành | 9 | Cao | 23
17 | Design prototype, sequence, use case description View statistic - report website | Quốc Nhân | 2020-05-25 | 2020-05-26 | 1 | Đã hoàn thành | 9 | Cao | 15
18 | Design prototype, sequence, use case description Import file website | Quốc Nhân | 2020-05-27 | 2020-05-28 | 1 | Đã hoàn thành | 9 | Cao | 16
19 | Design prototype, sequence, use case description View personal information app | Quốc Nhân | 2020-06-01 | 2020-06-03 | 2 | Đã hoàn thành | 18 | Cao | 16
20 | Design messages list module 3 | Quốc Nhân | 2020-06-04 | 2020-06-06 | 2 | Đã hoàn thành | 18 | Cao | 21
21 | Design business rule module 3 | Quốc Nhân | 2020-06-08 | 2020-06-10 | 2 | Đã hoàn thành | 18 | Cao | 24
22 | Design use case diagram module 3 | Quốc Nhân | 2020-06-11 | 2020-06-13 | 2 | Đã hoàn thành | 18 | Cao | 20
23 | Code Front-end View business results the week "Employees" app and "View personal information" app | Đạt Huỳnh | 2020-04-01 | 2020-04-03 | 2 |  | 18 | Cao
24 | Code Front-end View details of the weekly business results the "Employees" app | Đạt Huỳnh | 2020-04-06 | 2020-04-08 | 2 |  | 18 | Cao
25 | Code Front-end View business results the week "Team" app | Đạt Huỳnh | 2020-04-09 | 2020-04-11 | 2 |  | 18 | Cao
26 | Code Front-end View business results the week "Room" app | Đạt Huỳnh | 2020-04-13 | 2020-04-14 | 1 |  | 9 | Cao
27 | Code Front-end View business results graph "Employees" app | Đạt Huỳnh | 2020-04-16 | 2020-04-17 | 1 |  | 9 | Cao
28 | Code Front-end Search business results graph "Employees" app | Đạt Huỳnh | 2020-04-20 | 2020-04-22 | 2 |  | 18 | Cao
29 | Code Front-end View the "Team" business results graph app | Đạt Huỳnh | 2020-04-23 | 2020-04-25 | 2 |  | 18 | Cao
30 | Code Front-end Search results graph "Team" app | Đạt Huỳnh | 2020-04-27 | 2020-04-28 | 1 |  | 9 | Cao
31 | Code Front-end View business results graph "Rooms" app | Đạt Huỳnh | 2020-04-29 | 2020-05-01 | 2 |  | 18 | Cao
32 | Code Front-end Search business results graph "Room" app | Đạt Huỳnh | 2020-05-04 | 2020-05-06 | 2 |  | 18 | Cao
33 | Code Front-end View compare business results "Employees" | Đạt Huỳnh | 2020-05-07 | 2020-05-09 | 2 |  | 18 | Cao
34 | Code Front-end Search and compare business results "Employees" app | Đạt Huỳnh | 2020-05-11 | 2020-05-13 | 2 |  | 18 | Cao
35 | Code Front-end View the business results "Team" app | Đạt Huỳnh | 2020-05-14 | 2020-05-16 | 2 |  | 18 | Cao
36 | Code Front-end Search and compare business results "Team" app | Đạt Huỳnh | 2020-05-18 | 2020-05-20 | 2 |  | 18 | Cao
37 | Code Front-end View compare business results "Rooms" app | Đạt Huỳnh | 2020-05-21 | 2020-05-23 | 2 |  | 18 | Cao
38 | Code Front-end Search and compare business results "Rooms" app | Đạt Huỳnh | 2020-05-25 | 2020-05-27 | 2 |  | 18 | Cao
39 | Code Front-end View personal information app | Đạt Huỳnh | 2020-05-28 | 2020-05-30 | 2 |  | 18 | Cao
40 | Code Back-end View business results the week "Employees" app | Quang Vương | 2020-04-01 | 2020-04-03 | 2 |  | 18 | Cao
41 | Code Back-end View details of the weekly business results the "Employees" app | Quang Vương | 2020-04-06 | 2020-04-08 | 2 |  | 18 | Cao
42 | Code Back-end View business results the week "Team" app | Quang Vương | 2020-04-09 | 2020-04-11 | 2 |  | 18 | Cao
43 | Code Back-end View business results the week "Room" app | Quang Vương | 2020-04-13 | 2020-04-14 | 1 |  | 9 | Cao
44 | Code Back-end View business results graph "Employees" app | Quang Vương | 2020-04-16 | 2020-04-17 | 1 |  | 9 | Cao
45 | Code Back-end Search business results graph "Employees" app | Quang Vương | 2020-04-20 | 2020-04-22 | 2 |  | 18 | Cao
46 | Code Back-end View the "Team" business results graph app | Quang Vương | 2020-04-23 | 2020-04-25 | 2 |  | 18 | Cao
47 | Code Back-end Search results graph "Team" app | Quang Vương | 2020-04-27 | 2020-04-28 | 1 |  | 9 | Cao
48 | Code Back-end View business results graph "Rooms" app | Quang Vương | 2020-04-29 | 2020-05-01 | 2 |  | 18 | Cao
49 | Code Back-end Search business results graph "Room" app | Quang Vương | 2020-05-04 | 2020-05-06 | 2 |  | 18 | Cao
50 | Code Back-end View compare business results "Employees" | Quang Vương | 2020-05-07 | 2020-05-09 | 2 |  | 18 | Cao
51 | Code Back-end Search and compare business results "Employees" app | Quang Vương | 2020-05-11 | 2020-05-13 | 2 |  | 18 | Cao
52 | Code Back-end View the business results "Team" app | Quang Vương | 2020-05-14 | 2020-05-16 | 2 |  | 18 | Cao
53 | Code Back-end Search and compare business results "Team" app | Quang Vương | 2020-05-18 | 2020-05-20 | 2 |  | 18 | Cao
54 | Code Back-end View compare business results "Rooms" app | Quang Vương | 2020-05-21 | 2020-05-23 | 2 |  | 18 | Cao
55 | Code Back-end Search and compare business results "Rooms" app | Quang Vương | 2020-05-25 | 2020-05-27 | 2 |  | 18 | Cao
56 | Code Back-end View personal information app | Quang Vương | 2020-05-28 | 2020-05-30 | 2 |  | 18 | Cao
57 | Code Front-end, back-end "Forgot password" website | Anh Minh | 2020-04-01 | 2020-04-10 | 9 |  | 81 | Cao
58 | Code Front-end, back-end View statistic - report website | Anh Minh | 2020-04-13 | 2020-04-24 | 11 |  | 99 | Cao
59 | Code Front-end, back-end Import file website | Anh Minh | 2020-04-27 | 2020-05-08 | 11 |  | 99 | Cao
60 | Code Front-end, back-end Export file website | Anh Minh | 2020-05-09 | 2020-05-16 | 7 |  | 63 | Cao
61 | Code Front-end, back-end Add "Team & Room" Website | Anh Minh | 2020-05-18 | 2020-05-24 | 6 |  | 48 | Medium
62 | Code Front-end, back-end Edit "Team & Room" Website | Anh Minh | 2020-05-25 | 2020-05-31 | 6 |  | 48 | Medium
63 | Code Front-end, back-end Delete "Team & Room" Website | Anh Minh | 2020-06-01 | 2020-06-10 | 9 |  | 72 | Medium
64 | Test View business results the week "Employees" app | Như Phương | 2020-04-01 | 2020-04-03 | 2 | Đã hoàn thành | 18 | Cao
65 | Test View details of the weekly business results the "Employees" app | Như Phương | 2020-04-06 | 2020-04-08 | 2 | Đã hoàn thành | 18 | Cao
66 | Test View business results the week "Team" app | Như Phương | 2020-04-09 | 2020-04-11 | 2 | Đã hoàn thành | 9 | Cao
67 | Test View business results the week "Room" app | Như Phương | 2020-04-13 | 2020-04-14 | 1 | Đã hoàn thành | 9 | Cao
68 | Test View business results graph "Employees" app | Như Phương | 2020-04-16 | 2020-04-17 | 1 | Đã hoàn thành | 9 | Cao
69 | Test Search business results graph "Employees" app | Như Phương | 2020-04-20 | 2020-04-22 | 2 | Đã hoàn thành | 18 | Cao
70 | Test View the "Team" business results graph app | Như Phương | 2020-04-23 | 2020-04-25 | 2 | Đã hoàn thành | 18 | Cao
71 | Test Search results graph "Team" app | Như Phương | 2020-04-27 | 2020-04-28 | 1 | Đã hoàn thành | 9 | Cao
72 | Test View business results graph "Rooms" app | Như Phương | 2020-04-29 | 2020-05-01 | 2 | Đã hoàn thành | 18 | Cao
73 | Test Search business results graph "Room" app | Như Phương | 2020-05-04 | 2020-05-06 | 2 | Đã hoàn thành | 18 | Cao
74 | Test View compare business results "Employees" | Như Phương | 2020-05-07 | 2020-05-09 | 2 | Đã hoàn thành | 18 | Cao
75 | Test Search and compare business results "Employees" app | Như Phương | 2020-05-11 | 2020-05-13 | 2 | Đã hoàn thành | 18 | Cao
76 | Test View the business results "Team" app | Như Phương | 2020-05-14 | 2020-05-16 | 2 | Đã hoàn thành | 18 | Cao
77 | Test Search and compare business results "Team" app | Như Phương | 2020-05-18 | 2020-05-20 | 2 | Đã hoàn thành | 18 | Cao
78 | Test View compare business results "Rooms" app | Như Phương | 2020-05-21 | 2020-05-23 | 2 | Đã hoàn thành | 18 | Cao
79 | Test Search and compare business results "Rooms" app | Như Phương | 2020-05-25 | 2020-05-27 | 2 | Đã hoàn thành | 18 | Cao
80 | Test View business results View statistic - report | Như Phương | 2020-05-28 | 2020-05-29 | 1 | Đã hoàn thành | 9 | Cao
81 | Test Import file website | Như Phương | 2020-05-30 | 2020-05-31 | 1 | Đã hoàn thành | 9 | Cao
82 | Test View personal information app and "Forgot password" website | Như Phương | 2020-06-01 | 2020-06-02 | 1 | Đã hoàn thành | 9 | Cao
83 | Test Export file website | Như Phương | 2020-06-02 | 2020-06-03 | 1 |  | 9
84 | Test Add "Team & Room" Website | Như Phương | 2020-06-04 | 2020-06-06 | 2 |  | 18
85 | Test Edit "Team & Room" Website | Như Phương | 2020-06-08 | 2020-06-10 | 2 |  | 18 | Cao
86 | Test Delete "Team & Room" Website | Như Phương | 2020-06-11 | 2020-06-13 | 2 |  | 18 | Cao
Kết thúc planning, analysing & training |  |  |  |  | 198 |  | 1752 |  | 381
Phần trăm hoàn thành
| Đã hoàn thành | 0%
| Quá hạn | 0%
| Đang thực hiện | 0%
| Chưa thực hiện | 0%
Ngân sách
Theo kế hoạch
Theo thực tế
Cơ cấu công việc
| Đạt Huỳnh | 6
| Quốc Nhân | 21
| Quang Vương | 6
| Anh Minh | 11
| Như Phương | 17