## Revision History
Schedule Module 4 BDS Project
| Project Name: | BDS Project
| Team: | Team 03 - Hello World
| Document: | Schedule module 4
| Creator: | Nhan Pham
| Created Date: | 2019-04-04
Revision History
| Version | Date | Author | Content
| Version 1.0 | 2019-04-04 | Nhan Pham | Create schedule module 4

## Dữ liệu dự án
Bảng công việc
Nội dung công việc | Người phụ trách | Ngày bắt đầu | Ngày kết thúc | Số ngày (ngày) | Tình trạng | Số giờ hoàn thành công việc kế hoạch (Giờ) | Mức độ ưu tiên | Số giờ hoàn thành công việc cá nhân (Giờ)
Design prototype, sequence, use case description "Sign up for a business trip" app | Quốc Nhân | 2019-05-13 | 2019-05-14 | 1 |  | 10 | Cao
Design prototype, sequence, use case description "View a business trip" app | Quốc Nhân | 2019-05-14 | 2019-05-15 | 1 |  | 10 | Cao
Design prototype, sequence, use case description "Locate business trip" app | Quốc Nhân | 2019-05-15 | 2019-05-16 | 1 |  | 10 | Cao
Design prototype, sequence, use case description "Browse business trips" app | Quốc Nhân | 2019-05-18 | 2019-05-19 | 1 |  | 10 | Cao
Design prototype, sequence, use case description "Refuse business trip" app | Quốc Nhân | 2019-05-19 | 2019-05-20 | 1 |  | 10 | Cao
Design prototype, sequence, use case description "View the "approving votes" business trip" app | Quốc Nhân | 2019-05-20 | 2019-05-21 | 1 |  | 10 | Cao
Design prototype, sequence, use case description "View details of the business trip" app | Quốc Nhân | 2019-05-21 | 2019-05-22 | 1 |  | 10 | Cao
Design prototype, sequence, use case description "View business trip history" app | Quốc Nhân | 2019-05-22 | 2019-05-23 | 1 |  | 10 | Cao
Design prototype, sequence, use case description "Searching for business trip" app | Quốc Nhân | 2019-05-23 | 2019-05-24 | 1 |  | 10 | Cao
Design messages list module 4 | Quốc Nhân | 2019-05-24 | 2019-05-25 | 1 |  | 15 | Cao
Design business rule module 4 | Quốc Nhân | 2019-05-25 | 2019-05-26 | 1 |  | 15 | Cao
Design use case diagram module 4 | Quốc Nhân | 2019-05-26 | 2019-05-27 | 1 |  | 15 | Cao
Code Front-end "Sign up for a business trip" app | Đạt Huỳnh | 2019-05-06 | 2019-05-07 | 1 |  | 15 | Cao
Code Front-end "View a business trip" app | Đạt Huỳnh | 2019-05-07 | 2019-05-08 | 1 |  | 15 | Cao
Code Front-end "Locate business trip" app | Đạt Huỳnh | 2019-05-08 | 2019-05-09 | 1 |  | 15 | Cao
Code Front-end "Browse business trips" app | Đạt Huỳnh | 2019-05-11 | 2019-05-12 | 1 |  | 15 | Cao
Code Front-end "Refuse business trip" app | Đạt Huỳnh | 2019-05-12 | 2019-05-13 | 1 |  | 15 | Cao
Code Front-end "View the "approving votes" business trip" app | Đạt Huỳnh | 2019-05-13 | 2019-05-15 | 2 |  | 20 | Cao
Code Front-end "View details of the business trip" app | Đạt Huỳnh | 2019-05-18 | 2019-05-20 | 2 |  | 20 | Cao
Code Front-end "View business trip history" app | Đạt Huỳnh | 2019-05-21 | 2019-05-23 | 2 |  | 20 | Cao
Code Front-end "Searching for business trip" app | Đạt Huỳnh | 2019-05-25 | 2019-05-27 | 2 |  | 20 | Cao
Code Back-end "Sign up for a business trip" app | Quang Vương | 2019-05-06 | 2019-05-07 | 1 |  | 15 | Cao
Code Back-end "View a business trip" app | Quang Vương | 2019-05-07 | 2019-05-08 | 1 |  | 15 | Cao
Code Back-end "Locate business trip" app | Quang Vương | 2019-05-08 | 2019-05-09 | 1 |  | 15 | Cao
Code Back-end "Browse business trips" app | Quang Vương | 2019-05-11 | 2019-05-12 | 1 |  | 15 | Cao
Code Back-end "Refuse business trip" app | Quang Vương | 2019-05-12 | 2019-05-13 | 1 |  | 15 | Cao
Code Back-end "View the "approving votes" business trip" app | Quang Vương | 2019-05-13 | 2019-05-15 | 2 |  | 20 | Cao
Code Back-end "View details of the business trip" app | Quang Vương | 2019-05-18 | 2019-05-20 | 2 |  | 20 | Cao
Code Back-end "View business trip history" app | Quang Vương | 2019-05-21 | 2019-05-23 | 2 |  | 20 | Cao
Code Back-end "Searching for business trip" app | Quang Vương | 2019-05-25 | 2019-05-27 | 2 |  | 20 | Cao
Test "Sign up for a business trip" app | Như Phương | 2019-05-13 | 2019-05-14 | 1 |  | 10 | Cao
Test "View a business trip" app | Như Phương | 2019-05-14 | 2019-05-15 | 1 |  | 10 | Cao
Test "Locate business trip" app | Như Phương | 2019-05-15 | 2019-05-16 | 1 |  | 10 | Cao
Test "Browse business trips" app | Như Phương | 2019-05-18 | 2019-05-19 | 1 |  | 10 | Cao
Test "Refuse business trip" app | Như Phương | 2019-05-19 | 2019-05-20 | 1 |  | 10 | Cao
Test "View the "approving votes" business trip" app | Như Phương | 2019-05-20 | 2019-05-21 | 1 |  | 10 | Cao
Test "View details of the business trip" app | Như Phương | 2019-05-21 | 2019-05-22 | 1 |  | 10 | Cao
Test "View business trip history" app | Như Phương | 2019-05-22 | 2019-05-23 | 1 |  | 10 | Cao
Test "Searching for business trip" app | Như Phương | 2019-05-25 | 2019-05-26 | 1 |  | 10 | Cao
Kết thúc planning, analysing & training |  |  |  | 47 |  | 535 |  | 0
Phần trăm hoàn thành
Đã hoàn thành | 0%
Quá hạn | 0%
Đang thực hiện | 0%
Chưa thực hiện | 0%
Ngân sách
Theo kế hoạch
Theo thực tế
Cơ cấu công việc
Đạt Huỳnh | 6
Quốc Nhân | 21
Quang Vương | 6
Anh Minh | 11
Như Phương | 17