## Summary
Actual | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Total
Đạt Huỳnh | #REF! | #REF! | [35 empty] | #REF!
0
0
0
0
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Planed | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Total
Đạt Huỳnh | #REF! | #REF! | [35 empty] | #REF!
0
0
0
0
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Vương Trương
Timelog:
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
1 | Monday | Meeting Mentor |  | 14/10/2019 | 4 | 4 | Done
1 | Tuesday | Research | research webgis | 15/10/2019 | 5 | 5 | Inprogress
1 | Wednesday | Research | research webgis | 16/10/2019 | 4.5 | 4.5 | Inprogress
1 | Thursday | Research | find another app like webgis | 17/10/2019 | 5 | 5 | Done
1 | Friday | Meetting Customer |  | 18/10/2019 | 4 | 4 | Done
1 | Saturday | Research | Project | 19/10/2019 | 4 | 5 | Inprogress
Total | Actual: | 26.5 |  |  |  | Plan: | 27.5
Week | Day | Task | Name Task |  | Actual | Plan | Status | Deliverible
2 | Monday | Research | Research model | 21/10/2019 | 5.5 | 6 | Done
2 | Tuesday | Research | Install qgis | 22/10/2019 | 5 | 6 | Done
2 | Wednesday | Meeting Mentor |  | 23/10/2019 | 4 | 4 | Done
2 | Thursday | Project Management | research webgis | 24/10/2019 | 5 | 6 | Done
2 | Friday | Research | Readding Customer Documments | 25/10/2019 | 6 | 6 | Done
2 | Saturday | Research | Presentation Customer Documments | 26/10/2019 | 4 | 6 | Done
Total | Actual: | 29.5 |  |  |  | Plan: | 34
Week | Day | Task | Name Task |  | Actual | Plan | Status | Deliverible
3 | Monday | Plan | Architecter plan document | 28/10/2019 | 5 | 5 | Done
3 | Tuesday | Meeting Mentor |  | 29/10/2019 | 4 | 4 | Done
3 | Wednesday | Meetting Customer |  | 30/10/2019 | 4.5 | 5 | Done
3 | Thursday | Research | research react | 31/10/2019 | 5 | 5 | Done
3 | Friday | Research | Architecture process document | 2019-01-11 | 6 | 5 | Done
3 | Saturday | Project Management | Document quality management | 2019-02-11 | 5.5 | 5 | Done
Total | Actual: | 30 |  |  |  | Plan: | 29
Week | Day | Task | Name Task |  | Actual | Plan | Status | Deliverible
4 | Monday | Meeting team |  | 2019-11-04 | 5.5 | 6 | Done
4 | Tuesday | Requirement | UC description | 2019-11-05 | 4 | 4 | Inprogress
4 | Wednesday | Meetting mentor |  | 2019-11-06 | 4 | 4 | Done
4 | Thursday | Meeting team | research react | 2019-11-07 | 5 | 5 | Done
4 | Friday | Meetting Customer |  | 2019-11-08 | 5 | 5 | Done
4 | Saturday | Requirement | UC description | 2019-11-09 | 6 | 6 | Done
Total | Actual: | 29.5 |  |  |  | Plan: | 30
Week | Day | Task | Name Task |  | Actual | Plan | Status | Deliverible
5 | Monday | Meeting team |  | 2019-11-11 | 5 | 5 | Done
5 | Tuesday | Meeting Mentor |  | 2019-11-12 | 4 | 4 | Done
5 | Wednesday | Requirement | Data design | 2019-11-13 | 4.5 | 5 | Done
5 | Thursday | Meeting team | research react | 2019-11-14 | 5.5 | 6 | Done
5 | Friday | Requirement | Data distionary | 2019-11-15 | 6 | 6 | Inprogress
5 | Saturday | Requirement | Data distionary | 2019-11-16 | 5.5 | 6 | Done
Total | Actual: | 30.5 |  |  |  | Plan: | 32
Week | Day | Task | Name Task |  | Actual | Plan | Status | Deliverible
6 | Monday | Meeting team |  | 2019-11-17 | 5.5 | 6 | Done
6 | Tuesday | Meetting Customer |  | 2019-11-18 | 4 | 4 | Done
6 | Wednesday | Architect | Architecture driver document | 2019-11-19 | 4.5 | 5 | Inprogress
6 | Thursday | Meeting team |  | 2019-11-20 | 5.5 | 6 | Done
6 | Friday | Architect | Architecture driver document | 2019-11-21 | 6 | 5 | Inprogress
6 | Saturday | Architect | Architecture driver document | 2019-11-22 | 5.5 | 5 | Done
Total | Actual: | 31 |  |  |  | Plan: | 31
Week | Day | Task | Name Task |  | Actual | Plan | Status | Deliverible
7 | Monday | Meeting team |  | 2019-11-24 | 5.5 | 6 | Done
7 | Tuesday | Meeting Mentor |  | 2019-11-25 | 4 | 4 | Done
7 | Wednesday | Architect | Architecture design document | 2019-11-26 | 4.5 | 5 | Done
7 | Thursday | Meeting team | research react | 2019-11-27 | 5.5 | 6 | Done
7 | Friday | Architect | Architecture design document | 2019-11-28 | 6 | 5 | Done
7 | Saturday | Architect | Architecture design document | 2019-11-29 | 5.5 | 5 | Done
Total | Actual: | 31 |  |  |  | Plan: | 31
Week | Day | Task | Name Task |  | Actual | Plan | Status | Deliverible
8 | Monday | Meeting team |  | 2019-12-01 | 5.5 | 6 | Done
8 | Tuesday | Meeting Mentor |  | 2019-12-02 | 4 | 4 | Done
8 | Wednesday | Detail design | UC description detail module 1 | 2019-12-03 | 6 | 6 | Done
8 | Thursday | Training | Install react native invironment | 2019-12-04 | 5 | 5 | Done
8 | Friday | Training | Install react native invironment | 2019-12-05 | 6 | 6 | Done
8 | Saturday | Training | Research JS | 2019-12-06 | 5.5 | 5 | Inprogress
Total | Actual: | 32 |  |  |  | Plan: | 32
Week | Day | Task | Name Task |  | Actual | Plan | Status | Deliverible
9 | Monday | Meeting team |  | 2019-12-08 | 5.5 | 6 | Done
9 | Tuesday | Training | Research JS | 2019-12-09 | 5.5 | 6 | Inprogress
9 | Wednesday | Training | Research JS | 2019-12-10 | 4.5 | 5 | Inprogress
9 | Thursday | Meeting team |  | 2019-12-11 | 5 | 5 | Done
9 | Friday | Meeting Mentor | Research JS | 2019-12-12 | 4 | 4 | Done
9 | Saturday | Meeting team | Review | 2019-12-13 | 5.5 | 5 | Done
Total | Actual: | 30 |  |  |  | Plan: | 31
Week | Day | Task | Name Task |  | Actual | Plan | Status | Deliverible
10 | Monday | Meeting team |  | 2019-12-15 | 5 | 5 | Done
10 | Tuesday | Training | Research firebase | 2019-12-16 | 5.5 | 6 | Inprogress
10 | Wednesday | Training | Research firebase | 2019-12-17 | 5.5 | 6 | Done
10 | Thursday | Meeting Mentor |  | 2019-12-18 | 4 | 4 | Done
10 | Friday | Training | Connect firebase with project | 2019-12-19 | 6 | 6 | Done
10 | Saturday | Meeting team | Review | 2019-12-20 | 6 | 6 | Done
Total | Actual: | 32 |  |  |  | Plan: | 33

## Sheet2
Timelog:
Work in period
Week | Day | Task | Name Task | Date | Actual | Plan | Status | Deliverible
1 | Monday | Training | Research GIS | 2019-10-28 | 5 | 5 | Done
1 | Tuesday | Meeting Mentor |  | 2019-10-29 | 4 | 4 | Done
1 | Wednesday | Meetting Customer |  | 2019-10-30 | 4.5 | 5 | Done
1 | Thursday | Training | research react | 2019-10-31 | 5 | 5 | Done
1 | Friday | Training | Install react | 2019-10-01 | 6 | 5 | Done
1 | Saturday | Project Management | Document quality management | 2019-10-02 | 5.5 | 5 | Done
Total | Actual: | 30 |  |  |  | Plan: | 29
2 | Monday | Project Management |  | 20/10/2019 |  |  | Done
2 | Tuesday | Project Management |  | 21/10/2019 |  |  | Done
2 | Wednesday | Meeting Mentor |  | 22/10/2019 |  |  | Done
2 | Thursday | Project Management |  | 23/10/2019 |  |  | Done
2 | Friday | Project Management |  | 24/10/2019 |  |  | Done
2 | Saturday | Project Management |  |  |  |  | Done
Total | Actual: | 0 |  |  |  | Plan: | 0