## Revision History
Schedule Module 2 BDS Project
| Project Name: | BDS Project
| Team: | Team 03 - Hello World
| Document: | Schedule module 2
| Creator: | Nhan Pham
| Created Date: | 2019-02-12
Revision History
| Version | Date | Author | Content
| Version 1.0 | 2019-02-12 | Nhan Pham | Create schedule module 2

## Dữ liệu dự án
Bảng công việc
ID | Nội dung công việc | Người phụ trách | Ngày bắt đầu | Ngày kết thúc | Số ngày (ngày) | Tình trạng | Số giờ hoàn thành công việc kế hoạch (Giờ) | Mức độ ưu tiên | Số giờ hoàn thành công việc cá nhân (Giờ)
1 | Design prototype, sequence, use case description "View all project listings" app | Quốc Nhân | 2020-03-09 | 2020-03-11 | 2 | Đã hoàn thành | 20 | Cao | 22
2 | Design prototype, sequence, use case description "View all project listings being implemented" app | Quốc Nhân | 2020-03-12 | 2020-03-14 | 2 | Đã hoàn thành | 20 | Cao | 19
3 | Design prototype, sequence, use case description "View all project listings prepare to deploy" app | Quốc Nhân | 2020-03-16 | 2020-03-17 | 1 | Đã hoàn thành | 10 | Cao | 16 | Formula
4 | Design prototype, sequence, use case description "View all project listings has deployed" app | Quốc Nhân | 2020-03-18 | 2020-03-19 | 1 | Đã hoàn thành | 10 | Cao | 19 | Số giờ hoàn thành công việc cá nhân = Thời gian cồng việc + Số công việc đã làm (cập nhật time log)
5 | Design prototype, sequence, use case description "View all project listings" website | Quốc Nhân | 2020-03-20 | 2020-03-21 | 1 | Đã hoàn thành | 10 | Cao | 16
6 | Design prototype, sequence, use case description "Add projects" website | Quốc Nhân | 2020-03-23 | 2020-03-25 | 2 | Đã hoàn thành | 20 | Cao | 27
7 | Design prototype, sequence, use case description "Edit projects" website | Quốc Nhân | 2020-03-26 | 2020-03-28 | 2 | Đã hoàn thành | 20 | Cao | 22
8 | Design messages list module 2 | Quốc Nhân | 2020-03-10 | 2020-03-14 | 4 | Đã hoàn thành | 28 | Cao | 23
9 | Design business rule module 2 | Quốc Nhân | 2020-03-30 | 2020-04-01 | 2 | Đã hoàn thành | 20 | Cao | 15
10 | Design use case diagram module 2 | Quốc Nhân | 2020-04-02 | 2020-04-04 | 2 | Đã hoàn thành | 20 | Cao | 19
11 | Code Front-end "View all project listings" app | Đạt Huỳnh | 2020-03-02 | 2020-03-06 | 4 | Đã hoàn thành | 40 | Cao
12 | Code Front-end "View all project listings being implemented" app | Đạt Huỳnh | 2020-03-09 | 2020-03-13 | 4 | Đã hoàn thành | 40 | Cao
13 | Code Front-end "View all project listings prepare to deploy" app | Đạt Huỳnh | 2020-03-16 | 2020-03-20 | 4 | Đã hoàn thành | 40 | Cao
14 | Code Front-end "View all project listings has deployed", "View detail project" app | Đạt Huỳnh | 2020-03-23 | 2020-03-31 | 8 | Đã hoàn thành | 80 | Cao
15 | Code Back-end "View all project listings" app | Quang Vương | 2020-03-02 | 2020-03-06 | 4 | Đã hoàn thành | 40 | Cao
16 | Code Back-end "View all project listings being implemented" app | Quang Vương | 2020-03-09 | 2020-03-13 | 4 | Đã hoàn thành | 40 | Cao
17 | Code Back-end "View all project listings prepare to deploy" app | Quang Vương | 2020-03-16 | 2020-03-20 | 4 | Đã hoàn thành | 40 | Cao
18 | Code Back-end "View all project listings has deployed" , "View detail project" app | Quang Vương | 2020-03-23 | 2020-03-31 | 8 | Đã hoàn thành | 80 | Cao
19 | Code Front-end, back-end "View all project listings" website | Anh Minh | 2020-03-10 | 2020-03-17 | 7 | Đã hoàn thành | 70 | Cao
20 | Code Front-end, back-end "Add projects" website | Anh Minh | 2020-03-18 | 2020-03-25 | 7 | Đã hoàn thành | 70 | Cao
21 | Code Front-end, back-end "Edit projects" website | Anh Minh | 2020-03-26 | 2020-04-01 | 6 | Đã hoàn thành | 60 | Cao
22 | Test "View all project listings" app | Như Phương | 2020-03-09 | 2020-03-11 | 2 | Đã hoàn thành | 20 | Cao
23 | Test "View all project listings being implemented" app | Như Phương | 2020-03-12 | 2020-03-13 | 1 | Đã hoàn thành | 10 | Cao
24 | Test "View all project listings prepare to deploy" app | Như Phương | 2020-03-16 | 2020-03-18 | 2 | Đã hoàn thành | 20 | Cao
25 | Test "View all project listings has deployed" app | Như Phương | 2020-03-19 | 2020-03-20 | 1 | Đã hoàn thành | 10 | Cao
26 | Test "View all project listings" website | Như Phương | 2020-03-23 | 2020-03-25 | 2 | Đã hoàn thành | 20 | Cao
27 | Test "Add projects" website | Như Phương | 2020-03-26 | 2020-03-28 | 2 | Đã hoàn thành | 20 | Cao
28 | Test "Edit projects" website | Như Phương | 2020-03-30 | 2020-04-01 | 2 | Đã hoàn thành | 20 | Cao
Kết thúc module 2 |  |  |  |  | 91 |  | 898 |  | 198
Phần trăm hoàn thành
| Đã hoàn thành | 0%
| Quá hạn | 33%
| Đang thực hiện | 21%
| Chưa thực hiện | 46%
Ngân sách
Theo kế hoạch
Theo thực tế
Cơ cấu công việc
| Đạt Huỳnh | 4
| Quốc Nhân | 10
| Quang Vương | 4
| Anh Minh | 3
| Như Phương | 7