## Report
Earned Value Analysis Report
| Prepared By: | Huỳnh Tuấn Đạt
| Date: | 2019-10-14
[42]
| For Period: | Week 12
[7 empty] | CPI | 0.79703 | Over Budget
[7 empty] | SPI | 1 | On Time
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | TBC | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28
1 | Planing | 0
1.1 | Project Management Plan & Process | 0
1.1.1 | Create Communication Plan | 12 | 6 | 6
1.1.2 | Create Configuration Plan | 12 | 6 | 6
1.1.3 | Create Project Charter | 11 | 5 | 6
1.1.4 | Create Project Plan | 11 | 5 | 6
1.1.5 | Create Development Process | 12 |  | 6 | 6
1.1.6 | Create Quality Management Plan | 10 |  | 4 | 6
1.1.7 | Create Measurement Plan | 6 |  |  | 6
1.1.8 | Create Risk Management Plan | 10 |  |  | 5 | 5
1.2 | Requirement Plan and Process | 0
1.2.1 | Create Requirement Plan | 11 |  | 6 | 5
1.2.2 | Create Requirement Process | 11 |  | 5 | 6
1.3 | Architecture Plan and Process | 0
1.3.1 | Create Architecture Plan | 6 |  |  | 6
1.3.2 | Create Architecture Process | 6 |  |  | 6
1.4 | Details Design Plan and Process | 0
1.4.1 | Create Details Design Process | 12 |  |  | 12
1.5 | Implementation Plan and Process | 0
1.5.1 | Create Implementation Plan | 6 |  |  |  | 6
1.5.2 | Create Implementation Process | 6 |  |  |  | 6
1.6 | Test Plan and Process | 0
1.6.1 | Create Test Plan | 6 |  |  |  | 6
1.6.2 | Create Test Process | 6 |  |  |  | 6
1.7 | Trainning Plan | 0
1.7.1 | Create Trainning Plan | 7 |  |  |  | 7
2 | Analysing & Training | 0
2.1 | Requirement | 0
2.1.1 | Release S.R.S | 54 |  |  |  |  | 30 | 24
2.1.2 | Release ConOp | 14 |  |  |  |  | 6 | 8
2.1.3 | Release Tracebility Matrix | 10 |  |  |  |  | 5 | 5
2.2 | Architecture and Design | 0
2.2.1 | Release Architecture Driver | 60 | [6 empty] | 30 | 30
2.2.2 | Release Architecture Design | 70 | [6 empty] | 25 | 25 | 20
2.2.3 | Release Details Design | 50 | [7 empty] | 25 | 25
2.3 | Risk Management | 0 | [7 empty] | 7
2.4 | Training | 20 | [6 empty] | 20 | 20 | 20 | 20
3 | Implementation & Testing | 0
3.1 | Module 1 | 0
3.1.1 | Implementation | 0
3.1.1.1 | Feature "Đăng nhập " | 0
3.1.1.2 | Feature "Quản lý thông tin" | 0
3.1.1.3 | Feature "Quản lý tài khoản" | 0
0
0
0
0
| Total Budgeted Cost | 439 | 22 | 45 | 58 | 36 | 41 | 37 | 75 | 107 | 65 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Planned Value (BCWS) | 22 | 67 | 125 | 161 | 202 | 239 | 314 | 421 | 486 | 506 | 506 | 506 | 506 | 506 | 506 | 506 | 506 | 506 | 506 | 506 | 506 | 506 | 506 | 506 | 506 | 506 | 506 | 506
Actual Cost and Earned Value
|  | Cumulative Actual Cost (ACWP) | 20 | 56 | 155 | 202 | 232 | 320 | 451.5 | 559.5 | 661 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735
|  | Cumulative Earned Value (BCWP) | 33.8 | 96 | 130 | 161 | 196 | 232 | 287 | 373.5 | 413.2 | 425 | 405 | 405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Performance Metrics
|  | Cost Variance (CV = BCWP-ACWP) | 13.8 | 40 | -25 | -41 | -36 | -88 | -164.5 | -186 | -247.8 | -310 | -330 | -330 | -735 | -735 | -735 | -735 | -735 | -735 | -735 | -735 | -735 | -735 | -735 | -735 | -735 | -735 | -735 | -735
|  | Schedule Variance (SV = BCWP - BCWS) | 11.8 | 29 | 5 | 0 | -6 | -7 | -27 | -47.5 | -72.8 | -81 | -101 | -101 | -506 | -506 | -506 | -506 | -506 | -506 | -506 | -506 | -506 | -506 | -506 | -506 | -506 | -506 | -506 | -506
|  | Cost Performance Index (CPI = BCWP/ACWP) | 1.69 | 1.7143 | 0.83871 | 0.79703 | 0.84483 | 0.725 | 0.63566 | 0.66756 | 0.62511 | 0.57823 | 0.55102 | 0.55102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Schedule Performance Index (SPI = BCWP/BCWS) | 1.5364 | 1.4328 | 1.04 | 1 | 0.9703 | 0.97071 | 0.91401 | 0.88717 | 0.85021 | 0.83992 | 0.8004 | 0.8004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Estimated Cost at Completion (EAC) | 259.7633 | 256.0833 | 523.4231 | 550.795 | 519.6327 | 605.5172 | 690.622 | 657.6185 | 702.2725 | 759.2118 | 796.7037 | 796.7037 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Note on A21: Work Breakdown Structure (WBS)
Note on C21: Total Budgeted Cost (TBC)

## ACWP
Actual Cost For Work Performed
Actual Cost For Work Performed (ACWP)
WBS | Task Name | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28
1 | Planing
1.1 | Project Management Plan & Process
1.1.1 | Create Communication Plan | W1: 8
1.1.2 | Create Configuration Plan | W1: 6; W2: 12
1.1.3 | Create Project Charter | W1: 6; W2: 12
1.1.4 | Create Project Plan | W2: 12
1.1.5 | Create Development Process | W3: 6.5
1.1.6 | Create Quality Management Plan | W3: 17.5
1.1.7 | Create Measurement Plan | W3: 9
1.1.8 | Create Risk Management Plan | W3: 11
1.2 | Requirement Plan and Process
1.2.1 | Create Requirement Plan | W3: 10.5; W4: 5.5
1.2.2 | Create Requirement Process | W3: 5; W4: 5
1.3 | Architecture Plan and Process
1.3.1 | Create Architecture Plan | W3: 5
1.3.2 | Create Architecture Process | W3: 6
1.4 | Details Design Plan and Process
1.4.1 | Create Details Design Process | W3: 18
1.5 | Implementation Plan and Process
1.5.1 | Create Implementation Plan | W4: 10
1.5.2 | Create Implementation Process | W4: 6.5
1.6 | Test Plan and Process
1.6.1 | Create Test Plan | W3: 10.5
1.6.2 | Create Test Process | W4: 5
1.7 | Trainning Plan
1.7.1 | Create Trainning Plan | W4: 5
2 | Analysing & Training
2.1 | Requirement
2.1.1 | Release S.R.S | W4: 10; W5: 20; W6: 26.5
2.1.2 | Release ConOp | W5: 5; W6: 20.5
2.1.3 | Release Tracebility Matrix | W5: 5; W6: 4.5
2.2 | Architecture and Design
2.2.1 | Release Architecture Driver | W6: 32; W7: 45
2.2.2 | Release Architecture Design | W6: 4.5; W7: 31; W8: 24.5; W9: 10
2.2.3 | Release Details Design | W8: 34; W9: 30; W10: 15
2.3 | Risk Management | W8: 5
2.4 | Training | W7: 55.5; W8: 44.5; W9: 61.5; W10: 59
3 | Implementation & Testing
3.1 | Module 1
3.1.1 | Implementation
3.1.1.1 | Feature "Đăng nhập "
3.1.1.2 | Feature "Quản lý thông tin"
3.1.1.3 | Feature "Quản lý tài khoản"
0.1
Insert new rows above this one
|  | 20 | 36 | 99 | 47 | 30 | 88 | 131.5 | 108 | 101.5 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ACWP | 20 | 56 | 155 | 202 | 232 | 320 | 451.5 | 559.5 | 661 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735 | 735
Sau khi cộng thời gian từ timelog từ các thành viên

## BCWP
Budget Cost For Work Performed
Budget Cost For Work Performed (BCWP)
WBS | Task Name | TCB | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28
1 | Planing | 0
1.1 | Project Management Plan & Process | 0
1.1.1 | Create Communication Plan | 12 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.1.2 | Create Configuration Plan | 12 | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.1.3 | Create Project Charter | 11 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.1.4 | Create Project Plan | 11 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.1.5 | Create Development Process | 12 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.1.6 | Create Quality Management Plan | 10 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.1.7 | Create Measurement Plan | 6 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.1.8 | Create Risk Management Plan | 10 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.2 | Requirement Plan and Process | 0
1.2.1 | Create Requirement Plan | 11 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.2.2 | Create Requirement Process | 11 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.3 | Architecture Plan and Process | 0
1.3.1 | Create Architecture Plan | 6 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.3.2 | Create Architecture Process | 6 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.4 | Details Design Plan and Process | 0
1.4.1 | Create Details Design Process | 12 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.5 | Implementation Plan and Process | 0
1.5.1 | Create Implementation Plan | 6 |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.5.2 | Create Implementation Process | 6 |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.6 | Test Plan and Process | 0
1.6.1 | Create Test Plan | 6 |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.6.2 | Create Test Process | 6 |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.7 | Trainning Plan | 0
1.7.1 | Create Trainning Plan | 7 |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2 | Analysing & Training | 0
2.1 | Requirement | 0
2.1.1 | Release S.R.S | 54 |  |  |  |  | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2.1.2 | Release ConOp | 0 |  |  |  |  | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2.1.3 | Release Tracebility Matrix | 10 |  |  |  |  | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2.2 | Architecture and Design | 0
2.2.1 | Release Architecture Driver | 60 | [6 empty] | 70% | 100% | 100% | 100% | 100% | 100%
2.2.2 | Release Architecture Design | 70 | [5 empty] | 10% | 20% | 75% | 100% | 100% | 100% | 100%
2.2.3 | Release Details Design | 50 | [7 empty] | 50% | 84% | 100% | 100% | 100%
2.3 | Risk Management | 0 | [7 empty] | 100%
2.4 | Training | 20 | [6 empty] | 30% | 55% | 81% | 100%
3 | Implementation & Testing | 0
3.1 | Module 1 | 0
3.1.1 | Implementation | 0
3.1.1.1 | Feature "Đăng nhập " | 0
3.1.1.2 | Feature "Quản lý thông tin" | 0
3.1.1.3 | Feature "Quản lý tài khoản" | 0
Insert new rows above this one
|  | Cumulative EV | 33.8 | 96 | 130 | 161 | 196 | 232 | 287 | 373.5 | 413.2 | 425 | 405 | 405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Số lượng công việc của các thành viên đã hoàn thành bao nhiêu phần trăm và báo lại, dựa trên timelog của thành viên.

## ©
Earned Value Management (EVM) Template
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/critical-path-method.html
© 2012-2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet.