## Cover
Project: Capstone Project_Quản Lý Cty Bất Động Sản
Team Development : Hello World
Mentor: Mr . Đặng Đình Hòa
Document: Defect Log
Purpose: This document is used to classify the defect, how they are prioritizied, date raise defect and date closed
Version History
| Version | Date | Author | Comment
| 1 | 2019-04-04 | Như phương | Create document
| 1.1 | 2020-11-04 | Như phương | Update document
| 1.2 | 2020-12-04 | Như phương | Update defect
| 1.3 | 2020-06-05 | Như phương | Update defect
| 1.4 | 2020-07-05 | Như phương | Update defect
| 1.5 | 21/5/2020 | Như phương | Update defect
| 1.6 | 30/5/2020 | Như phương | Update defect
| 1.7 | 2020-06-06 | Như phương | Update defect
| 1.8 | 2020-08-06 | Như phương | Update defect
| 1.9 | 13/6/2020 | team | Review

## Defect Log
DEFECT LOG MODULE 2
NO. | DEFECT ID | DEFECT DESCRIPTION | REFERENCE | VERSION | STEPS | DATE RASISED | DETECTED BY | STATUS | FIXED BY | DATE CLOSED | PRIORITY
1 | #1 | admin's "View BDS project" interface does not display enough project information images |  | 1 | Step 1: Access the link Step 2: Log in with the admin username and password Step 3: Access the Home page Step 4: Click the "Project management" system | 2020-12-04 | Như Phương | close | Anh Minh | 2020-06-05 | High
2 | #2 | The admin's "View BDS project" interface does not display project information images with the correct size |  | 1 | Step 1: Access the link Step 2: Log in with the admin username and password Step 3: Access the Home page Step 4: Click the "Project management" system | 2020-12-04 | Như Phương | close | Anh Minh | 2020-06-05 | medium
| #3 | Admin's "View BDS project" interface just shows the "edit" button |  | 1 | Step 1: Access the link Step 2: Log in with the admin username and password Step 3: Access the Home page Step 4: Click the "Project management" system | 2020-12-04 | Như Phương | close | Anh Minh | 2020-06-05 | medium
3 | #4 | The "add project" function lacks the price information field |  | 1 | Step 1: Access the link Step 2: Log in with the admin username and password Step 3: Access the Home page Step 4: Click the "Project management" system Step 5: Click the "add project" | 2020-12-04 | Như Phương | close | Anh Minh | 2020-06-05 | medium
4 | #5 | The "add project" function shows a number field but the word is still entered |  | 1 | Step 1: Access the link Step 2: Log in with the admin username and password Step 3: Access the Home page Step 4: Click the "Project management" system Step 5: Click the "add project" Step 6: Enter text information in the Sdt information field | 2020-12-04 | Như Phương | close | Anh Minh | 2020-06-06 | medium
5 | #6 | The "add project" function, the system can still add information without an information field |  | 1 | Step 1: Access the link Step 2: Log in with the admin username and password Step 3: Access the Home page Step 4: Click the "Project management" system Step 5: Click the "add project" Step 6: enter missing location information field. | 2020-12-04 | Như Phương | close | Anh Minh | 2020-06-06 | High
6 | #7 | The function "add project" after completing the import but does not show all the information added to the list |  | 1 | Step 1: Access the link Step 2: Log in with the admin username and password Step 3: Access the Home page Step 4: Click the "Project management" system Step 5: Click the "add project" Step 6: Complete project information Step 7: Click the add button | 2020-12-04 | Như Phương | close | Anh Minh | 2020-06-06 | medium
7 | #8 | The "add project" function adds a picture of the project information without adding a doc file |  | 1 | Step 1: Access the link Step 2: Log in with the admin username and password Step 3: Access the Home page Step 4: Click the "Project management" system Step 5: Click the "add project" Step 6: Complete project information Step 7: Click the "select file" button to select the doc file | 2020-12-04 | Như Phương | close | Anh Minh | 2020-06-05 | High
8 | #9 | The "add project" function has a blank input but still informs the success |  | 1 | Step 1: Access the link Step 2: Log in with the admin username and password Step 3: Access the Home page Step 4: Click the "Project management" system Step 5: Click the "add project" Step 6: Fill blank space in the information fields Step 7: Click the "add" button | 2020-12-04 | Như Phương | close | Anh Minh | 2020-06-06 | medium
9 | #10 | Function "Edit project" interface does not display the image of previous project information |  | 1 | Step 1: Access the link Step 2: Log in with the admin username and password Step 3: Access the Home page Step 4: Click the "Project management" system Step 5: Click the "edit project | 2020-12-04 | Như Phương | close | Anh Minh | 2020-06-05 | High
10 | #11 | "Edit project" function because it does not show the project information images in the list, so it will not display after editing. |  | 1 | Step 1: Access the link Step 2: Log in with the admin username and password Step 3: Access the Home page Step 4: Click the "Project management" system Step 5: Click the "edit project" Step 6: press "select file" to select images | 2020-12-04 | Như Phương | close | Anh Minh | 2020-06-05 | medium
11 | #12 | The "Edit project" function after editing does not show the full information on the project list |  | 2 | Step 1: Access the link Step 2: Log in with the admin username and password Step 3: Access the Home page Step 4: Click the "Project management" system Step 5: Click the "edit project" Step 6: press "select file" select image " Step 7: Enter new information in the information field Step 8: Click the" save "button | 2020-06-05 | Như Phương | close | Anh Minh | 2020-06-05 | High
12 | #13 | The "Edit project" function has a numeric data field but can still enter words |  | 2 | Step 1: Access the link Step 2: Log in with the admin username and password Step 3: Access the Home page Step 4: Click the "Project management" system Step 5: Click the "edit project" Step 6: press "select file" to select images " Step 7: Enter text in the digital information field Step 8: Click the" save "button | 2020-06-05 | Như Phương | close | Anh Minh | 2020-06-05 | medium
13 | #14 | The "Edit project" function, the user enters a blank character but still notices the successful modification |  | 2 | Step 1: Access the link Step 2: Log in with the admin username and password Step 3: Access the Home page Step 4: Click the "Project management" system Step 5: Click the "edit project" Step 6: press "select file" to select images " Step 7: Enter a blank character in the information fields Step 8: Click the" save "button | 2020-06-05 | Như Phương | close | Anh Minh | 2020-06-05 | medium
14 | #15 | The "project view" function on WedAdmin displays the missing project status column |  | 3 | Step 1: Access the link Step 2: Log in with the admin username and password Step 3: Access the Home page Step 4: Click the "Project management" system | 2020-07-05 | Như Phương | close | Anh Minh | 21/5/2020 | High
15 | #16 | "Edit project" function, users cannot update image when pressing "upload" button but must delete the previous image before clicking |  | 3 | Step 1: Access the link Step 2: Log in with the admin username and password Step 3: Access the Home page Step 4: Click the "Project management" system Step 5: Click the "edit project" Step 6: press "select file" to select images " Step 7: Enter text in the digital information field Step 8: Click the" save "button | 2020-07-05 | Như Phương | close | Anh Minh | 21/5/2020 | low
16 | #17 | function "edit project" on WebAdmin after users update project information, display the wrong message as "project added successfully" |  | 3 | Step 1: Access the link Step 2: Log in with the admin username and password Step 3: Access the Home page Step 4: Click the "Project management" system Step 5: Click the "edit project" Step 6: press "select file" select image " Step 7: Enter new information in the information field Step 8: Click the" save "button | 2020-07-05 | Như Phương | close | Anh Minh | 2020-06-06 | medium
17 | #18 | Interface "see project details" on mobile users after clicking the position information, the system does not display the location of that project |  | 3 | Step 1: access the Property Management App Step2: Log in with the username and password of the User Step3: access the homepage interface Step4: Click on the Real Estate project Step 5: click on a project Step 6 : click the "location" information item for that project | 2020-07-05 | Như Phương | close | Anh Minh | 2020-06-06 | medium
18 | #19 | function "change password", the user has entered enough and exactly two password fields but could not press the "change password" button |  | 4 | Step 1: User successfully login to BDS Company Management App Step2: Click on the avatar image displayed Step3: Select "change password" Step4: Enter "current password" Step 5: Enter "New Password" Step 6: Click "Change Password | 2020-06-06 | Như Phương | close | quang vương | 2020-08-06 | high
19 | #20 | function "change password" the user enters the current password incorrectly but does not show the message and cannot press the "change password" button |  | 4 | Step 1: User successfully login to BDS Company Management App Step2: Click on the avatar image displayed Step3: Select "change password" Step4: Enter "current password" (enter the wrong current information field ) Step 5: Enter "New Password" Step 6: Click "Change Password | 2020-06-06 | Như Phương | close | quang vương | 30/5/2020 | medium
20 | #21 | "Change password" function does not display the message "Change password successfully" |  | 4 | Step 1: User successfully login to BDS Company Management App Step2: Click on the avatar image displayed Step3: Select "change password" Step4: Enter "current password" Step 5: Enter "New Password" Step 6: Click "Change Password | 2020-06-06 | Như Phương | close | quang vương | 2020-08-06 | medium
21 | #22 | "Change password" function does not display the message "The current password is not valid" |  | 4 | Step 1: User successfully login to BDS Company Management App Step2: Click on the avatar image displayed Step3: Select "change password" Step4: Enter "current password" Step 5: Enter "New Password" Step 6: Click "Change Password | 2020-06-06 | Như Phương | close | quang vương | 2020-08-06 | medium
22 | #23 | "change password" function leaves the information field blank but does not display a message |  | 4 | Step 1: User successfully login to BDS Company Management App Step2: Click on the avatar image displayed Step3: Select "change password" Step4: Enter "current password" (leave blank) Step 5: Enter "New Password" Step 6: Click "Change Password | 2020-06-06 | Như Phương | close | quang vương | 2020-08-06 | medium
22 | #23 | function "change password" the user leaves the current password information field blank but does not display the message "blank" but shows the "wrong password" message |  | 4 | Step 1: User successfully login to BDS Company Management App Step2: Click on the avatar image displayed Step3: Select "change password" Step4: Enter "current password" (leave blank) Step 5: Enter "New Password" Step 6: Click "Change Password | 2020-06-06 | Như Phương | open |  |  | low
23 | #24 | function "edit project" interface "edit project" field of lead information does not display information of the project being edited |  | 4 | Step 1: Access the link Step 2: Log in with the admin username and password Step 3: Access the Home page Step 4: Click the "Project management" system Step 5: Click the "edit project" | 2020-06-06 | Như Phương | close | Anh Minh | 2020-08-06 | medium
24 | #25
25 | #26
26 | #27
27 | #28
28 | #29
29 | #30
30 | #31