## Cover
Project: Capstone Project_Quản Lý Cty Bất Động Sản
Team Development : Hello World
Mentor: Mr . Đặng Đình Hòa
Document: Defect Log
Purpose: This document is used to classify the defect, how they are prioritizied, date raise defect and date closed
Version History
| Version | Date | Author | Comment
| 1 | 2020-04-04 | Như phương | Create document
| 1.1 | 2020-11-04 | Như phương | Update document
| 1.2 | 2020-12-04 | Như phương | Update defect
| 1.3 | 28/04/2020 | Như phương | Update defect
| 1.4 | 2020-02-05 | Như phương | Update defect
| 1.5 | 2020-11-05 | Như phương | Update defect
| 1.6 | 21/05/2020 | Như phương | Update defect
| 1.7 | 25/05/2020 | Như phương | Update defect
| 1.8 | 2020-06-06 | Như phương | Update defect
| 1.9 | 13/06/2020 | Team | Review

## Defect Log
DEFECT LOG
NO. | DEFECT ID | DEFECT DESCRIPTION | REFERENCE | VERSION |  | DATE RASISED | DETECTED BY | STATUS | FIXED BY | DATE CLOSED | PRIORITY
1 | #1 | The "Login" function when the user leaves the system account information field blank automatically without showing the message |  | 1 | Step1: User access to Real Estate App Step2: Leave the account information field blank Step3: press "login" | 2020-06-03 | Như Phương | close | Quang Vương | 2020-02-05 | High
| #2 | The "WedAdmin Login" function displays the wrong message when the user enters the wrong username field |  | 1 | Step1: The user accesses the Real Estate Web site Step2: Enter the wrong "username" field Step3: click "login" | 2020-06-03 | Như Phương | close | Anh Minh | 2020-02-05 | High
2 | #3 | "Login" function when the user leaves the system password information field blank automatically without showing a message |  | 1 | Step1: User access to Real Estate App Step2: Leave the account information field blank Step3: press "login" | 2020-06-03 | Như Phương | close | Quang Vương | 2020-02-05 | High
| #4 | Function "see organizational chart" image diagram display is not up to quality |  | 1 | Step1: User login to Real Estate App with personal account Step2: On the homepage, click on "Information" Step3: In the information section, click on organization chart | 2020-06-03 | Như Phương | open | Quang Vương | 2020-06-06 | Medium
3 | #5 | The function "see organizational chart" of employee photos has not been uploaded yet |  | 1 | Step1: User login to Real Estate App with personal account Step2: On the homepage, click on "Information" Step3: In the information section, click on organization chart Step4: Click on the items in the diagram organization | 2020-06-03 | Như Phương | close | Quang Vương | 2020-02-05 | Medium
4 | #6 | The function "see the organization chart WedAdmin" image of the organization chart has not been displayed in the central position |  | 1 | Step1: Admin, log in to WebAdmin Real Estate with Admin account Step2: On the home page, click on the "Information" item Step3: In the information section, click on the organizational chart | 2020-06-03 | Như Phương | open | Anh Minh |  | low
5 | #7 | The "see WedAdmin organization chart" function displays multiple images as a list |  | 1 | Step1: Admin, log in to WebAdmin Real Estate with Admin account Step2: On the home page, click on the "Information" item Step3: In the information section, click on the organizational chart | 2020-06-03 | Như Phương | close | Anh Minh | 2020-02-05 | low
6 | #8 | "Upload organization chart" function after selecting the image and uploading, the image is not displayed |  | 1 | Step1: Admin, log in to WebAdmin Real Estate with Admin account Step2: On the home page, click on the "Information" Step3: In the information section, click on the organizational chart Step4: Click the "add organization chart" button in the organization chart section Steep5: select the image file to display for the organizational chart entry Step 6: Click "Luu" | 2020-06-03 | Như Phương | Close | Anh Minh | 28/04/2020 | High
7 | #9 | The "add company policy" function in the Admin policy name information field is still successful when entering a blank signature |  | 2 | Step1: Admin login to Real Estate WebAdmin with admin account Step2: On the homepage, click on the "Information" dropbox Step3: In the information dropbox, click on the company policy Step4: Click the "add policy" button Step5: : Enter the policy name Step6: Click the "select file" button Step7: select the image file to display Step8: Click the "open" button on browser Step9: Click "add" | 28/04/2020 | Như Phương | close | Anh Minh | 2020-02-05 | medium
8 | #10 | The "Edit company policy" function in the user editing interface still retains information when entering a blank character. |  | 2 | Step1: Admin login to Real Estate WebAdmin with admin account Step2: On the homepage, click on the "Information" dropbox Step3: In the information dropbox, click on the company policy Step4: Click the "edit policy" button Step5: : Enter a blank space in the policy name field Step6: Click the "select file" button Step7: select the image file to display Step8: Click the "open" button on the browser Step9: Click "Luu" | 28/04/2020 | Như Phương | close | Anh Minh | 2020-02-05 | medium
9 | #11 | The homepage interface after the user clicks on the avatar image to display that employee information but the employee name is missing |  | 2 | Step1: The user accesses the App of Real Estate Management Company Step2: The user enters the username and password Step3: the user logs into the system into the App Step4: click on the representative image Step5: Observe the system information display | 28/04/2020 | Như Phương | close | Quang Vương | 2020-02-05 | medium
10 | #12 | The system "View account information" displays missing the Employee Code column |  | 3 | Step1: Admin login to Real Estate WebAdmin with admin account Step2: On the homepage, click "manage account" | 2020-11-05 | Như Phương | Close | Anh Minh | 2020-06-06 | High
| #13 | The system "View account information" lacks the Employee column, so it does not display the A-Z's unorganized list of Employee codes |  | 3 | Step1: Admin login to Real Estate WebAdmin with admin account Step2: On the homepage, click "manage account" | 2020-11-05 | Như Phương | Close | Anh Minh | 2020-06-06 | medium
| #14 | The function "Add account" in the interface to add account without displaying information: employee code, group |  | 3 | Step1: Admin login to Real Estate WebAdmin with admin account Step2: On the homepage, click "manage account" Step3: Click "Add account" button | 2020-11-05 | Như Phương | close | Anh Minh | 21/5/2020 | medium
| #15 | The function "add account" Admin has left the information field blank but the system still displays the message "successfully added" |  | 3 | Step1: Admin login to Real Estate WebAdmin with admin account Step2: On the homepage, click "manage account" Step3: Click "Add account" button Step4: Enter account information (leave blank) Step5: Click "select file" Step6: select the image file to display Step7: Click the "open" button in browser Step8: Click "add" | 2020-11-05 | Như Phương | close | Anh Minh | 21/5/2020 | medium
11 | #16 | The function of 'adding account' after adding a new account still does not show enough information fields (MNV) |  | 3 | Step1: Admin login to Real Estate WebAdmin with admin account Step2: On the homepage, click "manage account" Step3: Click the "Add account" button Step4: Enter account information Step5: Click the "select" button file " Step6: select display image file Step7: select display image file Step8: Click" open "button in browser Step9: Click" add " | 2020-11-05 | Như Phương | close | Anh Minh | 25/05/2020 | high
| #17 | The function of 'adding accounts' users adding emails already exists but the system does not display the message |  | 4 | Step1: Admin login to Real Estate WebAdmin with admin account Step2: On the homepage, click "manage account" Step3: Click "Add account" button Step4: Enter account information (Email already exists) Step5: Click the "select file" button Step6: select the displayed image file Step7: select the displayed image file Step8: Click the "open" button in browser Step9: Click "add" | 21/5/2020 | Như Phương | close | Anh Minh | 25/05/2020 | High
| #18 | Add account' function in user information field enter the first character that is number but the following characters are letters but system does not give error |  | 4 | Step1: Admin login to Real Estate WebAdmin with admin account Step2: On the homepage, click "manage account" Step3: Click "Add account" button Step4: Enter account information (SDT information field eg : 6sssssss) Step5: Click the "select file" button Step6: select the image file to display Step7: Click the "open" button on browser Step8: Click "add" | 22/5/2020 | Như Phương | close | Anh Minh | 25/05/2020 | High
| #19 | Add account' function could not load employee avatar |  | 4 | Step1: Admin login to Real Estate WebAdmin with admin account Step2: On the homepage, click "manage account" Step3: Click the "Add account" button Step4: Enter account information Step5: Press the "select" button file " Step6: select the image file to display Step7: Click the" open "button in the browser (the image does not upload) Step8: Click" add " | 22/5/2020 | Như Phương | close | Anh Minh | 25/05/2020 | High
| #20 | "Logout" function on WebAdmin after pressing logout, the system will not display a confirmation message |  | 4 | Step1: User access to Real Estate App Step2: click "sign out" | 22/5/2020 | Như Phương | open | Anh Minh |  | low
| #21 | The function of "adding accounts" after adding accounts has not yet shown the room and group names |  | 4 | Step1: Admin login to Real Estate WebAdmin with admin account Step2: On the homepage, click "manage account" Step3: Click the "Add account" button Step4: Enter account information Step5: Press the "select" button file " Step6: select the image file to display Step7: Click the" open "button on the browser Step8: Click" add " | 25/05/2020 | Như Phương | open | Anh Minh | 2020-06-06 | mediu m
| #22 | function "edit account" after users edit the information of the department, the system does not update the information of that interview |  | 4 | Step1: Admin login to Real Estate WebAdmin with admin account Step2: On the homepage, click "manage account" Step3: Click the "edit account" button Step4: Enter new account information (Add department) Step5: Click "select file" Step6: select the image file to display Step7: Click "open" button in browser Step8: Click "add" | 2020-06-06 | Như Phương | open | Anh Minh | 2020-06-06 | mediu m
| #23 | Interface "View account information" system displays the list of accounts in AZ order of staff codes |  | 4 | Step1: Admin login to Real Estate WebAdmin with admin account Step2: On the homepage, click "manage account" | 2020-06-06 | Như Phương | open | Anh Minh |  | low
18 | #24 | The function "search account" user enters blank characters but does not show the message "account not found" |  | 4 | Step1: admin login to the Real Estate App with personal account Step2: On the home page, click on "Account management" Step3: In the Account management section, click the account Step4: Enter the characters blank into the search bar | 2020-06-06 | Như Phương | open | Anh Minh |  | medium
19 | #25 | function "search account" the user enters the first character but the system does not display suggestions |  | 4 | Step1: admin login to the Real Estate App with personal account Step2: On the home page, click on "Account management" Step3: In the Account management section, click the account Step4: Enter the characters Firstly | 2020-06-06 | Như Phương | open | Anh Minh |  | low
20 | #26 | The function of "adding accounts" in the interface of adding accounts when users select rooms, the system has not yet selected the corresponding group |  | 4 | Step1: Admin login to Real Estate WebAdmin with admin account Step2: On the homepage, click "manage account" Step3: Click "Add account" button Step4: Enter account information Step5: Select department | 2020-06-06 | Như Phương | open | Anh Minh |  | medium
21 | #27
22 | #28
23 | #29
24 | #30
25 | #31
26 | #27
27 | #28
28 | #29
29 | #30
30 | #31