## Cover
Project: Capstone Project_Quản Lý Cty Bất Động Sản
Team Development : Hello World
Mentor: Mr . Đặng Đình Hòa
Document: Defect Log
Purpose: This document is used to classify the defect, how they are prioritizied, date raise defect and date closed
Version History
| Version | Date | Author | Comment
| 1 | 2019-04-04 | Như phương | Create document
| 1.1 | 2019-11-04 | Như phương | Update document
| 1.2 | 2019-12-04 | Như phương | Update defect
| 1.3 |  | Như phương | Update defect
| 1.4 |  | Như phương | Update defect
| 1.5 |  | Như phương | Update defect
| 1.6 |  | Như phương | Update defect
| 1.7 |  | Như phương | Update defect

## Defect Log
DEFECT LOG
NO. | DEFECT ID | DEFECT DESCRIPTION | REFERENCE | VERSION | STEPS | DATE RASISED | DETECTED BY | STATUS | FIXED BY | DATE CLOSED | PRIORITY
1 | #1 | giao diện" xem kết quả kinh doanh tuần " hệ thống không cho người dùng trượt trên màn hình nên đối với các màn hình nhỏ sẽ không thể xem hết kết quả kinh doanh |  | 1 | step1 : người dùng đăng nhập vào app bằng tài khoản nhân viên step 2 : nhấn chọn " báo cáo thống kê " step 3 : chọn " xem kết quả kinh doanh tuần " | 28/5/2020 | Như phuong | open | Quang Vương | 2020-06-06 | medium
2 | #2 | giao diện" xem kết quả kinh doanh tuần " khi có cùng kết quả kinh doanh nhưng không được xếp chung 1 xếp hạng |  | 1 | step1 : người dùng đăng nhập vào app bằng tài khoản nhân viên step 2 : nhấn chọn " báo cáo thống kê " step 3 : chọn " xem kết quả kinh doanh tuần " | 28/5/2020 | Như phuong | open | Quang Vương |  | medium
3 | #3 | [9 empty] | High
4 | #4 | [9 empty] | Medium
5 | #5 | [9 empty] | Medium
6 | #6 | [9 empty] | low
7 | #7 | [9 empty] | low
8 | #8 | [9 empty] | High
9 | #9 | [9 empty] | medium
10 | #10 | [9 empty] | medium
11 | #11 | [9 empty] | medium
12 | #12 | [9 empty] | High
13 | #13 | [9 empty] | medium
14 | #14 | [9 empty] | medium
15 | #15 | [9 empty] | medium
11 | #16 | [9 empty] | high
| #17 | [9 empty] | High
| #18 | [9 empty] | High
| #19 | [9 empty] | High
18 | #19
19 | #20
20 | #21
21 | #22
22 | #23
23 | #24
24 | #25
25 | #26
26 | #27
27 | #28
28 | #29
29 | #30
30 | #31